## Gannt
ERPC PROJECT
SL. No. | ACTIVITY NAME | DURATION (WEEKS) | APR '16 | MAY '16 | JUN '16 | JULY '16 | AUG '16 | SEP '16 | OCT '16 | NOV '16 | DEC '16 | JAN '17 | FEB '17 | MAR '17 | APR '17
1 | DPR SUBMISSION | 2
2 | DATA BASE CASE | 2
3 | OPERATIONAL LOAD FLOW AND SCS | 6
4 | PILOT STATE (ODISHA)
4.1 | DATA COLLECTION | 20 |  |  | List of substations visited'!A1
4.2 | SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES | 20 |  |  |  | database and SLD preparation'!A1
5 | WB&SIKKIM
5.1 | DATA COLLECTION | 26
5.2 | SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES | 30
6 | BIHAR&JHARKHAND
6.1 | DATA COLLECTION | 26 |  |  |  |  | List of SS visited JHARKHAND'!A1
6.2 | SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES | 30
7 | SERVER ROOM COMPLETION
8 | SUPPLY INSTALLATION OF SERVER | 4
9 | SUPPLY INSTALLATION OF PDMS | 2
10 | SAT OF PILOT STATE | 4
11 | POPULATING ALL DATA IN SERVER | 20
12 | TRAINING PROGRAM PDMS | 4
13 | DELIVERY OF 32 NOS. PSCT LICENSE | 18
14 | TRAINING PROGRAM PSCT | 12
15 | FINAL DISCUSS. & COMME. | 2
16 | FINAL ACCEPTANCE
Completed
In progress
Yet to commence
Same Day Completion
Final milestone

## Detailed activities
SL. NO. | MILESTONES | Activities / Sub Activities |  |  |  | Start week / date |  | Expected completion week / date |  | Completion Week/date
|  | PSS | Software | R&D | IT | [6 empty] | Completed
1 | DPR SUBMISSION | Completed |  |  |  | Week 3 | 15.4.16 | Week 4 | 30.4.16 | Week 4 | 30.4.16 | Next Milestone
2 | OPERATIONAL LOAD FLOW AND SCS | Completed |  |  |  | Week 3 | 15.4.16 | Week 11 | 15.6.16 | week 13 | 30.6.16
3 | DATA COLLECTION, SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES - PILOT STATE | 1. Data Collection completed for Odisha except for three stations. 2. For 75 stations few numerical relay data to be received by email. Followup in progress. 3. Database and GUI preparation for bus breaker modelling in progress, 50 stations completed till date. 4. PDMS relay data entry in progress. | Relay Data template preparation in progress | Bus breaker modeling template finalization |  | Week 10 | 7.6.16 | Week 31 | 31.10.16
3 | DATA COLLECTION, SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES - OTHER STATE | 1. Data collected for all stations in Sikkim except numerical relay data. 2. Data collection for jharkhand is in progress. Data for 20 stations has been collected. 3. For 13 stations few numerical relay data and generator details yet to be received. | Relay Data template preparation in progress |  |  |  |  | Week 50 | 15.3.17
4 | SUPPLY INSTALLATION OF SERVER |  |  |  | Hardware specification finalization done. System installed In ERPC office for initial level application configuration. |  |  | Week 26 | 30.9.16
5 | SUPPLY INSTALLATION OF PDMS |  | Application to report network changes(DMNS) is installed in ERPC system.DMNS User names will be provided to all substation incharges . |  |  |  |  | Week 29 | 15.10.16
6 | SAT OF PILOT STATE | [6 empty] | Week 35 | 30.11.16
7 | POPULATING ALL DATA IN SERVER | [6 empty] | Week 50 | 15.3.17
8 | DELIVERY OF 32 NOS. PSCT LICENSE | [6 empty] | Week 41 | 15.1.17
9 | COMPLETION OF TRAINING PROGRAM | [6 empty] | Week 52 | 31.3.17

## List of SS visited ODISHA
Sl.No. | Date of visit | Station name | Owner | Status
1 | 2016-06-08 | Mendhasal | OPTCL | COMPLETED
2 | 2016-06-08 | Chandaka | OPTCL | COMPLETED
3 | 2016-06-09 | Meramundali | OPTCL/PGCIL | COMPLETED
4 | 2016-06-09 | Atri | OPTCL | COMPLETED
5 | 2016-06-09 | Khurda | OPTCL | COMPLETED
6 | 2016-06-10 | Bidanasi | OPTCL | COMPLETED
7 | 2016-06-10 | Nayagarh | OPTCL | COMPLETED
8 | 2016-06-10 | Bhanjanagar | OPTCL | COMPLETED
9 | 2016-06-11 | Narendrapur | OPTCL | COMPLETED
10 | 2016-06-11 | Cuttack | OPTCL | COMPLETED
11 | 2016-06-12 | Aska | OPTCL | COMPLETED
12 | 2016-06-12 | Purusottampur | OPTCL | COMPLETED
13 | 2016-06-13 | Angul 765 | PGCIL | COMPLETED
14 | 2016-06-13 | Angul 132 | OPTCL | COMPLETED
15 | 2016-06-13 | Berhampore | OPTCL | COMPLETED
16 | 2016-06-14 | Chhatrapur | OPTCL | COMPLETED
17 | 2016-06-14 | JITPL (Derang) | JITPL | NR and Generator data pending
18 | 2016-06-15 | GMR Kamalanga TPS | GMR | COMPLETED
19 | 2016-06-15 | Jindal steel and power Ltd. (Angul) | JSPL | COMPLETED
20 | 2016-06-16 | Talcher(old) TPS | NTPC | COMPLETED
21 | 2016-06-16 | Talcher STPS | NTPC | NR and Generator data pending
22 | 2016-06-17 | Mohana | OPTCL | COMPLETED
23 | 2016-06-17 | Daipahari( Digapandi) | OPTCL | COMPLETED
24 | 2016-06-20 | Bhshan steel | Bhshan steel | Numerical relay data
25 | 2016-06-20 | Rengali 220 | OPTCL | COMPLETED
26 | 2016-06-20 | Balugaon | OPTCL | COMPLETED
27 | 2016-06-20 | Chandpur | OPTCL | numerical relay data pending
28 | 2016-06-21 | Nandira | rungta mines | COMPLETED
29 | 2016-06-21 | Chaipal | OPTCL | numerical relay data pending
30 | 2016-06-21 | Rengali | OHPC | COMPLETED
31 | 2016-06-21 | P.khemundi | OPTCL | COMPLETED
32 | 2016-06-22 | Boinda | OPTCL | numerical relay data pending
33 | 2016-06-22 | Akshusirgha | OPTCL | COMPLETED
34 | 2016-06-23 | OPCL | OPCL | Generator details and Numerical relay data pending
35 | 2016-06-23 | NBVL | NBVL | NR data pending
36 | 2016-06-23 | ferro alloy |  | Closed
37 | 2016-06-24 | BRG | BRG | numerical relay data pending
38 | 2016-06-24 | FCI | FCI | COMPLETED
39 | 2016-06-24 | Raygoda | OPTCL | COMPLETED
40 | 2016-06-25 | Rairakhol | OPTCL | COMPLETED
41 | 2016-06-25 | Rengali | PGCIL | NR data for one relay SEL relay pending
42 | 2016-06-25 | J K pur | J K pur | COMPLETED
43 | 2016-06-27 | Chiplima | OHPC | COMPLETED
44 | 2016-06-27 | Rairangpur | OPTCL | data pending for 2 relays
45 | 2016-06-27 | Theruballi | OPTCL | COMPLETED
46 | 2016-06-28 | Burla | OHPC | COMPLETED
47 | 2016-06-28 | Bangir | OPTCL | not charged
48 | 2016-06-28 | Baripada | OPTCL | Micom and seimens data pending
49 | 2016-06-28 | Laxmipur S/W | OPTCL | COMPLETED
50 | 2016-06-29 | ACC | ACC | COMPLETED
51 | 2016-06-29 | Bargarh | OPTCL | 3 NR data to be received
52 | 2016-06-29 | Baripada | PGCIL | 17 NR data pending
53 | 2016-06-29 | Vedanta | Vedanta | COMPLETED
54 | 2016-06-30 | Katapalli | OPTCL | NR data pending
55 | 2016-06-30 | Balasore | OPTCL | 7 NR relays data pending
56 | 2016-06-30 | Sunabeda | OPTCL | COMPLETED
57 | 2016-07-01 | Barpali | OPTCL | NR data pending
58 | 2016-07-01 | Sambalpur | OPTCL | NR data pending
59 | 2016-07-01 | Soro | OPTCL | ABB relay data pending
60 | 2016-07-01 | HAL | HAL | COMPLETED
61 | 2016-07-01 | Dabugaon | OPTCL | numerical data pending
62 | 2016-07-02 | Hindalco | Hindalco | NR relays to be received
63 | 2016-07-02 | Birla TY | Birla TY | COMPLETED
64 | 2016-07-04 | Aditya alluminium | Aditya alluminium | COMPLETED
65 | 2016-07-04 | ISPAT alloys(balasore) | ISPAT alloys | Numerical relay data pending
66 | 2016-07-04 | BLS-B s/w stn(somnathpur) | OPTCL | COMPLETED
67 | 2016-07-04 | Upper kolab | OHPC | COMPLETED
68 | 2016-07-05 | SF alloys | SF alloys | Station Closed
69 | 05.07.2016 | Jharsuguda | OPTCL | COMPLETED
70 |  | Muchkund | OHPC | COMPLETED
71 | 06.07.2016 | Jharsuguda | PGCIL | COMPLETED
72 |  | Emmami | Emmami | COMPLETED
73 |  | JAYPORE | PGCIL | COMPLETED
74 | 07.07.2016 | Vedanta | Vedanta | COMPLETED
75 |  | Basta | OPTCL | COMPLETED
76 |  | jaleshwar | OPTCL | COMPLETED
77 | 08.07.2016 | SMC | SMC | COMPLETED
78 |  | udala | OPTCL | Under Commissioning
79 | 09.07.2016 | Action ISPAT | Action ISPAT | NR data to be received
80 |  | Bhadrak | OPTCL | COMPLETED
81 |  | UMERKOTE | OPTCL | COMPLETED
82 |  | TENTULIKHUNTI | OPTCL | COMPLETED
83 | 11.07.2016 | Shayam dri | Shayam dri | Generator Relay data to be received
84 |  | Facor | Facor | NR data to be received
85 |  | MEENAKSHI | OWN | COMPLETED
86 | 12.07.2016 | Budipatar | OPTCL | COMPLETED
87 |  | Dhamra | Adani Group | Postponed (Visiting permission not cleared)
88 |  | UTKAL ALUMINA | UTKAL ALUMINA | COMPLETED
89 | 13.07.2016 | IB valley | OPGC | COMPLETED
90 |  | Anandpur | OPTCL | COMPLETED
91 |  | BALIMELA | OHPC | COMPLETED
92 | 14.07.2016 | Brajranagar | OPTCL | COMPLETED
93 |  | Duburi | OPTCL | COMPLETED
94 |  | INDIRAVATI | PGCIL | COMPLETED
95 | 15.07.2016 | Lapanga | OPTCL | COMPLETED
96 |  | Rohit | Rohit | COMPLETED
97 |  | UPPER INDIRAVATI | OHPC | COMPLETED
98 | 16.07.2016 | Bhushan steel | Bhushan steel | NR and GENERATOR DATA TO BE RECEIVED
99 |  | Jajpur rd | OPTCL | COMPLETED
100 |  | JFAL | JFAL | COMPLETED
101 |  | JUNAGARH | OPTCL | RELAY DATA NOT RECIVED
102 |  | BHAWANIPATNA | OPTCL | RELAY DATA NOT RECIVED
103 | 18/07/2016 | Sundargarh | OPTCL | NR data to be received
104 |  | JSL | JSL | COMPLETED
105 |  | SAINTALA | OPTCL | COMPLETED
106 |  | KESINGHA | OPTCL | NR data to be received
107 | 19/7/2016 | Visa | Visa | COMPLETED
108 |  | NUAPADA | OPTCL | COMPLETED
109 |  | KHERIAR | OPTCL | COMPLETED
110 | 20/7/2016 | MINL | MINL | NR data to be received
111 |  | POWMAX | OWN | COMPLETED
112 | 2016-07-21 | Aryan ISPAT | Aryan ISPAT | Generator Relay data to be received
113 |  | NINL | NINL | NR data to be received
114 |  | PADAMPUR | OPTCL | COMPLETED
115 |  | PATNAGARH | OPTCL | COMPLETED
116 |  | BOLANGIR (OLD) | OPTCL | COMPLETED
117 | 22.07.2016 | NEW BOLANGIR | pgcil | NR data to be received
118 |  | BOLANGIR | PGCIL | COMPLETED
119 |  | IND bharat | IND bharat | NR and GENERATOR DATA TO BE RECEIVED
120 |  | Kuchinda | OPTCL | NR data to be received
121 |  | Kalrangi | OPTCL | COMPLETED
122 |  | K.nagar | OPTCL | NR data to be received
123 | 23.07.2016 | Cemco | Cemco | COMPLETED
124 |  | MESCO | MESCO | Under Commissioning
125 |  | SONEPUR | OPTCL | NR data to be received
126 |  | BOUDH | OPTCL | NR data to be received
127 | 25/07/2016 | Rourkela 132kV | OPTCL | NR data to be received
128 |  | Chend | OPTCL | NR data to be received
129 |  | New Duburi | PGCIL/OPTCL | NR data to be received
130 | 26.07.2016 | Jajpur TW | OPTCL | COMPLETED
131 |  | Rajgangpur | OPTCL | NR data to be received
132 |  | kalunga | OPTCL | NR data to be received
133 | 2016-07-27 | Chandiknol | OPTCL | COMPLETED
134 |  | Kendapara |  | COMPLETED
135 |  | Marsaghai |  | COMPLETED
136 |  | Tarkera | OPTCL | NR data to be received
137 | 28.07.2016 | RourkelLa | PGCIL | COMPLETED
138 |  | BC Mohanti | BC Mohanti | COMPLETED
139 |  | Brahmanipal/BRPL | OPTCL | COMPLETED
140 |  | PHULNAKHARA | OPTCL | COMPLETED
141 |  | BHUBANESWAR | OPTCL | NR data to be received
142 | 29.07.2016 | Adhunik metals | Adhunik metals | NR and GENERATOR DATA TO BE RECEIVED
143 |  | sri ganesh | sri ganesh | COMPLETED
144 |  | Tata Ferocrom | Tata Group of Co. | COMPLETED
145 |  | R.S PUR | OPTCL | NR data to be received
146 |  | KESURA | OPTCL | NR data to be received
147 | 30.07.2016 | OCL | OCL/OPTCL | COMPLETED
148 |  | bppl (lilo) | bppl (lilo) | NR data to be received
149 |  | ts alloy | ts alloy | NR data to be received
150 | 31.07.2016 | arti steel | arti steel | COMPLETED
151 |  | bppl | bppl | NR data to be received
152 | 01.08.2017 | argul | OPTCL | COMPLETED
153 |  | barkot | OPTCL | NR data to be received
154 | 02.08.2018 | Naupanta | OPTCL | COMPLETED
155 |  | ICCL | ICCL | COMPLETED
156 |  | Chowduar | OPTCL | COMPLETED
157 | 03.08.2018 | Salepur | OPTCL | COMPLETED
158 |  | OCL | OCL | COMPLETED
159 |  | konark | OPTCL | NR data to be received
160 |  | nimapara | OPTCL | NR data to be received
161 | 04.08.2018 | RSP | RSP | COMPLETED
162 |  | Dhenkanal | OPTCL | NR data to be received
163 |  | samuka | OPTCL | NR data to be received
164 |  | puri | OPTCL | NR data to be received
165 | 05.08.2018 | Pattamundai | OPTCL | COMPLETED
166 |  | Jagatsinghpur | OPTCL | COMPLETED
167 |  | samangara | OPTCL | NR data to be received
168 | 06.08.2018 | JODA | OPTCL | NR data to be received
169 |  | TSIL | TSIL | NR and GENERATOR DATA TO BE RECEIVED
170 |  | Paradip | OPTCL | NR data to be received
171 |  | phulbani | OPTCL | COMPLETED
172 | 08.08.2018 | Arya | Arya | NR data to be received
173 |  | B.k steel | B.k steel | COMPLETED
174 |  | BRG | BRG | NR data to be received
175 |  | BRPL | BRPL | NR data to be received
176 |  | Misrilal | Misrilal | NR data to be received
177 |  | kharagprasad | OPTCL | NR data to be received
178 | 09.08.2018 | JSPL | JSPL | COMPLETED
179 |  | ESSAR | ESSAR | NR data to be received
180 |  | MSP | MSP | NR data to be received
181 |  | P ponga | OPTCL | NR data to be received
182 |  | Tata Steel | Tata Group | COMPLETED
183 |  | nalco | nalco | COMPLETED
184 | 10.08.2018 | kaniha hvdc | PGCIL | COMPLETED
185 |  | Keonjhar | PGCIL | COMPLETED
186 | 11.08.2018 | Karanjia | OPTCL | NR data to be received
187 |  | IMFA | IMFA | COMPLETED
188 | 12.08.2018 | Barbil | OPTCL | NR data to be received
189 |  | Bolani | OPTCL | NR data to be received
190 | 13.08.2018 | FAP | FAP | COMPLETED
191 | 16.08.2016 | IFFCO | IFFCO | NR data to be received
192 | 17.08.2016 | ESSAR steel | ESSAR steel | COMPLETED
193 | 18.08.2016 | IOCL | IOCL | COMPLETED
194 | 23.08.2016 | FACOR STEEL | FACOR STEEL | COMPLETED

## List of SS visited JHARKHAND
Sl.No. | Date of visit | Station name | Owner | Status
1 | 2016-08-18 | Hatia-Old_132KV | JUSNL | numerical relay data pending
2 | 2016-08-18 | Hatia_New_220/132kV | JUSNL | numerical relay data pending
3 | 2016-08-19 | PTPS_1Gen | State | numerical relay data pending
4 | 2016-08-20 | Gumla_132KV | JUSNL | numerical relay data pending
5 | 2016-08-22 | Kanke_132kV | JUSNL | numerical relay data pending
6 |  | TVNL | TVNL | COMPLETED
7 | 2016-08-23 | Ranchi new_765kV | PGCIL | COMPLETED
8 |  | BTPS_A/BOKARO_D 400KV | DVC | AVR & TURBINE DATA PENDING
9 | 2016-08-24 | Chandwa JHK POOL | PGCIL | COMPLETED
10 |  | BTPS-B DVC_220/132kV | DVC | NR DATA & GOVERNER DATA PENDING
11 | 2016-08-25 | Ranchi_400/220 kV | PGCIL | COMPLETED
12 | 2016-08-26 | Namkum_132KV | JUSNL | numerical relay data pending
13 |  | CTPS-New-DVC_220kV | DVC | AVR, TURBINE AND NR DATA PENDING
14 | 2016-08-27 | Usha martin 132kV_GEN | Usha Martin(CPP) | numerical relay data pending
15 | 2016-08-29 | HEC 132 | HEC 132 | COMPLETED
16 |  | CTPS-OLD-DVC_220kV | DVC | NUmerical relay & GENERATOR data pending
17 | 2016-08-30 | Lohardaga_132KV | JUSNL | numerical relay data pending
18 |  | Putki-DVC_132kV | DVC | COMPLETED
19 | 2016-08-31 | Kamdara_132KV | JUSNL | numerical relay data pending
20 |  | Biada_DVC132kV | DVC | COMPLETED

## List of SS visited SIKKIM
Sl. No. | Voltage | Station Name | Owner | Status
1 | 400 | Rangpo | PGCIL | Collected
2 | 220 | Samardang | PGCIL | Collected
3 | 220 | New Melli | PGCIL | Collected
4 | 132 | Gantok | PGCIL | Collected
5 | 132 | Melli | SIKKIM | Collected (except numerical relay)
6 | 132 | Geyzing | SIKKIM | Collected (except numerical relay)
7 | 66 | Bulbuley | SIKKIM | Collected (except numerical relay)
8 | 66 | Geyzing | SIKKIM | Collected (except numerical relay)
9 | 66 | Mangan | SIKKIM | Collected (except numerical relay)
10 | 66 | Melli | SIKKIM | Collected (except numerical relay)
11 | 66 | Namchi | SIKKIM | Collected (except numerical relay)
12 | 66 | Pelling | SIKKIM | Collected (except numerical relay)
13 | 66 | Phodong | SIKKIM | Collected (except numerical relay)
14 |  | Pakyong | SIKKIM | Collected (except numerical relay)
15 | 66 | Rhenock | SIKKIM | Collected (except numerical relay)
16 | 66 | Rongly | SIKKIM | Collected (except numerical relay)
17 | 66 | Rothak | SIKKIM | Collected (except numerical relay)
18 | 66 | Sichey | SIKKIM | Collected (except numerical relay)
19 | 66 | Soreng |  | Collected (except numerical relay)
20 | 66 | Tadong | SIKKIM | Collected (except numerical relay)
21 | 66 | LLHP,Ranipool | SIKKIM | Collected (except numerical relay)
22 | 66 | Lingdok,SKPPL | SIKKIM | Collected (except numerical relay)
23 | Gen | Jorethang Loop |  | Collected
24 | Gen | Rangit HPS |  | Collected
25 | Gen | Teesta V HPS |  | Collected
26 | Gen | LLHP HEP |  | Collected (except numerical relay)
27 | Gen | Meyongchu Hep |  | Collected (except numerical relay)

## database and SLD preparation
Sl. No. | State | Substation Name (with Voltage Level) | Database Modeling |  |  | SLD Preparation
|  |  | Start Date (dd.mm.yy) | End Date (dd.mm.yy) | Status | Start Date (dd.mm.yy) | End Date (dd.mm.yy) | Status
1 | Odisha | DIGAPAHANDI(132/33kV) | 27/7/2016 | 2016-05-08 | Completed | 27/7/2016 | 2016-05-08 | Completed
2 | Odisha | MOHANA(132/33kV) | 27/7/2016 | 2016-05-08 | Completed | 27/7/2016 | 2016-05-08 | Completed
3 | Odisha | ASKA(132/33kV) | 27/7/2016 | 2016-05-08 | Completed | 27/7/2016 | 2016-05-08 | Completed
4 | Odisha | Khurda(220/33) | 27/7/2016 | 2016-05-08 | Completed | 27/7/2016 | 2016-05-08 | Completed
5 | Odisha | GMR(400/20kV) | 27/7/2016 | 2016-05-08 | Completed | 27/7/2016 | 2016-05-08 | Completed
6 | Odisha | NAYAGARH(132/33kV) | 27/7/2016 | 2016-05-08 | Completed | 27/7/2016 | 2016-05-08 | Completed
7 | Odisha | CHAINPAL(220/132kV) | 27/7/2016 | 2016-05-08 | Completed | 27/7/2016 | 2016-05-08 | Completed
8 | Odisha | TTPS(220/132kV) | 27/7/2016 | 2016-05-08 | Completed | 27/7/2016 | 2016-05-08 | Completed
9 | Odisha | ATRI(220/132/33kV) | 2016-01-08 | 2016-05-08 | Completed | 2016-01-08 | 2016-05-08 | Completed
10 | Odisha | MENDHASAL(400/220/132Kv) | 2016-01-08 | 2016-05-08 | Completed | 2016-01-08 | 2016-05-08 | Completed
11 | Odisha | BIDANASI(220/132/33kV) | 2016-01-08 | 2016-05-08 | Completed | 2016-01-08 | 2016-05-08 | Completed
12 | Odisha | BRG STEELS(220/11kV) | 2016-01-08 | 2016-05-08 | Completed | 2016-01-08 | 2016-05-08 | Completed
13 | Odisha | BHANJANAGAR(220/132kV) | 2016-01-08 | 2016-05-08 | Completed | 2016-01-08 | 2016-05-08 | Completed
14 | Odisha | DUBURI (220/132/33kV) | 2016-01-08 | 2016-05-08 | Completed | 2016-01-08 | 2016-05-08 | Completed
15 | Odisha | CHandaka(220/132kV) | 2016-01-08 | 2016-05-08 | Completed | 2016-01-08 | 2016-05-08 | Completed
16 | Odisha | ANGUL(765/400KV) | 2016-05-08 | 2016-08-08 | Completed | 2016-05-08 | 2016-08-08 | Completed
17 | Odisha | TSTPS(400/220kV) | 2016-05-08 | 2016-08-08 | Completed | 2016-05-08 | 2016-08-08 | Completed
18 | Odisha | MERAMANDALI(400/220KV) | 2016-05-08 | 2016-08-08 | Completed | 2016-05-08 | 2016-08-08 | Completed
19 | Odisha | AKUSINGHI(132KV/33KV) | 2016-09-08 | 2016-12-08 | Completed | 2016-09-08 | 2016-12-08 | Completed
20 | Odisha | Sambalpur(132/33KV) | 2016-09-09 | 2016-12-08 | Completed | 2016-09-09 | 2016-12-08 | Completed
21 | Odisha | NARENDRAPUR(220/132/33KV) | 2016-09-10 | 2016-12-08 | Completed | 2016-09-10 | 2016-12-08 | Completed
22 | Odisha | NANIDRA (132/33KV) | 2016-09-11 | 2016-12-08 | Completed | 2016-09-11 | 2016-12-08 | Completed
23 | Odisha | SUNABEDA(132/33KV) | 2016-09-12 | 2016-12-08 | Completed | 2016-09-12 | 2016-12-08 | Completed
24 | Odisha | Paralakhemundi(132/33KV) | 2016-09-13 | 19/8/2016 | Completed | 2016-09-13 | 19/8/2016 | Completed
26 | Odisha | Balugaon(132/33KV) | 2016-09-14 | 19/8/2016 | Completed | 2016-09-14 | 19/8/2016 | Completed
27 | Odisha | BONIDA(132/33KV) | 2016-09-15 | 19/8/2016 | Completed | 2016-09-15 | 19/8/2016 | Completed
28 | Odisha | BARIPADA(132/33) | 2016-09-16 | 19/8/2016 | Completed | 2016-09-16 | 19/8/2016 | Completed
29 | Odisha | PUROSOTTAMPUR | 2016-09-17 | 19/8/2016 | Completed | 2016-09-17 | 19/8/2016 | Completed
30 | Odisha | KarakPrasad(132kV) | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
31 | Odisha | Arti Steel(132/11kV) | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
32 | Odisha | NBVL(132/11kV) | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
33 | Odisha | Kuchei/Baripada(PGCIL)400/220/132kV | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
34 | Odisha | Dhenkanal(132/33kV) | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
35 | Odisha | New Duri (400/220kV) | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
36 | Odisha | NALCO | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
37 | Odisha | SEL | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
38 | Odisha | JSPL | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
39 | Odisha | ML Rungtna (Nadira)132/33kV | 15/08/2016 | 22/8/2016 | Completed | 15/08/2016 | 22/8/2016 | Completed
40 | Odisha | Barapalli(132/33kV) | 22/08/2016 | 26/8/2016 | Completed | 22/08/2016 | 26/8/2016 | Completed
41 | Odisha | Basta(132/33kV) | 22/08/2016 | 26/8/2016 | Completed | 22/08/2016 | 26/8/2016 | Completed
42 | Odisha | Chhend(132/33kV) | 22/08/2016 | 26/8/2016 | Completed | 22/08/2016 | 26/8/2016 | Completed
43 | Odisha | Jaipur Town(132/33kV) | 22/08/2016 | 26/8/2016 | Completed | 22/08/2016 | 26/8/2016 | Completed
44 | Odisha | Jaleswar(132/33kV) | 22/08/2016 | 26/8/2016 | Completed | 22/08/2016 | 26/8/2016 | Completed
45 | Odisha | Kalarangi(132/33kV) | 22/08/2016 | 26/8/2016 | Completed | 22/08/2016 | 26/8/2016 | Completed
46 | Odisha | Cuttack(132/33) | 22/08/2017 | 26/8/2017 | Completed | 22/08/2017 | 26/8/2017 | Completed
47 | Odisha | Bargarh(132/33) | 22/08/2018 | 26/8/2018 | Completed | 22/08/2018 | 26/8/2018 | Completed
48 | Odisha | SMC | 29/8/2016 | 2016-02-09 | Under Progress | 29/8/2016 | 2016-02-09 | Not Completed
49 | Odisha | BEEKAY STEEL | 29/8/2017 | 2016-02-10 | Under Progress | 29/8/2017 | 2016-02-10 | Not Completed
50 | Odisha | KARANJIA | 29/8/2018 | 2016-02-11 | Under Progress | 29/8/2018 | 2016-02-11 | Not Completed
51 | Odisha | ULTRATECH | 29/8/2019 | 2016-02-12 | Under Progress | 29/8/2019 | 2016-02-12 | Not Completed
52 | Odisha | JSPL | 29/8/2020 | 2016-02-13 | Under Progress | 29/8/2020 | 2016-02-13 | Not Completed
53 | Odisha | PADAMPUR | 29/8/2021 | 2016-02-14 | Under Progress | 29/8/2021 | 2016-02-14 | Not Completed
54 | Odisha | RAJGANGPUR(132/33) | 29/8/2022 | 2016-02-15 | Completed | 29/8/2022 | 2016-02-15 | Not Completed
55 | Odisha | SUNDARGARH(132/33) | 29/8/2023 | 2016-02-16 | Completed | 29/8/2023 | 2016-02-16 | Not Completed