## Gannt
ERPC PROJECT
SL. No. | ACTIVITY NAME | DURATION (WEEKS) | APR '16 | MAY '16 | JUN '16 | JULY '16 |  | AUG '16 | SEP '16 | OCT '16 | NOV '16 | DEC '16 | JAN '17 | FEB '17 | MAR '17 | APR '17
1 | DPR SUBMISSION | 2
2 | DATA BASE CASE | 2
3 | OPERATIONAL LOAD FLOW AND SCS | 6
4 | PILOT STATE (ODISHA)
4.1 | DATA COLLECTION | 20 |  |  | List of substations visited'!A1
4.2 | SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES | 20 |  |  |  | database and SLD preparation'!A1
5 | WB&SIKKIM
5.1 | DATA COLLECTION | 26 |  |  |  |  | List of SS visited West Bengal
5.2 | SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES | 30
6 | BIHAR&JHARKHAND
6.1 | DATA COLLECTION | 26 | [5 empty] | List of SS visited JHARKHAND'!A1
6.2 | SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES | 30
7 | SERVER ROOM COMPLETION
8 | SUPPLY INSTALLATION OF SERVER | 4
9 | SUPPLY INSTALLATION OF PDMS | 2
10 | SAT OF PILOT STATE | 4
11 | POPULATING ALL DATA IN SERVER | 20
12 | TRAINING PROGRAM PDMS | 4
13 | DELIVERY OF 32 NOS. PSCT LICENSE | 18
14 | TRAINING PROGRAM PSCT | 12
15 | FINAL DISCUSS. & COMME. | 2
16 | FINAL ACCEPTANCE
Completed
In progress
Yet to commence
Same Day Completion
Final milestone
Extended

## Detailed activities
SL. NO. | MILESTONES | Activities / Sub Activities |  |  |  | Start week / date |  | Expected completion week / date |  | Completion Week/date
|  | PSS | Software | R&D | IT | [6 empty] | Completed
1 | DPR SUBMISSION | Completed |  |  |  | Week 3 | 15.4.16 | Week 4 | 30.4.16 | Week 4 | 30.4.16 | Next Milestone
2 | OPERATIONAL LOAD FLOW AND SCS | Completed |  |  |  | Week 3 | 15.4.16 | Week 11 | 15.6.16 | week 13 | 30.6.16
3 | DATA COLLECTION, SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES - PILOT STATE | 1. Data Collection completed for Odisha except for three stations. 2. For 35 stations few numerical relay data to be received by email. Followup in progress. 3. Database and GUI preparation for bus breaker modelling in progress, 180 stations completed till date. 4. PDMS relay data entry in progress. 172 stations data uploaded. | Relay Data template preparation for odisha completed. | tripping analysis and software requirement analysis provided by end user during SAT. |  | Week 10 | 7.6.16 | Week 31 | 31.10.16
3 | DATA COLLECTION, SLD PREPARATION, RELAY DATA POPULATION IN PDMS & SYSTEM STUDIES - OTHER STATE | 1. Data collected for all stations in Sikkim except numerical relay data. 2. Data collection for jharkhand is in progress. Data for 93 stations has been collected. Pending numerical relay list submitted to ERPC for necessary action. 3.Data collection forWest Bengal is in progress. Data for193 stations has been collected, numerical relay data for 137 stations received. 4. Plan for Bihar in progress. | Relay Data template preparation in progress |  |  |  |  | Week 50 | 15.3.17
4 | SUPPLY INSTALLATION OF SERVER | Completed | [5 empty] | Week 26 | 30.9.16 | Week 37 | 24.12.16
5 | SUPPLY INSTALLATION OF PDMS | Completed | [5 empty] | Week 29 | 15.10.16 | Week 37 | 24.12.16
6 | SAT OF PILOT STATE | PSCT SAT completed for 70 % fuctionalities | PDMS installed in server. SAT scheduled on 11.1.17 |  |  |  |  | Week 35 | 30.11.16
7 | POPULATING ALL DATA IN SERVER | [6 empty] | Week 50 | 15.3.17
8 | DELIVERY OF 32 NOS. PSCT LICENSE |  | Software license delivered |  |  |  |  | Week 41 | 15.1.17
9 | COMPLETION OF TRAINING PROGRAM |  |  | First level training completed |  |  |  | Week 52 | 31.3.17

## List of SS visited ODISHA
ODISHA
Sl.No. | Date of visit | Station name | Owner | Status
1 | 2016-06-08 | Mendhasal | OPTCL | COMPLETED
2 | 2016-06-08 | Chandaka | OPTCL | COMPLETED
3 | 2016-06-09 | Meramundali | OPTCL/PGCIL | COMPLETED
4 | 2016-06-09 | Atri | OPTCL | COMPLETED
5 | 2016-06-09 | Khurda | OPTCL | COMPLETED
6 | 2016-06-10 | Bidanasi | OPTCL | COMPLETED
7 | 2016-06-10 | Nayagarh | OPTCL | COMPLETED
8 | 2016-06-10 | Bhanjanagar | OPTCL | COMPLETED
9 | 2016-06-11 | Narendrapur | OPTCL | COMPLETED
10 | 2016-06-11 | Cuttack | OPTCL | COMPLETED
11 | 2016-06-12 | Aska | OPTCL | COMPLETED
12 | 2016-06-12 | Purusottampur | OPTCL | COMPLETED
13 | 2016-06-13 | Angul 765 | PGCIL | COMPLETED
14 | 2016-06-13 | Angul 132 | OPTCL | COMPLETED
15 | 2016-06-13 | Berhampore | OPTCL | COMPLETED
16 | 2016-06-14 | Chhatrapur | OPTCL | COMPLETED
17 | 2016-06-14 | JITPL (Derang) | JITPL | RELAY DATA PARTIALLY COLLECTED and Generator data pending
18 | 2016-06-15 | GMR Kamalanga TPS | GMR | COMPLETED
19 | 2016-06-15 | Jindal steel and power Ltd. (Angul) | JSPL | COMPLETED
20 | 2016-06-16 | Talcher(old) TPS | NTPC | COMPLETED
21 | 2016-06-16 | Talcher STPS | NTPC | NR and Generator data pending
22 | 2016-06-17 | Mohana | OPTCL | COMPLETED
23 | 2016-06-17 | Daipahari( Digapandi) | OPTCL | COMPLETED
24 | 2016-06-20 | Bhshan steel | Bhshan steel | Numerical relay data
25 | 2016-06-20 | Rengali 220 | OPTCL | COMPLETED
26 | 2016-06-20 | Balugaon | OPTCL | COMPLETED
27 | 2016-06-20 | Chandpur | OPTCL | numerical relay data pending
28 | 2016-06-21 | Nandira | rungta mines | COMPLETED
29 | 2016-06-21 | Chaipal | OPTCL | numerical relay data pending
30 | 2016-06-21 | Rengali | OHPC | COMPLETED
31 | 2016-06-21 | P.khemundi | OPTCL | COMPLETED
32 | 2016-06-22 | Boinda | OPTCL | numerical relay data pending
33 | 2016-06-22 | Akshusirgha | OPTCL | COMPLETED
34 | 2016-06-23 | OPCL | OPCL | Generator details and Numerical relay data pending
35 | 2016-06-23 | NBVL | NBVL | NR data pending
36 | 2016-06-23 | ferro alloy |  | Closed
37 | 2016-06-24 | BRG | BRG | numerical relay data pending
38 | 2016-06-24 | FCI | FCI | COMPLETED
39 | 2016-06-24 | Raygoda | OPTCL | COMPLETED
40 | 2016-06-25 | Rairakhol | OPTCL | COMPLETED
41 | 2016-06-25 | Rengali | PGCIL | NR data for one relay SEL relay pending
42 | 2016-06-25 | J K pur | J K pur | COMPLETED
43 | 2016-06-27 | Chiplima | OHPC | COMPLETED
44 | 2016-06-27 | Rairangpur | OPTCL | PARTIALLY COLLECTED
45 | 2016-06-27 | Theruballi | OPTCL | COMPLETED
46 | 2016-06-28 | Burla | OHPC | COMPLETED
47 | 2016-06-28 | Bangir | OPTCL | not charged
48 | 2016-06-28 | Baripada | OPTCL | Micom and seimens data pending
49 | 2016-06-28 | Laxmipur S/W | OPTCL | COMPLETED
50 | 2016-06-29 | ACC | ACC | COMPLETED
51 | 2016-06-29 | Bargarh | OPTCL | 3 NR data to be received
52 | 2016-06-29 | Baripada | PGCIL | 17 NR data pending
53 | 2016-06-29 | Vedanta | Vedanta | COMPLETED
54 | 2016-06-30 | Katapalli | OPTCL | PARTIALLY COLLECTED
55 | 2016-06-30 | Balasore | OPTCL | 7 NR relays data pending
56 | 2016-06-30 | Sunabeda | OPTCL | COMPLETED
57 | 2016-07-01 | Barpali | OPTCL | NR data pending
58 | 2016-07-01 | Sambalpur | OPTCL | NR data pending
59 | 2016-07-01 | Soro | OPTCL | ABB relay data pending
60 | 2016-07-01 | HAL | HAL | COMPLETED
61 | 2016-07-01 | Dabugaon | OPTCL | numerical data pending
62 | 2016-07-02 | Hindalco | Hindalco | NR relays to be received
63 | 2016-07-02 | Birla TY | Birla TY | COMPLETED
64 | 2016-07-04 | Aditya alluminium | Aditya alluminium | COMPLETED
65 | 2016-07-04 | ISPAT alloys(balasore) | ISPAT alloys | Numerical relay data pending
66 | 2016-07-04 | BLS-B s/w stn(somnathpur) | OPTCL | COMPLETED
67 | 2016-07-04 | Upper kolab | OHPC | COMPLETED
68 | 2016-07-05 | SF alloys | SF alloys | Station Closed
69 | 05.07.2016 | Jharsuguda | OPTCL | COMPLETED
70 |  | Muchkund | OHPC | COMPLETED
71 | 06.07.2016 | Jharsuguda | PGCIL | COMPLETED
72 |  | Emmami | Emmami | COMPLETED
73 |  | JAYPORE | PGCIL | COMPLETED
74 | 07.07.2016 | Vedanta | Vedanta | COMPLETED
75 |  | Basta | OPTCL | COMPLETED
76 |  | jaleshwar | OPTCL | COMPLETED
77 | 08.07.2016 | SMC | SMC | COMPLETED
78 |  | udala | OPTCL | Under Commissioning
79 | 09.07.2016 | Action ISPAT | Action ISPAT | PARTIALLY COLLECTED
80 |  | Bhadrak | OPTCL | COMPLETED
81 |  | UMERKOTE | OPTCL | COMPLETED
82 |  | TENTULIKHUNTI | OPTCL | COMPLETED
83 | 11.07.2016 | Shayam dri | Shayam dri | Generator Relay data to be received ,PARTIALLY COLLECTED RELAY DATA
84 |  | Facor | Facor | NR data to be received
85 |  | MEENAKSHI | OWN | COMPLETED
86 | 12.07.2016 | Budipatar | OPTCL | COMPLETED
87 |  | Dhamra | Adani Group | Postponed (Visiting permission not cleared)
88 |  | UTKAL ALUMINA | UTKAL ALUMINA | COMPLETED
89 | 13.07.2016 | IB valley | OPGC | COMPLETED
90 |  | Anandpur | OPTCL | COMPLETED
91 |  | BALIMELA | OHPC | COMPLETED
92 | 14.07.2016 | Brajranagar | OPTCL | COMPLETED
93 |  | Duburi | OPTCL | COMPLETED
94 |  | INDIRAVATI | PGCIL | COMPLETED
95 | 15.07.2016 | Lapanga | OPTCL | COMPLETED
96 |  | Rohit | Rohit | COMPLETED
97 |  | UPPER INDIRAVATI | OHPC | COMPLETED
98 | 16.07.2016 | Bhushan steel | Bhushan steel | NR and GENERATOR DATA TO BE RECEIVED
99 |  | Jajpur rd | OPTCL | COMPLETED
100 |  | JFAL | JFAL | COMPLETED
101 |  | JUNAGARH | OPTCL | RELAY DATA NOT RECIVED
102 |  | BHAWANIPATNA | OPTCL | PARTIALLY COLLECTED
103 | 18/07/2016 | Sundargarh | OPTCL | PARTIALLY COLLECTED
104 |  | JSL | JSL | COMPLETED
105 |  | SAINTALA | OPTCL | COMPLETED
106 |  | KESINGHA | OPTCL | PARTIALLY COLLECTED
107 | 19/7/2016 | Visa | Visa | COMPLETED
108 |  | NUAPADA | OPTCL | COMPLETED
109 |  | KHERIAR | OPTCL | COMPLETED
110 | 20/7/2016 | MINL | MINL | NR data to be received
111 |  | POWMAX | OWN | COMPLETED
112 | 2016-07-21 | Aryan ISPAT | Aryan ISPAT | Generator Relay data to be received ; PARTIALL COLLECTED RELAY DATA
113 |  | NINL | NINL | NR data to be received
114 |  | PADAMPUR | OPTCL | COMPLETED
115 |  | PATNAGARH | OPTCL | COMPLETED
116 |  | BOLANGIR (OLD) | OPTCL | COMPLETED
117 | 22.07.2016 | NEW BOLANGIR | pgcil | PARTIALLY COLLECTED
118 |  | BOLANGIR | PGCIL | COMPLETED
119 |  | IND bharat | IND bharat | ALL RELAY DATA AND GANERATOR DATA PENDING
120 |  | Kuchinda | OPTCL | NR data to be received
121 |  | Kalrangi | OPTCL | COMPLETED
122 |  | K.nagar | OPTCL | NR data to be received
123 | 23.07.2016 | Cemco | Cemco | COMPLETED
124 |  | SONEPUR | OPTCL | PARTIALLY COLLECTED
125 |  | BOUDH | OPTCL | NR data to be received
126 | 25/07/2016 | Rourkela 132kV | OPTCL | NR data to be received
127 |  | Chend | OPTCL | NR data to be received
128 |  | New Duburi | PGCIL/OPTCL | ONE NUMERICAL RELAY PENDING
129 | 26.07.2016 | Jajpur TW | OPTCL | COMPLETED
130 |  | Rajgangpur | OPTCL | PARTIALLY COLLECTED
131 |  | kalunga | OPTCL | NR data to be received
132 | 2016-07-27 | Chandiknol | OPTCL | COMPLETED
133 |  | Kendapara |  | COMPLETED
134 |  | Marsaghai |  | COMPLETED
135 |  | Tarkera | OPTCL | PARTIALLY COLLECTED
136 | 28.07.2016 | RourkelLa | PGCIL | COMPLETED
137 |  | BC Mohanti | BC Mohanti | COMPLETED
138 |  | Brahmanipal/BRPL | OPTCL | COMPLETED
139 |  | PHULNAKHARA | OPTCL | COMPLETED
140 |  | BHUBANESWAR | OPTCL | NR data to be received
141 | 29.07.2016 | Adhunik metals | Adhunik metals | NR and GENERATOR DATA TO BE RECEIVED
142 |  | sri ganesh | sri ganesh | COMPLETED
143 |  | Tata Ferocrom | Tata Group of Co. | COMPLETED
144 |  | R.S PUR | OPTCL | NR data to be received
145 |  | KESURA | OPTCL | NR data to be received
146 | 30.07.2016 | OCL | OCL/OPTCL | COMPLETED
147 |  | bppl (lilo) | bppl (lilo) | NR data to be received
148 |  | ts alloy | ts alloy | PARTIALLY COLLECTED
149 | 31.07.2016 | arti steel | arti steel | COMPLETED
150 |  | bppl | bppl | NR data to be received
151 | 01.08.2016 | argul | OPTCL | COMPLETED
152 |  | barkot | OPTCL | NR data to be received
153 | 02.08.2016 | Naupanta | OPTCL | COMPLETED
154 |  | ICCL | ICCL | COMPLETED
155 |  | Chowduar | OPTCL | COMPLETED
156 | 03.08.2016 | Salepur | OPTCL | COMPLETED
157 |  | OCL | OCL | COMPLETED
158 |  | konark | OPTCL | COMPLETED
159 |  | nimapara | OPTCL | COMPLETED
160 | 04.08.2016 | RSP | RSP | COMPLETED
161 |  | Dhenkanal | OPTCL | PARTIALLY COLLECTED
162 |  | samuka | OPTCL | COMPLETED
163 |  | puri | OPTCL | COMPLETED
164 | 05.08.2016 | Pattamundai | OPTCL | COMPLETED
165 |  | Jagatsinghpur | OPTCL | COMPLETED
166 |  | samangara | OPTCL | COMPLETED
167 | 06.08.2016 | JODA | OPTCL | RELAY DATA NOT RECIVED
168 |  | TSIL | TSIL | COMPLETED
169 |  | Paradip | OPTCL | NR data to be received
170 |  | phulbani | OPTCL | COMPLETED
171 | 08.08.2016 | Arya | Arya | PARTIALLY COLLECTED
172 |  | B.k steel | B.k steel | COMPLETED
173 |  | BRG | BRG | NR data to be received
174 |  | BRPL | BRPL | NR data to be received
175 |  | Misrilal | Misrilal | NR data to be received
176 |  | kharagprasad | OPTCL | NR data to be received
177 | 09.08.2016 | JSPL | JSPL | COMPLETED
178 |  | ESSAR | ESSAR | PARTIALLY COLLECTED
179 |  | MSP | MSP | PARTIALLY COLLECTED
180 |  | P ponga | OPTCL | NR data to be received
181 |  | Tata Steel | Tata Group | COMPLETED
182 |  | nalco | nalco | COMPLETED
183 | 10.08.2016 | kaniha hvdc | PGCIL | COMPLETED
184 |  | Keonjhar | PGCIL | COMPLETED
185 | 11.08.2016 | Karanjia | OPTCL | NR data to be received
186 |  | IMFA | IMFA | COMPLETED
187 | 12.08.2016 | Barbil | OPTCL | PARTIALLY COLLECTED
188 |  | Bolani | OPTCL | PARTIALLY COLLECTED
189 | 13.08.2016 | FAP | FAP | COMPLETED
190 | 16.08.2016 | IFFCO | IFFCO | PARTIALLY COLLECTED
191 | 17.08.2016 | ESSAR steel | ESSAR steel | COMPLETED
192 | 18.08.2016 | IOCL | IOCL | COMPLETED
193 | 23.08.2016 | FACOR STEEL | FACOR STEEL | COMPLETED
Detailed data pending list(click)
Back

## List of SS visited JHARKHAND
Sl.No. | Date of visit | Station name | Owner | Status
1 | 2016-08-18 | Hatia-Old_132KV | JUSNL | Partially Collected
2 | 2016-08-18 | Hatia_New_220/132kV | JUSNL | Partially Collected
3 | 2016-08-19 | PTPS_1Gen | State | Pending
4 | 2016-08-20 | Gumla_132KV | JUSNL | Pending
5 | 2016-08-22 | Kanke_132kV | JUSNL | Partially Collected
6 |  | TVNL | TVNL | COMPLETED
7 | 2016-08-23 | Ranchi new_765kV | PGCIL | COMPLETED
8 |  | BTPS_A/BOKARO_D 400KV | DVC | AVR & TURBINE DATA PENDING
9 | 2016-08-24 | Chandwa JHK POOL | PGCIL | COMPLETED
10 |  | BTPS-B DVC_220/132kV | DVC | NR DATA PARTIAL COLLECTED & GOVERNER DATA PENDING
11 | 2016-08-25 | Ranchi_400/220 kV | PGCIL | COMPLETED
12 | 2016-08-26 | Namkum_132KV | JUSNL | Partially Collected
13 |  | CTPS-New-DVC_220kV | DVC | NR DATA PARTIAL COLLECTED AVR & TURBINE DATA PENDING
14 | 2016-08-27 | Usha martin 132kV_GEN | Usha Martin(CPP) | COMPLETED
15 |  | Usha martin 132kV | Usha Martin(CPP) | COMPLETED
16 | 2016-08-29 | HEC 132 | HEC 132 | COMPLETED
17 |  | CTPS-OLD-DVC_220kV | DVC | Numerical relay , TURBINE & GENERATOR data pending
18 | 2016-08-30 | Lohardaga_132KV | JUSNL | Partially Collected
19 |  | Putki-DVC_132kV | DVC | Numerical relay data pending
20 | 2016-08-31 | Kamdara_132KV | JUSNL | Partially Collected
21 |  | Biada_DVC132kV | DVC | partial Numerical relay data pending
22 | 2016-09-01 | JSPL | JSPL | Pending
23 |  | Patherdih-DVC_132kV | DVC | partial Numerical relay data pending
24 |  | Sindri-DVC_132kV | DVC | COMPLETED
25 | 2016-09-02 | SIKIDIRI S/S | JUSNL | Pending
26 |  | Dhanbad-DVC_220/132kV | DVC | PARTALLY COLLECTED
27 | 2016-09-03 | SHPS 1 | JUSNL | Pending
28 |  | SHPS 2 | JUSNL | Pending
29 |  | Giridih-DVC_220/132kV | DVC | COMPLETED
30 | 2016-09-05 | Nimighat-DVC_132kV | DVC | COMPLETED
31 | 2016-09-06 | Hazaribagh-DVC_132kV | DVC | Numerical relay data pending
32 | 2016-09-07 | Koderma_400/220/132kV | DVC | COMPLETED
33 |  | Inland powere | JUSNL | Pending
34 | 2016-09-08 | KTPS_Gen_400 | DVC | Generation data pending
35 |  | KTPS_220 | DVC | Pending
36 | 2016-09-09 | Barhi-DVC_132kV | DVC | Partial Numerical relay data pending
37 |  | Koderma-DVC-132kV | DVC | COMPLETED
38 |  | latehar | JUSNL | Partially Collected
39 | 2016-09-10 | Abcil | Aditya Birla | Pending
40 |  | garwa | JUSNL | Partially Collected
41 |  | Tilaiya_DVC_Gen | DVC
42 | 2016-09-12 | Japla | JUSNL | Partially Collected
43 |  | Ramghar-DVC_220/132kV | DVC | COMPLETED
44 | 2016-09-13 | daltongunj | JUSNL | Partially Collected
45 |  | Gola-DVC_132kV | DVC | COMPLETED
46 | 2016-09-14 | Patratu | DVC | COMPLETED
47 | 2016-09-15 | Jamtara | JUSNL | Pending
48 |  | N_Karanpur | DVC | COMPLETED
49 | 2016-09-16 | Mithon | PGCIL | Pending
50 | 2016-09-19 | Deoghar | JUSNL | Pending
51 |  | Mosabini-DVC_132kV | DVC | COMPLETED
52 | 2016-09-20 | Madhupur | JUSNL | Pending
53 |  | Manique_DVC_132 | DVC | COMPLETED
54 | 2016-09-21 | Dumka | JUSNL | Pending
55 |  | Jamshedpur-DVC_220/132kV | DVC | Numerical relay data pending
56 | 2016-09-22 | Pakur | JUSNL | Pending
57 |  | Sahebganj | JUSNL | Pending
58 | 2016-09-23 | Lalmatia | JUSNL | Pending
59 |  | Dhankunda | NTPC | COMPLETED
60 |  | Kalyanswari-DVC_220/132kV | DVC | Numerical relay data pending
61 | 2016-09-24 | Dumka_220 | JUSNL | Pending
62 |  | Kumardhubi-DVC_132kV | DVC | COMPLETED
63 | 2016-09-26 | Jaduguda | JUSNL | Pending
64 |  | Maithaon(MHPS)-DVC_132kV | DVC | Numerical relay data pending
65 |  | MaithonDam-DVC_Gen | DVC | PARTIALLY COLLECTED
66 | 2016-09-27 | adityapur_132 | JUSNL | Pending
67 | 2016-09-28 | chandil220 | JUSNL | Pending
68 | 2016-09-29 | adhunik 400 | Adhunik | COMPLETED
69 | 2016-09-30 | Usha Martin_Adityapur | Usha Martin | COMPLETED
70 |  | Panchet-DVC_Gen | DVC | Partially Collected
71 | 2016-10-01 | Konar DVC | DVC | Partially Collected
72 |  | Tamar | JUSNL | Numerical relay data pending
73 | 2016-10-03 | Golmuri | JUSNL | Numerical relay data pending
74 | 2016-10-04 | Ramchandapur_220 | JUSNL | Numerical relay data pending
75 | 2016-10-05 | Manique | JUSNL | Numerical relay data pending
76 | 2016-10-14 | Dalbhumgarh | JUSNL | Numerical relay data pending
77 | 2016-10-18 | Jamshedpur- | PGCIL | Numerical relay data pending
78 | 2016-10-20 | TISCO | TATA STEEL | Numerical relay data pending
79 | 2016-10-25 | NOAMUNDI | JUSNL | Numerical relay data pending
80 | 2016-10-26 | KENDPOSI | JUSNL | Numerical relay data pending
81 | 2016-10-27 | GOILKERA | JUSNL | Numerical relay data pending
82 | 2016-10-28 | CHAKRADHARPUR | JUSNL | Partially Collected
83 | 2016-11-01 | CHAIBASA 132KV | JUSNL | Partially Collected
84 | 2016-11-02 | CHAIBASA 220KV | JUSNL | Numerical relay data pending
85 | 2016-11-03 | MANOHARPUR 132KV | JUSNL | Numerical relay data pending
86 | 2016-11-04 | RAJKHARSWAN 132KV | JUSNL | Numerical relay data pending
87 | 2016-11-05 | CHAIBASA PGCIL | PGCIL | Numerical relay data pending
88 | 2016-11-10 | RUNGTA MINES | RUNGTA | Numerical relay data pending
89 | 2016-11-11 | JOJOBERA | TATA | Numerical relay data pending
90 | 2016-12-19 | ELECTROSTEEL | ELECTROSTEEL | Numerical relay data pending
91 | 2016-12-20 | B.C.C.L | B.C.C.L | COMPLETED
92 | 2016-12-21 | M.P.L | TATA & DVC | Numerical relay data pending
93 | 2016-12-23 | B.S.L | SAIL | NO RELAY DATA GIVEN BY PLANT
Back

## List of SS visited W.BENGAL
Sl.No. | Date of visit | Station name | Owner | RELAY STATUS
1 | 2016-09-19 | Waria (DTPS) | DVC | COLLECTED
2 |  | DTPS_Waria | DVC | COLLECTED
3 |  | Burnpur | DVC | COLLECTED
4 | 2016-09-20 | Ramkanli | DVC | COLLECTED
5 | 2016-09-21 | Waria TPS (DTPS) | DVC | COLLECTED
6 |  | Durgapur steel TPS | DVC | COLLECTED
7 |  | Raghunathpur TPS | DVC | PENDING
8 |  | Raghunathpur TPS | DVC | PENDING
9 |  | Kolaghat TPS | WBPDCL | COLLECTED
10 | 2016-09-22 | Brjora | DVC | COLLECTED
11 |  | Barjora | DVC | COLLECTED
12 |  | ASP | DVC | PENDING
13 | 2016-09-23 | Durgapur MUCHIPARA | DVC | COLLECTED
14 |  | Muchipara | DVC | COLLECTED
15 |  | Jamuria | DVC | COLLECTED
16 |  | Parulia | DVC | COLLECTED
17 | 2016-09-24 | Kalipahari | DVC | COLLECTED
18 | 2016-09-26 | Burdwan | DVC | COLLECTED
19 |  | Belmuri | DVC | COLLECTED
20 |  | Santaldih TPS | WBPDCL | COLLECTED
21 | 2016-09-27 | Dum Dum | CESC | COLLECTED
22 |  | Park lane | CESC | COLLECTED
23 |  | Mejia TPS | DVC | COLLECTED
24 | 2016-09-28 | Kharagpur | DVC | COLLECTED
25 |  | Mejia TPS | DVC | COLLECTED
26 | 2016-09-29 | Kolaghat | DVC | COLLECTED
27 |  | How (d) | DVC | COLLECTED
28 |  | Bandel TPS | WBPDCL | COLLECTED
29 | 2016-10-03 | Brakeswar TPS | WBPDCL | COLLECTED
30 |  | Purulia | DVC | COLLECTED
31 | 2016-10-04 | Sagardighi TPS | WBPDCL | COLLECTED
32 | 2016-10-17 | Titagarh(trs) | CESC | COLLECTED
33 |  | Titagarh | CESC | COLLECTED
34 | 2016-10-18 | Kharagpur | WBSETCL | COLLECTED
35 |  | Egra | WBSETCL | COLLECTED
36 | 2016-10-19 | Midnapur | WBSETCL | COLLECTED
37 |  | B.Garden | CESC | COLLECTED
38 |  | Haldia | WBSETCL | COLLECTED
39 |  | East Calcutta | CESC | COLLECTED
40 | 2016-10-20 | Chandrakora road | WBSETCL | COLLECTED
41 |  | Haldia NIZ | WBSETCL | PENDING
42 |  | WBIIDC | WBSETCL | PENDING
43 |  | New Haldia | WBSETCL | COLLECTED
44 |  | NCGS | CESC | COLLECTED
45 | 2016-10-21 | VIDYASAGAR PARK | WBSETCL | COLLECTED
46 |  | Jhargram | WBSETCL | PENDING
47 |  | Tamluk | WBSETCL | PENDING
48 |  | Jadavpore | CESC | COLLECTED
49 |  | Patuli | CESC | COLLECTED
50 | 2016-10-22 | HIZLI TSS | WBSETCL | COLLECTED
51 |  | Hizli | WBSETCL | COLLECTED
52 |  | Kolaghat | WBSETCL | PENDING
53 |  | BT Road | CESC | COLLECTED
54 | 2016-10-24 | Pingla | WBSETCL | COLLECTED
55 |  | Balichak TSS | WBSETCL | COLLECTED
56 |  | Arambag | WBSETCL | PENDING
57 | 2016-10-25 | Rishra | WBSETCL | COLLECTED
58 |  | Majerhat | CESC | COLLECTED
59 |  | Taratala s/s | CESC | COLLECTED
60 | 2016-10-26 | Belmuri | WBSETCL | PENDING
61 |  | BBGS | CESC | COLLECTED
62 | 2016-10-27 | Bighati | WBSETCL | COLLECTED
63 |  | Birsingha | WBSETCL | COLLECTED
64 |  | Resmi Bulk | Resmi Bulk | PENDING
65 |  | Tata Metalic | Tata Metalic | PENDING
66 | 2016-10-28 | Jangipara | WBSETCL | PENDING
67 | 2016-10-31 | EMSS | CESC | COLLECTED
68 | 2016-11-01 | Satgachia | WBSETCL | PENDING
69 |  | Berhampore | WBSETCL | COLLECTED
70 | 2016-11-02 | KALNA | WBSETCL | PENDING
71 |  | Gokarna 220/132/33KV | WBSETCL | COLLECTED
72 |  | Gokarna 400/220KV | WBSETCL | COLLECTED
73 | 2016-11-03 | KATWA | WBSETCL | PENDING
74 |  | HALDIA | CESC | COLLECTED
75 |  | Debogram | WBSETCL | PENDING
76 | 2016-11-04 | Lalgola | WBSETCL | COLLECTED
77 |  | Raghunathganj | WBSETCL | COLLECTED
78 | 2016-11-04 | MAHACHANDA | WBSETCL | PENDING
79 | 2016-11-04 | SUBHAS GRAM | WBSETCL | COLLECTED
80 | 2016-11-05 | Rampurhat | WBSETCL | COLLECTED
81 |  | Sainthia | WBSETCL | COLLECTED
82 |  | BEHALA | WBSETCL | PENDING
83 | 2016-11-06 | Dhulian | WBSETCL | COLLECTED
84 | 2016-11-07 | Kuli | WBSETCL | COLLECTED
85 |  | SONARPUR | WBSETCL | COLLECTED
86 |  | JEERAT | WBSETCL | COLLECTED
87 |  | PRINCEP STREET | CESC | COLLECTED
88 |  | BBD BAG | CESC | COLLECTED
89 | 2016-11-08 | LAXMIKANTAPUR | WBSETCL | COLLECTED
90 |  | SOUTHERN GENERATING | CESC | COLLECTED
91 |  | AMTALA | WBSETCL | COLLECTED
92 | 2016-11-09 | SonarLal(Sonar bangla) | CONSUMER END | COLLECTED
93 |  | KASBA | WBSETCL | COLLECTED
94 |  | SOUTHERN RECEIVING | CESC | COLLECTED
95 |  | CHAKMIR | CESC | COLLECTED
96 |  | MANKAR | WBSETCL | COLLECTED
97 |  | RAINA | WBSETCL | PENDING
98 | 2016-11-10 | Malda | WBSETCL | COLLECTED
99 |  | BIDHANGAR 400KV | WBSETCL | PENDING
100 |  | BIDHANGAR 220/132KV | WBSETCL | PENDING
101 | 2016-11-11 | Balurghat | WBSETCL | COLLECTED
102 |  | DOMJUR | WBSETCL | COLLECTED
103 |  | PARK CIRCUS | CESC | COLLECTED
104 | 2016-11-12 | BELUR RECEIVING | CESC | COLLECTED
105 |  | WEST BANK RECEIVING | CESC | COLLECTED
106 |  | Bolpur | WBSETCL | COLLECTED
107 |  | Howrah | WBSETCL | COLLECTED
108 | 2016-11-14 | KRISNANAGAR(220/132/33) | WBSETCL | COLLECTED
109 | 2016-11-15 | KOLKATA LEATHER COMPLEX(220/132/33) | WBSETCL | COLLECTED
110 | 2016-11-16 | DHARAMPUR(220/132) | WBSETCL | COLLECTED
111 |  | DHARAMPUR(132/33) | WBSETCL | COLLECTED
112 |  | DSP | DSP | PENDING
113 | 2016-11-17 | ADISAPTAGRAM(132/33) | WBSETCL | COLLECTED
114 |  | Farakka(400/220 ) | NTPC | COLLECTED
115 | 2016-11-18 | Farakka(15.75/400 ) | NTPC | COLLECTED
116 |  | Ukhra | WBSETCL | COLLECTED
117 | 2016-11-19 | ASHOKENAGAR(132/33/25) | WBSETCL | COLLECTED
118 | 2016-11-21 | BARASAT(132/33/11) | WBSETCL | COLLECTED
119 |  | Dalkhola | WBSETCL | COLLECTED
120 | 2016-11-22 | DPL(220/132 ) | DPL | COLLECTED
121 |  | New town action area-III(220/132/33/11) | WBSETCL | COLLECTED
122 |  | Siliguri | WBSETCL | PENDING
123 | 2016-11-23 | A Zone | DPL | COLLECTED
124 |  | Darjeeling | WBSETCL | PENDING
125 |  | BASIRHAT(132/33/11) | WBSETCL | PENDING
126 | 2016-11-24 | B Zone | DPL | COLLECTED
127 |  | Kurseong | WBSETCL | PENDING
128 |  | BONGAON(132/33/11) | WBSETCL | PENDING
129 | 2016-11-25 | AB Zone | DPL | COLLECTED
130 |  | North Bengal university (NBU) | WBSETCL | PENDING
131 |  | ujanu | WBSETCL | PENDING
132 |  | CHANDITOLA(132/33) | WBSETCL | COLLECTED
133 | 2016-11-26 | C Zone | DPL | COLLECTED
134 |  | Falta | WBSETCL | COLLECTED
135 | 2016-11-28 | C1 Zone | DPL | COLLECTED
136 |  | New Jalpaiguri | WBSETCL | PENDING
137 |  | Gangarampur | WBSETCL | COLLECTED
138 | 2016-11-29 | Bamunara SS | DPL | COLLECTED
139 |  | Maynaguri | WBSETCL | PENDING
140 |  | Kakdwip | WBSETCL | COLLECTED
141 | 2016-11-30 | Chalsa_132/66/33 | WBSETCL | PENDING
142 |  | Kalyani | WBSETCL | COLLECTED
143 | 2016-12-01 | LILUAH(132/33) | WBSETCL | COLLECTED
144 | 2016-12-02 | Binaguri | PGCIL | COLLECTED
145 |  | NEW TOWN ACTION AREA-I(132/33) | WBSETCL | COLLECTED
146 |  | Asansol | WBSETCL | COLLECTED
147 | 2016-12-03 | RANAGHAT(132/66/33/25) | WBSETCL | COLLECTED
148 |  | Raghunathpur | WBSETCL | PENDING
149 | 2016-12-05 | Birpara | PGCIL | COLLECTED
150 | 2016-12-06 | JK Nagar | DPL | COLLECTED
151 |  | ULUBAREA(132/33) | WBSETCL | PENDING
152 | 2016-12-07 | Coochbehar | WBSETCL | COLLECTED
153 |  | Bishnupur (new) | WBSETCL | PENDING
154 |  | Bishnupur (old) | WBSETCL | PENDING
155 |  | FOOD PARK(132/33) | WBSETCL | COLLECTED
156 | 2016-12-08 | Alipurduar | WBSETCL | COLLECTED
157 |  | MATHABHANGA GIS | WBSETCL | COLLECTED
158 |  | TITAGARH(132/33) | WBSETCL | COLLECTED
159 | 2016-12-09 | NAZIRPUR(132/33) | WBSETCL | COLLECTED
160 | 2016-12-10 | Bankura | WBSETCL | COLLECTED
161 |  | Khatra | WBSETCL | PENDING
162 | 2016-12-13 | Siliguri PG | PGCIL | COLLECTED
163 |  | Hindmotor | Hindmotor | Plant Closed
164 |  | Concast Bengal | Concast Bengal | COLLECTED
165 | 2016-12-14 | Mahishpota | WBSETCL | PENDING
166 |  | Modern | Modern | COLLECTED
167 | 2016-12-15 | Raigunj | WBSETCL | COLLECTED
168 |  | Dankuni(rail) | RAIL | Fail to get permission from Railway
169 |  | Hura | WBSETCL | PENDING
170 | 2016-12-16 | Gangarampur | WBSETCL | COLLECTED
171 |  | Serakol | WBSETCL | PENDING
172 | 2016-12-17 | Samsi | WBSETCL | COLLECTED
173 |  | Purulia | WBSETCL | COLLECTED
174 | 2016-12-19 | Ambuja | Ambuja | COLLECTED
175 |  | khejuria GIS | WBSETCL | PENDING
176 |  | Bagnan | WBSETCL | PENDING
177 |  | PPSP | WBSETCL | COLLECTED
178 | 2016-12-20 | Malda PG | PGCIL | COLLECTED
179 |  | Foundary Park | WBSETCL | COLLECTED
180 | 2016-12-21 | Tarakeswar | WBSETCL | PENDING
181 | 2016-12-22 | BERAMPUR PG | PGCIL | COLLECTED
182 | 2016-12-23 | SHYAM STEEL | SHYAM STEEL | COLLECTED
183 | 2016-12-24 | SALT LAKE AIS | WBSETCL | COLLECTED
184 | 2016-12-26 | SALT LAKE GIS | WBSETCL | COLLECTED
185 | 2016-12-27 | MANAKSIA | MANAKSIA | COLLECTED
186 |  | SHYAM FERRO | SHYAM FERRO | COLLECTED
187 | 2016-12-28 | B D GOYAL | B D GOYAL | COLLECTED
188 |  | MODERN INDIA CONCAST | MODERN INDIA CONCAST | COLLECTED
189 |  | SUBHAS GRAM PGCIL | PGCIL | COLLECTED
190 | 2016-12-29 | SREE AMBEY ISPAT | SREE AMBEY ISPAT | COLLECTED
191 | 2016-12-30 | PCBL | SANJIB GOENKA GROUP | COLLECTED
192 |  | BARJORA | WBSETCL | COLLECTED
193 |  | KHANYAN | WBSETCL | PENDING
Back

## List of SS visited SIKKIM
Sl. No. | Voltage | Station Name | Owner | Status
1 | 400 | Rangpo | PGCIL | Collected
2 | 220 | Samardang | PGCIL | Collected
3 | 220 | New Melli | PGCIL | Collected
4 | 132 | Gantok | PGCIL | Collected
5 | 132 | Melli | SIKKIM | Collected (except numerical relay)
6 | 132 | Geyzing | SIKKIM | Collected (except numerical relay)
7 | 66 | Bulbuley | SIKKIM | Collected (except numerical relay)
8 | 66 | Geyzing | SIKKIM | Collected (except numerical relay)
9 | 66 | Mangan | SIKKIM | Collected (except numerical relay)
10 | 66 | Melli | SIKKIM | Collected (except numerical relay)
11 | 66 | Namchi | SIKKIM | Collected (except numerical relay)
12 | 66 | Pelling | SIKKIM | Collected (except numerical relay)
13 | 66 | Phodong | SIKKIM | Collected (except numerical relay)
14 |  | Pakyong | SIKKIM | Collected (except numerical relay)
15 | 66 | Rhenock | SIKKIM | Collected (except numerical relay)
16 | 66 | Rongly | SIKKIM | Collected (except numerical relay)
17 | 66 | Rothak | SIKKIM | Collected (except numerical relay)
18 | 66 | Sichey | SIKKIM | Collected (except numerical relay)
19 | 66 | Soreng |  | Collected (except numerical relay)
20 | 66 | Tadong | SIKKIM | Collected (except numerical relay)
21 | 66 | LLHP,Ranipool | SIKKIM | Collected (except numerical relay)
22 | 66 | Lingdok,SKPPL | SIKKIM | Collected (except numerical relay)
23 | Gen | Jorethang Loop |  | Collected
24 | Gen | Rangit HPS |  | Collected
25 | Gen | Teesta V HPS |  | Collected
26 | Gen | LLHP HEP |  | Collected (except numerical relay)
27 | Gen | Meyongchu Hep |  | Collected (except numerical relay)
Back

## database and SLD preparation
Sl. No. | State | Substation Name (with Voltage Level) | Database modelling | SLD preparation
|  |  | Status | Status
1 | Odisha | DIGAPAHANDI(132/33kV) | Completed | Completed
2 | Odisha | MOHANA(132/33kV) | Completed | Completed
3 | Odisha | ASKA(132/33kV) | Completed | Completed
4 | Odisha | Khurda(220/33) | Completed | Completed
5 | Odisha | GMR(400/20kV) | Completed | Completed
6 | Odisha | NAYAGARH(132/33kV) | Completed | Completed
7 | Odisha | CHAINPAL(220/132kV) | Completed | Completed
8 | Odisha | TTPS(220/132kV) | Completed | Completed
9 | Odisha | ATRI(220/132/33kV) | Completed | Completed
10 | Odisha | MENDHASAL(400/220/132Kv) | Completed | Completed
11 | Odisha | BIDANASI(220/132/33kV) | Completed | Completed
12 | Odisha | BRG STEELS(220/11kV) | Completed | Completed
13 | Odisha | BHANJANAGAR(220/132kV) | Completed | Completed
14 | Odisha | DUBURI (220/132/33kV) | Completed | Completed
15 | Odisha | CHandaka(220/132kV) | Completed | Completed
16 | Odisha | ANGUL(765/400KV) | Completed | Completed
17 | Odisha | TSTPS(400/220kV) | Completed | Completed
18 | Odisha | MERAMANDALI(400/220KV) | Completed | Completed
19 | Odisha | AKUSINGHI(132KV/33KV) | Completed | Completed
20 | Odisha | Sambalpur(132/33KV) | Completed | Completed
21 | Odisha | NARENDRAPUR(220/132/33KV) | Completed | Completed
22 | Odisha | SUNABEDA(132/33KV) | Completed | Completed
23 | Odisha | Paralakhemundi(132/33KV) | Completed | Completed
24 | Odisha | Balugaon(132/33KV) | Completed | Completed
25 | Odisha | BONIDA(132/33KV) | Completed | Completed
26 | Odisha | BARIPADA(132/33) | Completed | Completed
27 | Odisha | PUROSOTTAMPUR | Completed | Completed
28 | Odisha | KarakPrasad(132kV) | Completed | Completed
29 | Odisha | Arati Steel(132/11kV) | Completed | Completed
30 | Odisha | NBVL(132/11kV) | Completed | Completed
31 | Odisha | Kuchei/Baripada(PGCIL)400/220/132kV | Completed | Completed
32 | Odisha | Dhenkanal(132/33kV) | Completed | Completed
33 | Odisha | New Duri (400/220kV) | Completed | Completed
34 | Odisha | NALCO | Completed | Completed
35 | Odisha | SEL | Completed | Completed
36 | Odisha | JSPL(400/13.8kV) | Completed | Completed
37 | Odisha | Nadira_132/33kV | Completed | Completed
38 | Odisha | Barapalli(132/33kV) | Completed | Completed
39 | Odisha | Basta(132/33kV) | Completed | Completed
40 | Odisha | Chhend(132/33kV) | Completed | Completed
41 | Odisha | Jaijur Town(132/33kV) | Completed | Completed
42 | Odisha | Jaleswar(132/33kV) | Completed | Completed
43 | Odisha | Kalarangi(132/33kV) | Completed | Completed
44 | Odisha | Cuttack(132/33) | Completed | Completed
45 | Odisha | Bargarh(132/33) | Completed | Completed
46 | Odisha | SMC | Completed | Completed
47 | Odisha | BEEKAY STEEL_132kV | Completed | Completed
48 | Odisha | KARANJIA | Completed | Completed
49 | Odisha | ULTRATECH_CEMCO | Completed | Completed
50 | Odisha | JSPL_220kV/33kV | Completed | Completed
51 | Odisha | PADAMPUR | Completed | Completed
52 | Odisha | RAJGANGPUR(132/33) | Completed | Completed
53 | Odisha | SUNDARGARH(132/33) | Completed | Completed
54 | Odisha | Boudh(132/33) | Completed | Completed
55 | Odisha | Phulnakhara_132kV | Completed | Completed
56 | Odisha | Balasore_220kV | Completed | Completed
57 | Odisha | Chiplima_gen | Completed | Completed
58 | Odisha | Rairangpur_132kV | Completed | Completed
59 | Odisha | Rengali_PGCIL | Completed | Completed
60 | Odisha | Angul_132kV | Completed | Completed
61 | Odisha | Barbil_132kV | Completed | Completed
62 | Odisha | Brajrajnagar_132kV | Completed | Completed
63 | Odisha | Keonjhar_400kV | Completed | Completed
64 | Odisha | Budhipadar_220kV | Completed | Completed
65 | Odisha | Joda_132kV | Completed | Completed
66 | Odisha | Balimela_220kV | Completed | Completed
67 | Odisha | Junagarh_132kV | Completed | Completed
68 | Odisha | Jharsuguda_132kV | Completed | Completed
69 | Odisha | Barkote_220kV | Completed | Completed
70 | Odisha | Dabugaon_132kV | Completed | Completed
71 | Odisha | Samuka_132kV | Completed | Completed
72 | Odisha | Konark_132kV | Completed | Completed
73 | Odisha | Kesura_132kV | Completed | Completed
74 | Odisha | Phulbani_132kV | Completed | Completed
75 | Odisha | Nimapara_132kV | Completed | Completed
76 | Odisha | Therubali_220_132kV | Completed | Completed
77 | Odisha | Argul_132kV | Completed | Completed
78 | Odisha | Paradeep_220_132kV | Completed | Completed
79 | Odisha | Tentulikhunta_132kV | Completed | Completed
80 | Odisha | Puri_132kV | Completed | Completed
81 | Odisha | Kharaiar_132kV | Completed | Completed
82 | Odisha | Rayagada_132kV | Completed | Completed
83 | Odisha | Sonepur_132kV | Completed | Completed
84 | Odisha | Ranasighipur_132kV | Completed | Completed
85 | Odisha | Patnagarh_132kV | Completed | Completed
86 | Odisha | New Bolangir_220kV | Completed | Completed
87 | Odisha | OLD Bolangir_132kV | Completed | Completed
88 | Odisha | Samangara_220_132kV | Completed | Completed
89 | Odisha | Chatrapur_132kV | Completed | Completed
90 | Odisha | Umerkote_132kV | Completed | Completed
91 | Odisha | Kesinga_132kV | Completed | Completed
92 | Odisha | Bhawanipatana_132kV | Completed | Completed
93 | Odisha | Saintala_132kV | Completed | Completed
94 | Odisha | Bhubanewar_132kV | Completed | Completed
95 | Odisha | Nuapatha_132kV | Completed | Completed
96 | Odisha | Marshaghai_132kV | Completed | Completed
97 | Odisha | Pattamundai_132kV | Completed | Completed
98 | Odisha | Nuapara_132kV | Completed | Completed
99 | Odisha | Jagatsinghpur_132kV | Completed | Completed
100 | Odisha | Jayanagar_220/132kV | Completed | Completed
101 | Odisha | Choudwar_132kV | Completed | Completed
102 | Odisha | Anadpur_132kV | Completed | Completed
103 | Odisha | Soro_132kV | Completed | Completed
104 | Odisha | Jajipur Road(132/33kV) | Completed | Completed
105 | Odisha | Chandikhola_132kV | Completed | Completed
106 | Odisha | Kamkhyanagar_132kV | Completed | Completed
107 | Odisha | Kendrapara_132kV | Completed | Completed
108 | Odisha | ICCL | Completed | Completed
109 | Odisha | Chandpur_132kV | Completed | Completed
110 | Odisha | Salipur_132kV | Completed | Completed
111 | Odisha | Somathpur_132kV | Completed | Completed
112 | Odisha | Palaspanga_132kV | Completed | Completed
113 | Odisha | Berampur_132kV | Completed | Completed
114 | Odisha | B.C Mohanty | Completed | Completed
115 | Odisha | BRPL | Completed | Completed
116 | Odisha | IND_BHARAT_132kV | Completed | Completed
117 | Odisha | Kuchinda_132kV | Completed | Completed
118 | Odisha | Kalunga_132kV | Completed | Completed
119 | Odisha | Laxmipur_220/33kV | Completed | Completed
120 | Odisha | Rourkela_132/33kV | Completed | Completed
121 | Odisha | Tarkera_220/132kV | Completed | Completed
122 | Odisha | Lapanga_220/132kV | Completed | Completed
123 | Odisha | OCL | Completed | Completed
124 | Odisha | IMFA | Completed | Completed
125 | Odisha | JSL | Completed | Completed
126 | Odisha | NINL | Completed | Completed
127 | Odisha | Facor Power Ltd | Completed | Completed
128 | Odisha | SHYAM DRI | Completed | Completed
129 | Odisha | ACTION_ISPAT | Completed | Completed
130 | Odisha | ESSAR | Completed | Completed
131 | Odisha | Tata Group/FAP | Completed | Completed
132 | Odisha | ARYA_Steel | Completed | Completed
133 | Odisha | ARYA_ISPAT | Completed | Completed
134 | Odisha | TS_ALLOY | Completed | Completed
135 | Odisha | Indravati_400kV | Completed | Completed
136 | Odisha | Birla_Tyries | Completed | Completed
137 | Odisha | Facor_Alloy_Steel | Completed | Completed
138 | Odisha | Rohit_Ferro_Alloy_220kV | Completed | Completed
139 | Odisha | Rairakhol_132kV | Completed | Completed
141 | Odisha | Bolani_132/33kV | Completed | Completed
142 | Odisha | BPPL(LILO)_ | Completed | Completed
143 | Odisha | IOCL_Pradeep | Completed | Completed
144 | Odisha | Rangeli_hydro_220kV | Completed | Completed
145 | Odisha | Meenashi_hydro | Completed | Completed
146 | Odisha | Vedanta_Langrarh | Completed | Completed
147 | Odisha | Sri_Ganesh_Sw | Completed | Completed
148 | Odisha | HAL | Completed | Completed
149 | Odisha | Samal_Barrage_OPTCL | Completed | Completed
150 | Odisha | BPPL | Completed | Completed
151 | Odisha | TSIL | Completed | Completed
152 | Odisha | JK_MILLS | Completed | Completed
153 | Odisha | POWER_MAX | Completed | Completed
154 | Odisha | MSP_Joda | Completed | Completed
155 | Odisha | Aditya_Aluminum | Completed | Completed
156 | Odisha | Adunik_metals | Completed | Completed
157 | Odisha | MINL | Completed | Completed
158 | Odisha | Emami | Completed | Completed
159 | Odisha | Rangeli_OPTCL | Completed | Completed
160 | Odisha | Rourkela_400/220KV_PGCIL | Completed | Completed
161 | Odisha | Heavy water Plant_FCI | Completed | Completed
162 | Odisha | Visa_Steel | Completed | Completed
163 | Odisha | Misrial | Completed | Completed
164 | Odisha | IND_BHARAT_400kV | Completed | Completed
165 | Odisha | Uktal_Alumina_(UALI) | Completed | Completed
166 | Odisha | Bhusan_steel_THELKOLOI_Lapanga | Completed | Completed
167 | Odisha | UKHEP | Completed | Completed
168 | Odisha | JITPL | Completed | Completed
169 | Odisha | Upper_Indravati | Completed | Completed
170 | Odisha | IB_Thermal | Completed | Completed
171 | Odisha | Bolangir_PGCIL | Completed | Completed
172 | Odisha | Jarsuguda_PGCIL | Completed | Completed
173 | Odisha | Katapalli_220kV | Completed | Completed
174 | Odisha | ACC | Completed | Completed
175 | Odisha | BHEP | Completed | Completed
176 | Odisha | IFFCO | Completed | Completed
177 | Odisha | Burla | Completed | Completed
178 | Odisha | JFAL | Completed | Completed
179 | Odisha | Machukund_Hydro Electric | Completed | Completed
Back

## Odisha pending list
Sl no. | Station | Owner | Voltage level |  | Relay Data Status | contact details | REMARK | Collected file 2nd slot
1 | Bhushan steel | Bhshan steel |  |  | All relay data pending | ARVIND KUMAR SACHDEVA- 9437059668 , aksachdeva@bpsl.net
2 | Chaipal | OPTCL | 132 |  | All MICOM relay data pending | SRI AMIYA KUMAR RATH- 9438907179 emrt.sd.chp@optcl.co.in
3 | OPCL | OPCL | 132 |  | All relay data pending | G P MAHAPATRA- 09437128756- OPCLSAMAL@REDIFF.COM
4 | BRG | BRG | 132 |  | All relay data pending | SANJIB MUKHERJEE- 7682847132, sanjib.muk@brggroup.in
5 | Burla | OPTCL | 132 |  | Relay data and generator data pending ( for few relays data was collected manually) | SRI GYANA RANJAN DAS- 9437051197,testing team contact-Abani Mishra-ele.amishra@optcl.co.in
6 | Bargarh | OPTCL | 132 |  | All SEL relay data pending | MILKIYOR KERKETTA- 9438907136,testing team contact-Abani Mishra-ele.amishra@optcl.co.in
7 | Hindalco | Hindalco | 132 |  | ALL RELAY AND GENARATOR DATA PENDEING. | tapan.panda@adityabirla.com. nimai.mahapatro@adityabirla.com, tapan panda- 9090966597
8 | Action ISPAT | Action ISPAT | 132 |  | 1. 132 KV I/C-I MULTILIN L30,F650, 2. 132 KV I/C-2 MULTILIN L30, F650, 3. 132/11 KV TRF MICOM P642, 4. 11 KV INCOMIG MICOM P122, 5. 132 KV B/C 7SJ8042, 6. 132 KV LINEI/C-2 SIPROTEC 7SA611,7SJ8042, 7. 132KV LINE I/C-17SA611,7SJ8042, MICOM P341. | 7894462361- Mr. Rajni Kanta Das electrical@actionispat.com
9 | Brajranagar | OPTCL | 132 |  | all complete | ele.ssdasari@optcl.co.in, SDO- ele.smajhi@optcl.co.in
10 | Sundargarh | OPTCL | 132 |  | ALL RELAY DATA PENDING. | (SDO) Mr. D. K. Mohanty- 9438907453 ele.dkmohanta@optcl.co.in, emrt.sd.rkl@optcl.co.in |  | Budhipadar_I_And_II
11 | sri ganesh | sri ganesh | 132 |  | GENARATOR DATA & RELAY DATA PENDING (TG PROTECTION (GENARERATOR) - REM545) | V.B REDDY- 8763302212 reddy_vancha@yahoo.com/ v.bangar.reddy@gmail.com
12 | Aryan ISPAT | Aryan ISPAT |  |  | 1. 132 MVA TRANSFORMER FEEDER MICOM P632 & P341, 2. VIRAJ FEEDER MICOM P632, P341, 3. 132 KV ARYAN FEEDER REF 615. ALL GENARATOR DATA AND GENARETOR RELAY SETTING. | Kolapalli Padmakar-DGM-09937022792 K.PADMAKAR@ARYANISPAT.COM ALOK CHANDRA- 07894420348, alok.chandra@aryanispat.com
13 | IND bharat | IND bharat |  |  | ALL RELAY DATA AND GANERATOR DATA PENDING | (SDO) Mr. D. K. Mohanty- 9438907453 ele.dkmohanta@optcl.co.in, emrt.sd.rkl@optcl.co.in
14 | Kuchinda | OPTCL |  |  | all complete | ele.ssdasari@optcl.co.in, SDO- ele.smajhi@optcl.co.in
15 | Rourkela 132kV | OPTCL | 132 |  | PARTIAL DATA RECEVED(Tarkera Line 1,2,3 P14D RECEIVED ONLY, EXCEPT THAT ALL ARE PENDING) | (SDO) Mr. D. K. Mohanty- 9438907453 ele.dkmohanta@optcl.co.in, emrt.sd.rkl@optcl.co.in
16 | Chend | OPTCL | 132 |  | P430C ,P141(kuanrmunda main back up),SIPROTEC 7UT61(transformer 3 main) | (SDO) Mr. D. K. Mohanty- 9438907453 ele.dkmohanta@optcl.co.in, emrt.sd.rkl@optcl.co.in
17 | Tarkera | OPTCL | 220 |  | 1. RSP-1 MICOM P442,P141, 2. RSP-2 MICOM P442,P141, 3. BUDHUPADAR-2 REL670, 4.AUTO-III 81DV-L4F-2D0ED62NU, 5.AUTO-I DOUBIAS-M, 6.132KV SIDE AUTO-III P14DB16A7C0510A, 7.HSL-II MICOM P441, P127, 8.HSL-I MICOM P441,P127, 9.RAJGANGPUR-I 7SJ62, 10.RAJGANGPUR-II REL670, 11.BUDHIPADAR-I(KALUNGA) REL670 | (SDO) Mr. D. K. Mohanty- 9438907453 ele.dkmohanta@optcl.co.in, emrt.sd.rkl@optcl.co.in |  | Chhend_I_And_II Rajgangpur_I Rourkela_I_And_II
18 | Adhunik metals | Adhunik metals | 132 |  | 1.132 FEEDR PROTECTION PANEL MICOM P430, 2.132 KV MAIN INCOMING MICOM P341. | 9178454188 Mr. Bijay Panda bijaypanda@adhunikgroup.co.in
19 | JODA | OPTCL | 220 |  | 1. 220KV TATA STEEL MAIN-1 SIPROTEC 7SA52. 2. 220KV TATA STEEL BACKUP SIPROTEC 7SJ62. 3. 220KV RAMCHANDRAPUR BACKUP SEL-751A. 4. 220KV AUTO-II BACKUP SEL-751A 5. 132KV AUTO-II BACKUP SEL-751A 6. 220KV JSPL BACKUP SIPROTEC 7SJ8042. 8. 220KV JSPL BACKUP SIPROTEC 7SJ62. 10. 220KV M/s SML BACKUP SIPROTEC 7SJ62. 11. 132KV TRANFORMER-II BACKUP MICOM P141. 12. 132KV ROURKELA MAIN SEL-311C. | (DGM)S.S. Nanda 9438907803 emrt.div.jjp@optcl.co.in, (SDO) Gourhari Behera 9438907457 emrt.sd.jod@optcl.co.in | some data received
20 | Barbil | OPTCL | 132 |  | 1. 132KV TRANSFORMER-II MICOM P632, 2. 132 KV TRANSFORMER-I MICOM P-632. | (DGM)S.S. Nanda 9438907803 emrt.div.jjp@optcl.co.in, (SDO) Gourhari Behera 9438907457 emrt.sd.jod@optcl.co.in | All collected raw setting files are corrupted. | 132 BARBIL IN BACK UP 132 BARBIL OUT BACK UP 132 KV BARBIL IN DP 132 KV BARBIL OUT DP 132 KV BUS COUPLER 132 KV TR-1 BACK UP 132 KV TR-2 BACK UP TR- 1 DIFF TR-2 DIFF
21 | Bolani | OPTCL | 132 |  | all data received | (DGM)S.S. Nanda 9438907803 emrt.div.jjp@optcl.co.in, (SDO) Gourhari Behera 9438907457 emrt.sd.jod@optcl.co.in | All collected raw setting files are corrupted. | SEL DATA BOLANI 132KV TR-2 BACK UP
22 | Arya | Arya | 132 |  | all data received | PRADEEP BISWAL 9583000315 er.debiprasadnayak@gmail.com | All collected raw setting files are corrupted. | 132 KV BRPL BACK UP 132 KV BRPL 132 KV BUS-COUPLER BU 270916_ARYA IC DP ARYA IN BACK UP ARYA OUT BACK UP ARYA OUT DP GR-2
23 | TSIL | TSIL | 132 |  | Data received | PRATYUSHA KR. NANDA 9238883280 e.mail-pknanda@tatasponge.com
24 | P ponga | OPTCL | 132 |  | RELAY DATA PENDING | (DGM)S.S. Nanda 9438907803 emrt.div.jjp@optcl.co.in, (SDO) Gourhari Behera 9438907457 emrt.sd.jod@optcl.co.in
25 | Dhenkanal | BRPL | 132 |  | 1. 132 KV I/C LINE MICOM P127 , 2. 20 MVA TRANSFORMER MICOM P632, P127 | BIKASH RANJAN- 9937290926 bikas.panda@brplind.com
26 | ESSAR | ESSAR | 132 |  | ALL RELAY DATA RECIVED EXCEPT 1. 132 KV I/C LINE MICOM P442. | DIRENDRA SINGH- 9437058410 dhirendrasingh@essar.com
27 | MSP | MSP | 132 |  | ALL RELAY DATA RECIVED EXCEPT REF PROTECTION SCHEM | D. DASS- 9776193996 dibyajotidass55@gmail.com
28 | sri ganesh switching | optcl |  |  | RELAY DATA PENDING | (SDO) Mr. D. K. Mohanty- 9438907453 ele.dkmohanta@optcl.co.in, emrt.sd.rkl@optcl.co.in
29 | VIRAJ | VIRAJ |  |  | RELAY DATA PENDING | PRITHWI SINGH- 9238082029 e.mail-prithvipal2012@gmail.com
30 | Tata Steel, Kalinganagar | Tata Group | 220/132KV CPP | Turbo Generator 1&2 | Generator Protection-Main1 (7UM62) | Budhan Chandra Maji Mob- +91 9040040536 E.Mail- bcmaji@tatapower.com
Generator Protection-Main2 (7UM62)
Rotor Earth Fault- (7XT7100)
Stator Earth Fault- (7XT3300)
Overall Differential- (7UT63)
|  |  |  | Generator Transformer | Differential Protection- (7UT61)
O/C & E/F- (7SJ8041-5EB96-3FC0/CC)
|  |  |  | 220KV Grid Incoming 1 & 2 | Distance Main1- (7SD5) | Ranjit Kumar- Mob- +91 9040097687 E.Mail- ranjit.kumar1@tatasteel.com
Distance Main2- (7SD5)
Grid Islanding- (7SJ8031)
|  |  |  | Auto Transformer (200MVA * 3) | Differential Main1- (7UT61)
Differential Main2- (7UT61)
O/C & E/F- (7SJ62)
|  |  |  | 220KV Bus Coupler | O/C & E/F- (7SJ62)
|  |  |  | 220KV Bus Bar Protection | Muster Control Unit- (7SS52)
31 | Dhenkanal | OPTCL | 132/33KV | Joranda Line | Distance- SEL321 | M Z Huda, EMR DGM Mob- +91 9438907491 e.mail-
|  |  |  | Transformer-III | Differential- MiCOM P632
|  |  |  | Meramundali line | Distance- MiCOM P442
32 | Bhawanipatna | OPTCL | 132 |  | 1.TRANSFORMER 1 DIFFRENTIAL MICOM P632, 2.TRANSFORMER 1 DIR O/C & E/F MICOM P141 3.TRANSFORMER 1 HV REF MICOM P141 4.TRANSFORMER 2 DIFFRENTIAL MICOM P632, 5.TRANSFORMER 2 DIR O/C & E/F MICOM P141 6.TRANSFORMER 2 HV REF MICOM P141 7.BUSCOUPLER & TRANSFER BUS COUPLER MICOM P141 | BENUHAR PARIDA(E&MR)-9438907367 e.mail-ele.bparida@optcl.co.in
33 | Junagarh | OPTCL | 132 |  | 1. KESINGHA DISTANCE RELAY ALSTOM PD521. | BENUHAR PARIDA(E&MR)-9438907367 e.mail-ele.bparida@optcl.co.in
34 | Kesinga | OPTCL | 132 |  | 1. BHAWANIPATNA DISTANCE RELAY REL670 2. TRANSFORMER DIR O/C & E/F MULTILINF650 3. KHARIAR DISTANCE RELAY 670. | BENUHAR PARIDA(E&MR)-9438907367 e.mail-ele.bparida@optcl.co.in
35 | Sonepur | OPTCL | 132 |  | 1.TRANSFORMER '3' DIRECTIONAL 0/C & E/F SEL751A | ABANI MISHRA(E&MR)-9438907827 e.mail-
36 | Bhubaneshwar | OPTCL | 132 |  | all complete | GURUPRASAD MISHRA(E&MR)-9438907866,ele.gpmishra@optcl.co.in
37 | kesura | OPTCL | 132 |  | all complete | GURUPRASAD MISHRA(E&MR)-9438907866,ele.gpmishra@optcl.co.in
38 | nimapara | OPTCL | 132 |  | all complete | GURUPRASAD MISHRA(E&MR)-9438907866,ele.gpmishra@optcl.co.in
39 | Konark | OPTCL | 132 |  | all complete
40 | samangara | OPTCL | 220 |  | all complete
41 | puri | OPTCL | 132 |  | all complete
42 | SAMUKA | OPTCL | 132 |  | all complete
43 | Kharag prasad | OPTCL | 132 |  | all complete | NEED TO FIND E & M R TEAM FOR DOWLOAD
45 | Bidanasi | OPTCL | 220KV | Mendhasal | Distance Protection- ALSTOM- PD 571 | Satya Narayana Sahoo, EMR Engg. Mob-+91 9438907844 Ajay Das, EMR AGM Mob- +91 9438907495 e.mail-emrt.sd.cdw@optcl.co.in
|  |  |  | Meramundali | Distance Protection- ALSTOM- PD 571
|  |  |  | Choudwar | Distance Protection- ABB- REL-670
46 | Angul | OPTCL | 132KV | Transformer-I | Differential - SEL - 787 | M.Z.Huda Mob-9438907491 e.mail-
Transformer-II
Transformer-III
47 | Shyam DRI | OPTCL | 132KV |  | SIPROTEC 7UT61 ,MICOM P141(trf 1 MAIN & BACKUP) & SIPROTEC 7UM627SJ6001-4EA00-0DA0/BB(trf 2 MAIN & BACKUP) |  | some data received
48 | Shamuka | OPTCL | 132KV |  | all complete | Prasenjit Mishra, Mob-9438907463, e.mail-ele.pmishra@optcl.ci.on
49 | RAIRAKHOL | OPTCL | 132 |  | SEL-751A (boinda and katapalli line backup) | K.B.Behera Mob-9438907152 e.mail-ele.kbbehera@optcl.co.in
50 | RAJGANGPUR | OPTCL | 132 |  | PZ1000(BUDHIPADAR & TARKERA LINE)(P14D RECEIVED ) | Pandu Munda Mob-9438907764 |  | Budhipadar_fdr Rajgangpur_Kuchinda Rajgangpur_Tarkera
51 | BALASOR 220 | OPTCL | 220 |  | Quadra Mho SHPM(KUCHEI 2 LINE) | Mahendra Chanan Sing Mob-9438908052 e.mail-grid.ss.blsore@optcl.co.in
52 | TS ALLOY | TS ALLOY | 132 |  | SPAJ140C(BUS COUPLER/TRANSFORMER) | Manmath Nath Sahoo, Mob-9238407278, e.mail-mnsahoo@tatasteel.com
53 | VEDANTA | VEDANTA | 400 |  | 9625C , REF 610 | Shatrughna Das, Mob-9937251426, e.mailshatrughna.das@vedanta.co.in
54 | SOMNATHPUR | OPTCL | 132 |  | 81RV ,8ZLV(BALASORE-2) | Durgamadhaba Raut Mob-9438907903 e.mail-durgamadhaba.raut@gmail.com
55 | IB THERMEL | IB THERMEL | 132 |  | REG670(GENERATOR) | A.Prussi Mob-9938823964 e.mail-amresh.prusti@opgc.co.in
56 | MUCHKUND | OPTCL | 132 |  | REG670(GENERATOR) | P.Udaya Kumar, Mob-9437494888, e.mail-se-machkund@yahoo.co.in
57 | IFFCO | IFFCO | 132 |  | REG670(GENERATOR) | R.K.Swain Mob-9937238316
58 | Nalco | Nalco | 220 |  | 7SV600(LBB ,TIE) | A.K.Panda, Mob-9437079526, e.mail-anuj.panda@nalcoindia.co.in
59 | jitpl | jitpl | 132 |  | 7VK61(LBB,ALL BAYS) | Mukesh Khanna Mob-9583040150 e.mail-electrical_orissa@jindalgroup.com
60 | Nayagarh | OPTCL | 132 |  | 7UPS1(TRANSFORMER-III)
61 | Newduburi | OPTCL | 400 |  | 7VK51(LBB) | K.C.Jena Mob-9438907974 e.mail-grid.ss.ndubri@optcl.co.in
62 | New bolangir | OPTCL | 220 |  | SPAJ140(BUS COUPLER) , RET316*4(Auto transformer1 & 2 main) | Sri. Pradip Kumar Sahu Mob-9438907128 e.mail-
63 | JODA ,KAMAHYANAGAR | OPTCL | 132 |  | MC31A(B14(JODA)/B/33/2(KAMAKHYA NAGAR)) | A.K.Mohanta e.mail-grid.ss.joda@optcl.co.in
64 | ARTI STEEL | ARTI STEEL | 132 |  | REX521(Meramunli line backup) | O.P.Prasad, Mob-9437083794, op.prasad@aartisteelsltd.com
65 | KATAPALLI | OPTCL | 220 |  | REL316*4(lapanga1 , lapanga2, hindalco1 , hindalco2 line main2) | P.K.Pani Mob-9438907645 e.mail-grid.ss.ktpali@optcl.co.in | some data received
Back