## Sheet1
EASTERN REGIONAL LOAD DESPATCH CENTRE
ERLDC, KOLKATA
TRANSMISSION ELEMENTS OUTAGE APPROVED IN 155th OCC MEETING OF ERPC
|  | FROM |  | TO
SL. No | NAME OF THE ELEMENTS | DATE | TIME | DATE | TIME | REMARKS | S.D availed BY | Reason | SUBJECT TO CONSENT FROM AGENCY | COMMENT
1 | 125MVAR BR- I AT ALIPURDUAR | 2019-04-22 | 8:00 | 2019-04-23 | 18:00 | OCB | Powergrid, ER-II | Modification of HVW supply line to accommodate erection activity of Jigmeling bay.
2 | 125MVAR BR- II AT ALIPURDUAR | 2019-04-25 | 8:00 | 2019-04-26 | 18:00 | OCB | Powergrid, ER-II | Attending Oil leakage (Oil lekage from Conservator tank) and Associated Bay AMP work
3 | 125MVAR BUS REACTOR at Baharampore | 2019-04-10 | 9:00 | 2019-04-10 | 17:00 | ODB | Powergrid, ER-II | For balance construction activity (Fire fighting ring modification) pertaining to ERSS-XV.
4 | 80MVAR BUS REACTOR at Baharampore | 2019-04-11 | 9:00 | 2019-04-11 | 17:00 | ODB | Powergrid, ER-II | For Reactor AMP
5 | 400KV BERHAMPORE-SAGARDIGHI-1 | 2019-04-12 | 9:00 | 2019-04-13 | 17:00 | ODB | Powergrid, ER-II | Line Maintenance | WB
6 | 400KV MAIN BAY OF BUS REACTOR-1 (403 MAIN BAY) at Baharampore | 2019-04-16 | 9:00 | 2019-04-16 | 17:00 | ODB | Powergrid, ER-II | BAY AMP
7 | 400KV TIE BAY OF BHERAMARA-2/BUS REACTOR-1 (402 TIE BAY) at Alipurduar | 2019-04-17 | 9:00 | 2019-04-17 | 17:00 | ODB | Powergrid, ER-II | BAY AMP
8 | 400KV BERHAMPORE-SAGARDIGHI-1 | 2019-04-18 | 9:00 | 2019-04-18 | 17:00 | ODB | Powergrid, ER-II | Line Maintenance | WB
9 | 400KV BERHAMPORE-SAGARDIGHI-2 | 2019-04-20 | 9:00 | 2019-04-20 | 17:00 | ODB | Powergrid, ER-II | Line Maintenance | WB
10 | 400KV BERHAMPORE-BHERAMARA-1 | 2019-04-22 | 9:00 | 2019-04-23 | 17:00 | ODB | Modified SPS scheme implementation | Powergrid, ER-II | NLDC | Power order of Bheramara poles shall be restricted to 800MW.
11 | 400KV BERHAMPORE-BHERAMARA-2 | 2019-04-24 | 9:00 | 2019-04-25 | 17:00 | ODB | Modified SPS scheme implementation | Powergrid, ER-II | NLDC
12 | 400KV SAGARDIGHI-JEERAT LINE | 2019-04-24 | 9:00 | 2019-04-25 | 17:00 | ODB | Powergrid, ER-II | Live line defects attending and defective isulator replacement in line.. | WB
13 | 400KV SAGARDIGHI-SUBHASGRAM LINE | 2019-04-29 | 9:00 | 2019-04-30 | 17:00 | ODB | Powergrid, ER-II | Live line defects attending and defective isulator replacement in line. | WB
14 | 400KV MAIN BAY OF SAGARDIGHI-FARAKKA-2 at Sagardighi | 2019-04-09 | 9:00 | 2019-04-09 | 17:00 | ODB | Powergrid, ER-II | CT OIL SAMPLING | WB
15 | 400KV MAIN BAY OF SAGARDIGHI-JEERAT at Sagardighi | 2019-04-08 | 9:00 | 2019-04-08 | 17:00 | ODB | Powergrid, ER-II | CT OIL SAMPLING | WB
16 | 400KV RAJARHAT-JEERAT | 2019-03-25 | 10:00 | 2019-03-25 | 18:00 | ODB | Powergrid, ER-II | For erection of Bus Pipe of Gokarna Bay coming below Jeerat Line , shutdown require due to Clearance issue with Jeerat Line. Live line defects attending and defective isulator replacement in line. | WB
17 | 400KV RAJARHAT SUBHASGRAM | 2019-03-28 | 10:00 | 2019-03-29 | 18:00 | ODB | Powergrid, ER-II | For Termination of Farakka Line at Gantry Tower , Clearance issue with Subhashgram Line R-Ph LA Rlacement AT Subhasgram end and live line defects attending and defective isulator replacement in line. | WB
18 | 500MVA ICT-I AT RAJARHAT | 2019-04-06 | 10:00 | 2019-04-06 | 18:00 | ODB | Powergrid, ER-II | For attending LA Counter Jumper Connection i.e to attend BALANCE CONSTRUCTON WORK | WB
19 | 220kV Rajarhat Newtown-III Ckt-I | 2019-04-02 | 10:00 | 2019-04-02 | 18:00 | ODB | Powergrid, ER-II | For attending Wave Trap Jumper | WB
20 | 220kV Rajarhat Newtown-III Ckt-2 | 2019-04-02 | 10:00 | 2019-04-02 | 18:00 | ODB | Powergrid, ER-II | For attending Jumper inside Substation | WB
21 | 220kV Rajarhat Jeerat Ckt-I | 2019-04-04 | 10:00 | 2019-04-04 | 18:00 | ODB | Powergrid, ER-II | For attending Jumper inside Substation | WB
22 | 220kV Rajarhat Jeerat Ckt-II | 2019-04-04 | 10:00 | 2019-04-04 | 18:00 | ODB | Powergrid, ER-II | For attending Jumper inside Substation | WB
23 | 403 ICT#1 Main Bay at Subhasgram SS | 2019-04-01 | 9:00 | 2019-04-01 | 17:00 | ODB | Powergrid, ER-II | AMP work
24 | 406 ICT#2 Main Bay at Subhasgram SS | 2019-04-02 | 9:00 | 2019-04-02 | 17:00 | ODB | Powergrid, ER-II | AMP work
25 | 409 ICT#3 Main Bay at Subhasgram SS | 2019-04-03 | 9:00 | 2019-04-03 | 17:00 | ODB | Powergrid, ER-II | AMP work
26 | 412 ICT#4 Main Bay at Subhasgram SS | 2019-04-04 | 9:00 | 2019-04-04 | 17:00 | ODB | Powergrid, ER-II | AMP work
27 | 415 ICT#5 Main Bay at Subhasgram SS | 2019-04-05 | 9:00 | 2019-04-05 | 17:00 | ODB | Powergrid, ER-II | AMP Work
28 | 315 MVA ICT#1 at Subhasgram S/s | 2019-04-06 | 9:00 | 2019-04-06 | 17:00 | ODB | Powergrid, ER-II | Retrofitting of Numerical REF Relay | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
29 | 315 MVA ICT#2 at Subhasgram S/s | 2019-04-08 | 9:00 | 2019-04-08 | 17:00 | ODB | Powergrid, ER-II | Retrofitting of Numerical REF Relay | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
30 | 315 MVA ICT#3 at Powergrid,Subhasgram | 2019-04-09 | 9:00 | 2019-04-09 | 17:00 | ODB | Powergrid, ER-II | AMP of 315 MVA ICT#3. | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
31 | 315 MVA ICT#4 at Powergrid,Subhasgram | 2019-04-10 | 9:00 | 2019-04-10 | 17:00 | ODB | Powergrid, ER-II | AMP of 315 MVA ICT#4. | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
32 | 500 MVA ICT#5 at Powergrid,Subhasgram | 2019-04-11 | 9:00 | 2019-04-11 | 17:00 | ODB | Powergrid, ER-II | CSD Commissioing in 414 Bay | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
33 | 50 MVAR Sagardighi Line Reactor at Subhasgram S/s | 2019-04-12 | 9:00 | 2019-04-12 | 17:00 | ODB | Powergrid, ER-II | VT Section Work
34 | 220KV CESC CKT#2 (Bay No.203) at Powergrid,Subhasgram | 2019-04-13 | 9:00 | 2019-04-13 | 17:00 | ODB | Powergrid, ER-II | AMP work | WB
35 | 220KV CESC CKT#1 (Bay No.202) at Powergrid,Subhasgram | 2019-04-14 | 9:00 | 2019-04-14 | 17:00 | ODB | Powergrid, ER-II | AMP work | WB
36 | 220KV NEWTOWN LINE (Bay No.205) at Powergrid,Subhasgram | 2019-04-15 | 9:00 | 2019-04-15 | 17:00 | ODB | Powergrid, ER-II | AMP work | WB
37 | 220KV KLC Bantala Line (Bay No.206) at Powergrid,Subhasgram | 2019-04-16 | 9:00 | 2019-04-16 | 17:00 | ODB | Powergrid, ER-II | AMP work | WB
38 | 402 Tie Bay of 315 MVA ICT#1 and 400 KV Subhasgram Sagardighi Line | 2019-04-17 | 9:00 | 2019-04-17 | 17:00 | ODB | Powergrid, ER-II | Retrofitting of A/R Relay in 402 Bay
39 | 405 Tie Bay of 315 MVA ICT#2 and 400 KV Subhasgram Jeerat Line | 2019-04-18 | 9:00 | 2019-04-18 | 17:00 | ODB | Powergrid, ER-II | Retrofitting of A/R Relay in 405 Bay
40 | 401 Main Bay of Subhasgram Sagardighi Line at Subhasgram SS | 2019-04-19 | 9:00 | 2019-04-19 | 17:00 | ODB | Powergrid, ER-II | Retrofitting of A/R Relay in 401 Bay
41 | 404 Main Bay of Subhasgram Rajarhat Line at Subhasgram SS | 2019-04-20 | 9:00 | 2019-04-20 | 17:00 | ODB | Powergrid, ER-II | Retrofitting of A/R Relay in 404 Bay
42 | 414 Tie Bay of 500 MVA ICT#5 and 400 KV Subhasgram Haldia Line-2 | 2019-04-21 | 9:00 | 2019-04-23 | 17:00 | OCB | Powergrid, ER-II | Pole Inspection of 414 Breaker
43 | 220 KV Birpara-Siliguri Ckt-I | 2019-04-08 | 8:00 | 2019-04-08 | 17:30 | ODB | Powergrid, ER-II | Retrofitting of Numerical Distance Relay and Various shutdown related TLM works
44 | 220 KV Birpara-Siliguri Ckt-I | 2019-04-09 | 8:00 | 2019-04-09 | 17:30 | ODB | Powergrid, ER-II | Various Shutdown related TLM works
45 | 220 KV Birpara-Siliguri Ckt-II | 2019-04-10 | 8:00 | 2019-04-10 | 17:30 | ODB | Powergrid, ER-II | Retrofitting of Numerical Distance Relay and Various shutdown related TLM works
46 | 220 KV Birpara-Siliguri Ckt-II | 2019-04-11 | 8:00 | 2019-04-11 | 17:30 | ODB | Powergrid, ER-II | Various Shutdown related TLM works
47 | 220KV Birpara-Chukha Ckt-I | 2019-04-12 | 8:00 | 2019-04-12 | 17:30 | ODB | Powergrid, ER-II | Retrofitting of Numerical Distance Relay
48 | 220KV Birpara-Chukha Ckt-II | 2019-04-13 | 8:00 | 2019-04-13 | 17:30 | ODB | Powergrid, ER-II | Retrofitting of Numerical Distance Relay | NLDC
49 | 220KV Birpara-Malbase Line | 2019-04-16 | 8:00 | 2019-04-16 | 17:30 | ODB | Powergrid, ER-II | New Arching Horn fixing work at different Tension Towers | NLDC
50 | 400 KV Binaguri-Tala Ckt-III | 2019-04-17 | 8:00 | 2019-04-17 | 17:30 | ODB | Powergrid, ER-II | Broken Insulator Replacement,Line defect rectification & Line AMP works. | NLDC
51 | 400 KV Binaguri-Tala Ckt-IV | 2019-04-18 | 8:00 | 2019-04-18 | 17:30 | ODB | Powergrid, ER-II | Broken Insulator Replacement,Line defect rectification & Line AMP works. | NLDC
52 | 220KV SILIGURI-KISHENGUNJ # I & II | 2019-04-03 | 8:00 | 2019-04-04 | 17:00 | OCB | Powergrid, ER-II | For shorting at Anch-I tower (M/C)to by-pass the LILO portion of 220KV SLG-KNE-DLK -I&II line terminating Kishanganj S/S . This arrangement required for tower erection on new Pile foundation near Kishanganj S/S. After shoring line will be established as 220KV SLG-DLK line . Antipacted outage duration of LILO M/C portion feeding Kishanganj S/S 40 days.
53 | 220KV DALKHOLA-KISHENGUNJ # I & II | 2019-04-03 | 8:00 | 2019-04-04 | 17:00 | OCB | Powergrid, ER-II | For shorting at Anch-I tower (M/C)to by-pass the LILO portion of 220KV SLG-KNE-DLK -I&II line terminating Kishanganj S/S . This arrangement required for tower erection on new Pile foundation near Kishanganj S/S. After shoring line will be established as 220KV SLG-DLK line . Antipacted outage duration of LILO M/C portion feeding Kishanganj S/S 40 days.
54 | 220KV Main Bus-I at Dalkhola | 2019-04-22 | 8:00 | 2019-04-22 | 17:00 | ODB | Powergrid, ER-II | Jumper Replacement Work | WB
55 | 400 KV Malda-New Purnea -I | 2019-04-10 | 8:00 | 2019-04-11 | 17:00 | ODB | Powergrid, ER-II | S/D required for rectification of OPGW Peak Bend,CT replacement at Malda end | NLDC
56 | 132 KV kurseong-Rangit | 2019-04-01 | 9:00 | 2019-04-03 | 17:00 | ODB | Powergrid, ER-II | Sag/Tension correction between Loc 51-52, due to land slide. Complete release of tension required. | WB
57 | 132 KV siliguri Melli | 2019-04-04 | 9:00 | 2019-04-05 | 17:00 | ODB | Powergrid, ER-II | For 3-Ph A/R implementation. | SIKKIM
58 | 132 KV siliguri kurseong | 2019-04-06 | 9:00 | 2019-04-08 | 17:00 | ODB | Powergrid, ER-II | Line defect rectification & Line AMP works. | WB
59 | 400KV Binaguri Rangpo Ckt-1&2 | 2019-04-01 | 9:00 | 2019-04-30 | 17:00 | OCC | Line reconductoring job | Powergrid, ER-II | NLDC | Due to High hydro , SD may not be Feasible. If SD required consent from Teesta & Dickchu other shall be obtained.
60 | 220 KV Bus 1&2 with siliguri 1&2, Birpara1&2, Bus sectionalizer 1&2 | 2019-04-13 | 9:00 | 2019-04-13 | 15:00 | ODB | Powergrid, ER-II | for stringing of Jackbus of 315 MVA ICT#3(Construction package-Techno) under ERSS-XVII | WB | MAY BE AVOIDED ON ELECTION DAYS
61 | 220 KV Bus #1 at Binaguri | 2019-04-15 | 9:00 | 2019-04-15 | 17:00 | ODB | Powergrid, ER-II | Equipment erection of 220 KV ICT#3 bay under ERSS-XVII | WB
62 | 220 KV Bus #2 at Binaguri | 2019-04-16 | 9:00 | 2019-04-16 | 17:00 | ODB | Powergrid, ER-II | Equipment erection of 220 KV ICT#3 bay under ERSS-XVII | WB
63 | 400KV Bus#1 at Binaguri | 2019-04-17 | 9:00 | 2019-04-17 | 17:00 | ODB | Powergrid, ER-II | GIS bushing erection under 400KV Bus#1under ERSS-XVII | NLDC
64 | 400KV Bus#2 at Binaguri | 2019-04-18 | 9:00 | 2019-04-18 | 17:00 | ODB | Powergrid, ER-II | GIS bushing erection under 400KV Bus#2 under ERSS-XVII | NLDC
65 | 50 MVA ICT 132/66 KV at Powergrid,Gangtok | 2019-04-04 | 9:00 | 2019-04-04 | 18:00 | ODB | Powergrid, ER-II | For AnnualAMp Works | SIKKIM
66 | 50 MVA ICT 132/66KV at Powergrid,Gangtok | 2019-04-09 | 9:00 | 2019-04-09 | 18:00 | ODB | Powergrid, ER-II | For AnnualAMp Works | SIKKIM
67 | 132KV Gangtok-Rangpo Line | 2019-04-11 | 9:00 | 2019-04-11 | 12:00 | ODB | Powergrid, ER-II | Line A/R implementation | SIKKIM
68 | 66 KV Gangtok-Tadong Line | 2019-04-16 | 9:00 | 2019-04-16 | 12:00 | ODB | Powergrid, ER-II | For AnnualAMp Works | SIKKIM
69 | 66 KV Gangtok-LLHP Line | 2019-04-18 | 9:00 | 2019-04-18 | 17:00 | ODB | Powergrid, ER-II | For AnnualAMp Works & Relay replacement | SIKKIM
70 | 132kv Rangit -Rangpo Ckt | 2019-04-04 | 9:00 | 2019-04-05 | 17:30 | OCB | Powergrid, ER-II | LOC 52 & 53 balance porcelain insulator replacement work due to power line crossing | SIKKIM
71 | Rangpo - Teesta -V Line 2 | 2019-04-04 | 8:00 | 2019-04-08 | 17:00 | OCB | Powergrid, ER-II | For rectification of SF6 gas leakage repair work
72 | 220KV BUS-1 at Rangpo | 2019-04-09 | 8:00 | 2019-04-11 | 17:00 | OCB | Powergrid, ER-II | For rectification of SF6 gas leakage repair work(both Shutdown needed on same dates) & TLM insulator changing work
73 | 220KV Rangpo NEW MELLI line | 2019-04-09 | 8:00 | 2019-04-13 | 17:00 | OCB | Powergrid, ER-II
74 | 400\220kV 315 MVA ICT-2 at Rangpo | 2019-04-12 | 8:00 | 2019-04-15 | 17:00 | OCB | Powergrid, ER-II | For rectification of SF6 gas leakage repair work,
75 | 220\132 Kv 100 MVA ICT-2 at Rangpo | 2019-04-16 | 8:00 | 2019-04-19 | 17:00 | OCB | Powergrid, ER-II | For rectification of SF6 gas leakage repair work,
76 | 400\220kV 315 MVAICT -4 at Rangpo | 2019-04-20 | 8:00 | 2019-04-24 | 17:00 | OCB | Powergrid, ER-II | For rectification of SF6 gas leakage repair work,
77 | 400\220kV 315 MVAICT -3 at Rangpo | 2019-04-25 | 8:00 | 2019-04-29 | 17:00 | OCB | Powergrid, ER-II | For rectification of SF6 gas leakage repair work,
78 | 132KV Rangpo-Chuzachen line | 2019-04-14 | 9:00 | 2019-04-14 | 18:00 | ODB | Powergrid, ER-II | Line A/R implementation
79 | 132KV Rangpo Melli | 2019-04-18 | 9:00 | 2019-04-21 | 18:00 | ODB | Powergrid, ER-II | Sag adjustment work in Span LILO 84 - LILO85 - LILO86 under Sikkim Govt. jurisdiction | SIKKIM
80 | 132kV BUS-1 at Rangpo | 2019-04-02 | 9:00 | 2019-04-12 | 17:00 | OCB | Powergrid, ER-II | For Bus extension to new Chuzachen bays (Construction works) | SIKKIM
81 | 132kV BUS-2 at Rangpo | 2019-04-14 | 9:00 | 2019-04-24 | 17:00 | OCB | Powergrid, ER-II | For Bus extension to new Chuzachen bays (Construction works) | SIKKIM
82 | 132kV Rangpo Chuzachen and 132kV Rangpo Melli | 2019-04-28 | 8:00 | 2019-04-28 | 18:00 | ODB | Powergrid, ER-II | For new Chuzachen bays LILO (Construction works) | SIKKIM
83 | 220 KV TBC at Malda | 2019-04-01 | 8:00 | 2019-04-30 | 17:00 | OCB | Powergrid, ER-II | ERSS-XVII-B Constructional work | WB | DALKHOLA BUS COUPLER SHALL BE OPENED
84 | 400KV TBC at Malda | 2019-04-01 | 8:00 | 2019-04-30 | 17:00 | OCB | Powergrid, ER-II | ERSS-XVII-B Constructional work | WB | DALKHOLA BUS COUPLER SHALL BE OPENED
85 | 400 KV Malda-Purnea-II at Malda | 2019-04-17 | 8:00 | 2019-04-17 | 17:00 | ODB | Powergrid, ER-II | CT Replacement at Malda end | NLDC
86 | 400KV BUS-I at Malda | 2019-04-02 | 8:00 | 2019-04-02 | 17:00 | ODB | Powergrid, ER-II | Isolator opening(ERSS-XVII-B Constructional work) | WB
87 | 400KV BUS-II at Malda | 2019-04-03 | 8:00 | 2019-04-03 | 17:00 | ODB | Powergrid, ER-II | Isolator opening(ERSS-XVII-B Constructional work) | WB
88 | 400KV BUS-I at Malda | 2019-04-23 | 8:00 | 2019-04-24 | 17:00 | OCB | Powergrid, ER-II | Isolator closing(ERSS-XVII-B Constructional work) | WB
89 | 400 KV BUS-II at Malda | 2019-04-25 | 8:00 | 2019-04-26 | 17:00 | OCB | Powergrid, ER-II | Isolator closing(ERSS-XVII-B Constructional work) | WB
90 | 220KV BUS-I at Malda | 2019-04-04 | 8:00 | 2019-04-04 | 16:00 | ODB | Powergrid, ER-II | To conect isolator jumper(ERSS-XVII-B Constructional work ) | WB
91 | 220KV BUS-II at Malda | 2019-04-05 | 8:00 | 2019-04-05 | 17:00 | ODB | Powergrid, ER-II | To conect isolator jumper(ERSS-XVII-B Constructional work ) | WB
92 | 220 KV MALDA-DALKHOLA-I | 2019-04-10 | 8:00 | 2019-04-10 | 17:00 | ODB | Powergrid, ER-II | A/R Retrofitting,LA base insulator change in R-ph at Dlkhola | WB
93 | 220 KV MALDA-DALKHOLA-II | 2019-04-11 | 8:00 | 2019-04-11 | 17:00 | ODB | Powergrid, ER-II | A/R Retrofitting | WB
94 | A/R OF 400 KV Farakka- Sagradighi-II | 2019-04-01 | 9:00 | 31/04/19 | 18:00 | ODB | Powergrid, ER-II | Auto reclose to be kept on Non auto mode from both end for PID testing of insulator. | WB
95 | 400 KV BUS-I of NTPC Farakka | 2019-04-01 | 9:00 | 2019-04-01 | 18:00 | ODB | Powergrid, ER-II | For disconnecting BUS isolator of bay no-22 from BUS-I (For augmentation of BUS Isolator from 2000A to 3150 A rating under ERSS-XV projects).
96 | 400 KV Farakka- Berhampur-II with Reactor at Farakka | 2019-04-02 | 9:00 | 2019-04-03 | 18:00 | ODB | Powergrid, ER-II | For balance protection scheme checking of bay-23 ( Tie bay of 400 KV Fkk- Bhp-II and 400 KV Fkk- Khg-I) with respect with bay-24 & to carry out punch point works in TL
97 | 400 KV Farakka- Berhampur-I | 2019-04-04 | 9:00 | 2019-04-05 | 18:00 | ODB | Powergrid, ER-II | For protection scheme checking of Bay-34 with respect of bay-33 after upgradation of bay-34 under ERSS-XV projects
98 | 400 KV Farakka- Kahalgaon-III line | 2019-04-08 | 9:00 | 2019-04-09 | 18:00 | ODB | Powergrid, ER-II | For Jumper coonnection, relay setting change & Bay stability between Bay- 34 & 35 after upgradation of bay-34 under ERSS-XV projects.
99 | 400 KV BUS-I of NTPC Farakka | 2019-04-10 | 9:00 | 2019-04-10 | 18:00 | ODB | Powergrid, ER-II | For connecting BUS isolator of bay no-22 to BUS-I (After augmentation of BUS Isolator from 2000A to 3150 A rating under ERSS-XV projects).
100 | 400 KV Farakka- Kahalgaon-I line | 2019-04-11 | 9:00 | 2019-04-11 | 18:00 | ODB | Powergrid, ER-II | For connecting bay-22 (Main Bay of 400 KV Farakka- Kahalgaon-I) after augmentation of Isolator & CT from 2000A to 3150 A rating under ERSS-XV projects & bay stability between bay- 23 & 22.
101 | 400 KV Farakka-Gokarna-I | 2019-04-12 | 9:00 | 2019-04-13 | 18:00 | ODB | Powergrid, ER-II | For Event Logger commissioning (Integration with NTPC system) under ERSS-V. | WB
102 | 400 KV Farakka-Gokarna-II | 2019-04-15 | 9:00 | 2019-04-16 | 18:00 | ODB | Powergrid, ER-II | For Event Logger commissioning (Integration with NTPC system) under ERSS-V. | WB
103 | 400 KV Farakka- Sagradighi-II | 2019-04-11 | 9:00 | 2019-04-12 | 18:00 | ODB | Powergrid, ER-II | Reactification of damage earthpeak at loc no-15 & 103 | WB
104 | 400KV BUS 3 at Durgapur | 2019-04-01 | 9:30 | 2019-04-01 | 17:30 | ODB | Powergrid, ER-II | ICT -3 jumper connection
105 | 220 KV BUS -2 at Durgapur | 2019-04-02 | 9:30 | 2019-04-02 | 17:30 | ODB | Powergrid, ER-II | ICT -3 jumper connection | DVC
106 | 400KV BUS 1 at Durgapur | 2019-04-04 | 9:30 | 2019-04-04 | 17:30 | ODB | Powergrid, ER-II | AMP WORKS
107 | 400KV BUS 2 at Durgapur | 2019-04-05 | 9:30 | 2019-04-05 | 17:30 | ODB | Powergrid, ER-II | AMP WORKS
108 | 220 KV Durgapur DVC-1 | 2019-04-06 | 9:30 | 2019-04-06 | 17:30 | ODB | Powergrid, ER-II | Line CT Tan Delta test | DVC
109 | 400KV BUS 4 at Durgapur | 2019-04-08 | 9:30 | 2019-04-08 | 17:30 | ODB | Powergrid, ER-II | AMP WORKS
110 | 220 KV Durgapur DVC-II | 2019-04-24 | 9:30 | 2019-04-24 | 17:30 | ODB | Powergrid, ER-II | Line CT Tan Delta test | DVC
111 | 418 bay ( ICT-II main Bay) at Durgapur | 2019-04-08 | 9:30 | 2019-04-10 | 17:30 | ODB | Powergrid, ER-II | Interrupter replacement of main CB
112 | 420 Bay ( Mithon-II & Future Tie bay) at Durgapur | 2019-04-11 | 9:30 | 2019-04-13 | 17:30 | ODB | Powergrid, ER-II | Gasket replace in main pole
113 | 408 bay ( ICT-I & B'nagar -1 tie Bay) at Durgapur | 2019-04-15 | 9:30 | 2019-04-15 | 17:30 | ODB | Powergrid, ER-II | CT Replace & AMP WORK
114 | 409 bay ( ICT-I Main Bay) at Durgapur | 2019-04-16 | 9:30 | 2019-04-16 | 17:30 | ODB | Powergrid, ER-II | AMP WORK
115 | 404 bay ( B'Nagar-2 Main Bay) at Durgapur | 2019-04-17 | 9:30 | 2019-04-17 | 17:30 | ODB | Powergrid, ER-II | AMP WORK
116 | 417 bay ( ICT-2 & FUTURE TIE Bay) at Durgapur | 2019-04-18 | 9:30 | 2019-04-18 | 17:30 | ODB | Powergrid, ER-II | AMP WORK
117 | 400KV BUS SECTION -2 (BS-2) BAY at Durgapur | 2019-04-20 | 9:30 | 2019-04-20 | 17:30 | ODB | Powergrid, ER-II | AMP WORK
118 | 220KV BUS SECTION BAY (205) at Durgapur | 2019-04-22 | 9:30 | 2019-04-22 | 17:30 | ODB | Powergrid, ER-II | AMP WORK
119 | 400KV BUS SECTION -1 (BS-1) BAY at Durgapur | 2019-04-23 | 9:30 | 2019-04-23 | 17:30 | ODB | Powergrid, ER-II | AMP WORK
120 | 220 KV S/C STPS - Chandil TL-(TL-229-230)-WBSETCL | 2019-04-09 | 192:00 | 2019-04-10 | 408:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 83/0 (DD+9)-84/0( DD+9). Span Length-160 mtr | WB
121 | 400 KV D/C Maithan - Jamshedpur(TATA) (TL -(316-317) | 2019-04-11 | 192:00 | 2019-04-12 | 408:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 85/0 (DD+25)-86/0( DD+25+1.5 RC). Span Length-262 mtr
122 | 132 KV D/C Purulia - Jamshedpur (TL 104- MBE-DA+0—TL 105-MBE-DA+0) ) | 2019-04-17 | 192:00 | 2019-04-18 | 408:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 95/0 (DD+9)-96/0( DD+18). Span Length-258 mtr | DVC | AFTER 15/04/19 CHANDIL ASSISTENCE
123 | 400 KV D/C Durgapur - Jamshedpur (TL-286-287) | 2019-04-25 | 192:00 | 2019-04-26 | 408:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 101/0 (DD+25+1.5 RC)-102/0( DD+25+1.5 RC). Span Length-208 mtr
124 | 400 KV S/C Durgapur - Jamshedpur TL- ( TL-329-330) | 2019-04-23 | 192:00 | 2019-04-24 | 408:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 102/0 (DD+25+1.5 RC)-103/0( DD+9). Span Length-208 mtr
125 | 132 KV D/C Bishnupur - Khatra (TL- 180-181) | 2019-04-26 | 192:00 | 2019-04-27 | 408:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 134/4 (DD+9+3 RC)-135/0( DD+9). Span Length-320 mtr | WB
126 | 132 KV D/C CK Road - Medinipur TL | 2019-04-11 | 192:00 | 2019-04-12 | 408:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 162/0 (DD+9)-163/0( DD+9). Span Length-265 mtr | WB
127 | Tapping point of 400 KV D/C MID-KGP-CHANDITALA LILO LINE-( TL-56/0 &55/0 ) | 2019-04-28 | 192:00 | 2019-04-30 | 408:00 | OCB | Powergrid, ER-II | For TAPPING of 400 KV CKTL-Loop In AP-1/0( DD+0) SPAN-200 MTR and LOOP OUT AP-29/0-(DD+0)- - SPAN 200 MTR-- Subject to approval of ENGG and AM DEPT ******** | WB
128 | Maithon-Mejia #1 Line | 2019-04-01 | 10:00 | 2019-04-01 | 11:00 | ODB | Powergrid, ER-II | For oil sampling of line CT | DVC
129 | Maithon-Kahalgaon-2 Line | 2019-04-03 | 9:00 | 2019-04-04 | 18:00 | ODB | Powergrid, ER-II | Replacement of Main Bay and Line Bay CT
130 | 500MVA ICT-1 at Maithon SS. | 2019-04-05 | 7:00 | 2019-04-06 | 18:00 | ODB | Powergrid, ER-II | Rectification of MOG, CT replacement Main and X-mer bay, and AMP | DVC
131 | 400 kV Bus-3 at Maithon SS. | 2019-04-08 | 10:00 | 2019-04-08 | 14:00 | ODB | Powergrid, ER-II | Project Work under ERSS-XVII (Dismentling of Jumpers)
132 | 400 kV Bus-4 at Maithon SS. | 2019-04-09 | 10:00 | 2019-04-09 | 14:00 | ODB | Powergrid, ER-II | Project Work under ERSS-XVII (Dismentling of Jumpers)
133 | 220KV Maithon-Dhanbad#1 Line | 2019-04-10 | 9:00 | 2019-04-10 | 17:00 | ODB | Powergrid, ER-II | Bay AMP works | DVC
134 | 400KV Maithon-Mejia #3 line | 2019-04-11 | 9:00 | 2019-04-12 | 17:00 | ODB | Powergrid, ER-II | For power line crossing work i.r.o ERSS-XVII. | DVC
135 | 400KV Bus-2 at Maithon SS. | 2019-04-13 | 9:00 | 2019-04-13 | 17:00 | ODB | Powergrid, ER-II | For Bus CVT replacement work
136 | 400 kV Bus-3 at Maithon SS. | 2019-04-22 | 10:00 | 2019-04-22 | 14:00 | ODB | Powergrid, ER-II | Project Work under ERSS-XVII (Reconnection of Jumper)
137 | 400 kV Bus-4 at Maithon SS. | 2019-04-22 | 10:00 | 2019-04-22 | 14:00 | ODB | Powergrid, ER-II | Project Work under ERSS-XVII (Reconnection of Jumper)
138 | 400KV Maithon-Right Bank # 2 line | 2019-04-01 | 8:00 | 2019-04-08 | 18:00 | Continous basis | Powergrid, ER-II | Re conductoring work under ERSS-XVII.
139 | 400KV Maithon-Right Bank # 2 line | 2019-04-24 | 8:00 | 2019-04-30 | 18:00 | Continous basis | Powergrid, ER-II | Re conductoring work under ERSS-XVII.
140 | 400KV Maithon-Right Bank # 1 line | 2019-04-09 | 8:00 | 2019-04-23 | 18:00 | Continous basis | Powergrid, ER-II | Re conductoring work under ERSS-XVII.
141 | 400KV Maithon-Jamshedpur line. | 2019-04-08 | 9:00 | 2019-04-09 | 18:.00 | ODB | Powergrid, ER-II | Insulator replacement work.
142 | 400KV Mejia-Jamshedpur line | 2019-04-10 | 9:00 | 2019-04-11 | 18:.00 | ODB | Powergrid, ER-II | Insulator replacement work. | DVC
143 | 400KV Maithon-Durgapur# 2 line | 2019-04-15 | 9:00 | 2019-04-15 | 18:.00 | ODB | Powergrid, ER-II | Jumper rectification .
144 | 400KV PATNA-BALIA-I | 2019-04-10 | 8:00 | 2019-04-10 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer | NLDC
145 | 400KV PATNA-BALIA-II | 2019-04-11 | 8:00 | 2019-04-11 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer | NLDC
146 | 400KV PATNA-BALIA-III | 2019-04-12 | 8:00 | 2019-04-13 | 17:00 | ODB | Power line crossing work of 400 kV Patna - Nabinagar line | POWERGRID ER-I | NLDC | Subject to availability all other lines in ER-NR corridor.
147 | 400KV PATNA-BALIA-IV | 2019-04-12 | 8:00 | 2019-04-13 | 17:00 | ODB | Power line crossing work of 400 kV Patna - Nabinagar line | POWERGRID ER-I | NLDC
148 | 765 kV New Ranchi - Dharamjaygarh CKT-II | 2019-04-23 | 9:00 | 2019-04-27 | 18:00 | ODB | POWERGRID ER-I | for replacement of broken Glass insulators damaged by miscreants about 140 nos. locations | NLDC
149 | 400KV BIHARSHARIFF-BALIA-I | 2019-04-23 | 8:00 | 2019-04-24 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
150 | 400KV BIHARSHARIFF-BALIA-II | 2019-04-25 | 8:00 | 2019-04-26 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
151 | 400KV PATNA-BALIA-I | 2019-04-27 | 8:00 | 2019-04-27 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
152 | 400KV PATNA-BALIA-II | 2019-04-28 | 8:00 | 2019-04-28 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
153 | 765KV GAYA-BALIA-S/C | 2019-03-26 | 8:00 | 2019-04-10 | 18:00 | ODB | POWERGRID ER-I | FOR TOWER STRENGTHENING WORK. | NLDC | Subject to availability all other lines in ER-NR corridor.
154 | 400KV BIHARSHARIFF - VARANASI - I | 2019-04-01 | 8:00 | 2019-04-29 | 18:00 | OCB | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | POWERGRID ER-I | NLDC | After return of 400kv Biharsariff-Sasaram D/C
155 | 400KV BIHARSHARIFF - VARANASI - II | 2019-04-01 | 8:00 | 2019-04-29 | 18:00 | OCB | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | POWERGRID ER-I | NLDC
156 | 400KV BIHARSHARIFF - SASARAM- I | 2019-04-01 | 8:00 | 2019-04-25 | 18:00 | OCB | POWERGRID ER-I | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | NLDC
157 | 400KV BIHARSHARIFF - SASARAM- II | 2019-04-01 | 8:00 | 2019-04-25 | 18:00 | OCB | POWERGRID ER-I | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | NLDC
158 | 765 KV S/C Sasaram-Fatehpur | 2019-04-15 | 7:00 | 2019-04-30 | 19:00 | ODB | POWERGRID ER-I | FOR TOWER STRENTHENING WORK | NLDC | Subject to availability all other lines in ER-NR corridor.
159 | 765 KV S/C Gaya-Varanasi-II | 2019-04-11 | 7:00 | 2019-04-12 | 18:00 | ODB | for rectification of defects identified | POWERGRID ER-I | NLDC | Subject to availability all other lines in ER-NR corridor.
160 | 400 KV RANCHI-SIPAT-1 LINE AND ITS 80 MVAR LINE REACTOR AT RANCHI | 2019-04-22 | 10:00 | 2019-04-22 | 17:00 | ODB | POWERGRID ER-I | AMP & Replacement of defective CAPTHOR in FSC AND To attend oil leakage in Line Reactor | NLDC
161 | 765 kV Gaya-Varanasi-2 | 2019-04-23 | 9:00 | 2019-04-24 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | NLDC
162 | 220 kV Pusauli - Sahupuri | 2019-04-02 | 9:00 | 2019-04-05 | 18:00 | OCB | POWERGRID ER-I | TO FACILITATE THE SHUT DOWN OF ICT - I AT PUSAULI SS | NLDC
163 | 400kV JAMSHEDPUR -DURGAPUR LINE | 2019-04-02 | 9:30 | 2019-04-02 | 17:30 | ODB | POWERGRID ER-I | Static Auto reclose relay to be replaced with numerical relay
164 | 400kV Ranchi - Rourkela -II | 2019-04-04 | 9:30 | 2019-04-04 | 17:30 | ODB | POWERGRID ER-I | Defective Insulator replacement work Loc no300
165 | 400kV JAMSHEDPUR - Mejia LINE | 2019-04-06 | 9:30 | 2019-04-06 | 17:30 | ODB | POWERGRID ER-I | Static Auto reclose relay to be replaced with numerical relay | DVC
166 | 400kV JAMSHEDPUR - Maithon Line | 2019-04-08 | 9:30 | 2019-04-08 | 17:30 | ODB | POWERGRID ER-I | Static Auto reclose relay to be replaced with numerical relay
167 | 400kV JAMSHEDPUR - Chaibasa-I | 2019-04-10 | 9:30 | 2019-04-10 | 17:30 | ODB | POWERGRID ER-I | Static Auto reclose relay to be replaced with numerical relay
168 | 400kV JAMSHEDPUR - Chaibasa-II | 2019-04-12 | 9:30 | 2019-04-12 | 17:30 | ODB | POWERGRID ER-I | Static Auto reclose relay to be replaced with numerical relay
169 | 400KV MAIN BAY OF ANDAL -I AT JAMSHEDPUR | 2019-04-17 | 9:30 | 2019-04-17 | 17:30 | ODB | POWERGRID ER-I | Maintenance of CB Catch gear unit
170 | 400KV MAIN BAY OF ANDAL -II AT JAMSHEDPUR | 2019-04-18 | 9:30 | 2019-04-18 | 17:30 | ODB | POWERGRID ER-I | Maintenance of CB Catch gear unit
171 | 400kV JSR - Baripada S/C | 2019-04-19 | 9:30 | 2019-04-19 | 17:30 | ODB | POWERGRID ER-I | Defective Insulator replacement work Loc no 241
172 | 765KV 240MVAR B/R-2 AT NEW RANCHI | 2019-04-02 | 9:00 | 2019-04-03 | 17:00 | ODB | POWERGRID ER-I | AMP | NLDC
173 | 765/400KV, 1500MVA ICT-2 AT NEW RANCHI | 2019-04-04 | 9:00 | 2019-04-05 | 17:00 | ODB | POWERGRID ER-I | AMP | NLDC
174 | 765/400 KV, 1500MVA ICT-1 AT NEW RANCHI | 2019-04-06 | 9:00 | 2019-04-06 | 17:00 | ODB | POWERGRID ER-I | AMP | NLDC
175 | 765KV Bus-1 AT NEW RANCHI | 2019-04-08 | 9:00 | 2019-04-08 | 17:00 | ODB | POWERGRID ER-I | AMP | NLDC
176 | 50MVAR L/R-1 (Non Switchable) of 400KV New Purulia -1 AT NEW RANCHI | 2019-04-11 | 9:00 | 2019-04-11 | 17:00 | ODB | POWERGRID ER-I | AMP WORK The mentioned line will be out for 10min each time for taking out and taking in the L/R | WB
177 | 400KV BUS-1 AT NEW RANCHI | 2019-04-15 | 9:00 | 2019-04-15 | 17:00 | ODB | POWERGRID ER-I | AMP | JSEB
178 | 765KV Tie bay of 240MVAR B/R-1 and Future AT NEW RANCHI | 2019-04-16 | 9:00 | 2019-04-16 | 17:00 | ODB | POWERGRID ER-I | AMP | NLDC
179 | 400KV BUS-2 AT NEW RANCHI | 2019-04-20 | 9:00 | 2019-04-20 | 17:00 | ODB | POWERGRID ER-I | AMP | JSEB
180 | 765 KV MAIN BAY 1500MVA ICT-2 AT NEW RANCHI | 2019-04-22 | 9:00 | 2019-04-22 | 17:00 | ODB | POWERGRID ER-I | AMP | NLDC
181 | 765KV BUS-2 AT NEW RANCHI | 2019-04-29 | 9:00 | 2019-04-29 | 17:00 | ODB | POWERGRID ER-I | AMP | NLDC
182 | 765KV , 240MVAR B/R-1 AT NEW RANCHI | 2019-04-30 | 9:00 | 31/04/19 | 17:00 | ODB | POWERGRID ER-I | AMP | NLDC
183 | VSC-1 (+/- 150MVAR) OF STATCOM AT NEW RANCHI | 2019-04-22 | 9:00 | 2019-04-25 | 17:00 | ODB | POWERGRID ER-I | Connector tightening of Bus Duct
184 | VSC-2 (+/- 150MVAR) OF STATCOM AT NEW RANCHI | 2019-04-15 | 9:00 | 2019-04-18 | 17:00 | ODB | POWERGRID ER-I | Connector tightening of Bus Duct
185 | 400KV New Ranchi- Ranchi -1 | 2019-04-09 | 9:00 | 2019-04-09 | 18:00 | ODB | POWERGRID ER-I | For Insulator changing work, tightning of keeper, CC ring, Jumper etc.
186 | 400KV New Ranchi- Ranchi -2 | 2019-04-10 | 9:00 | 2019-04-10 | 18:00 | ODB | POWERGRID ER-I | For Insulator changing work, tightning of keeper, CC ring, Jumper etc.
187 | 400KV New Ranchi- Ranchi Ckt-3 | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | POWERGRID ER-I | For Insulation sleeve installation work at Loc 054-055 OF 400 kV Ranchi-New Ranchi CKT-3 & 4.
188 | 400KV New Ranchi- Ranchi Ckt-4 | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | POWERGRID ER-I | For Insulation sleeve installation work at Loc 054-055 OF 400 kV Ranchi-New Ranchi CKT-3 & 4.
189 | 400kv Ranchi-Maithan(PG) -s/c | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | POWERGRID ER-I | For Insulation sleeve installation work at Loc 054-055 OF 400 kV Ranchi-New Ranchi CKT-3 & 4.
190 | 400 kv Ranchi-Raghunathpur -I | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | POWERGRID ER-I | For Insulation sleeve installation work at Loc 054-055 OF 400 kV Ranchi-New Ranchi CKT-3 & 4.
191 | 400 kV Chandwa-Gaya CKT-I | 2019-04-18 | 9:00 | 2019-04-18 | 18:00 | ODB | POWERGRID ER-I | For shifting of 33 kV under crossing line of JUSNL (400 kV Chandwa-Gaya T/L Line tripped due to less clearence). | NLDC
192 | 400 kV Chandwa-Gaya CKT-II | 2019-04-18 | 9:00 | 2019-04-18 | 18:00 | ODB | POWERGRID ER-I | For shifting of 33 kV under crossing line of JUSNL (400 kV Chandwa-Gaya T/L Line tripped due to less clearence). | NLDC
193 | 765 kV New Ranchi - Dharamjaygarh CKT-II | 2019-04-23 | 9:00 | 2019-04-27 | 18:00 | ODB | POWERGRID ER-I | for replacement of broken Glass insulators damaged by miscreants about 140 nos. locations | NLDC
194 | 400KV BUS-1 AT DALTANAGNJ | 2019-04-07 | 9:30 | 2019-04-07 | 17:30 | ODB | POWERGRID ER-I | AMP | JSEB
195 | 400kV BUS-2 AT DALTANAGNJ | 2019-04-08 | 9:30 | 2019-04-08 | 17:30 | ODB | POWERGRID ER-I | AMP | JSEB
196 | 400 KV DALTANGNAJ-SASARAM -1 | 2019-04-11 | 9:30 | 2019-04-11 | 17:30 | ODB | POWERGRID ER-I | BAY AMP
197 | 400 KV DALTANGNAJ-SASARAM -2 | 2019-04-12 | 9:30 | 2019-04-12 | 17:30 | ODB | POWERGRID ER-I | BAY AMP
198 | 132kV DALTONGANJ- DALTONGANJ-1 | 2019-04-13 | 9:30 | 2019-04-13 | 17:30 | ODB | POWERGRID ER-I | BAY AMP
199 | 132kV DALTONGANJ- DALTONGANJ-2 | 2019-04-14 | 9:30 | 2019-04-14 | 17:30 | ODB | POWERGRID ER-I | BAY AMP
200 | 400KV TIE BAY OF SASARAM L-1 AND ICT-I AT DALTANAGNJ | 2019-04-18 | 9:30 | 2019-04-18 | 17:30 | ODB | POWERGRID ER-I | AMP
201 | 220kV BUS-1 AT DALTANAGNJ | 2019-04-25 | 9:30 | 2019-04-25 | 17:30 | ODB | POWERGRID ER-I | AMP | JSEB
202 | 220kV BUS-2 AT DALTANAGNJ | 2019-04-26 | 9:30 | 2019-04-26 | 17:30 | ODB | POWERGRID ER-I | AMP | JSEB
203 | 132KV BUS AT ARA | 2019-04-03 | 10:00 | 2019-04-03 | 16:00 | ODB | POWERGRID ER-I | AMP and Corona ring installation in bus isolator. ALL 132KV LINE WILL BE OUT | BSEB
204 | 132KV ARA-ARA-S/C | 2019-04-04 | 10:00 | 2019-04-04 | 16:00 | ODB | POWERGRID ER-I | Isolator current carrying assembly replacement | BSEB
205 | 400KV BIHARSHARIFF-BALIA-I | 2019-04-23 | 8:00 | 2019-04-24 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
206 | 400KV BIHARSHARIFF-BALIA-II | 2019-04-25 | 8:00 | 2019-04-26 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
207 | 400KV PATNA-BALIA-I | 2019-04-27 | 8:00 | 2019-04-27 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
208 | 400KV PATNA-BALIA-II | 2019-04-28 | 8:00 | 2019-04-28 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
210 | 400/220KV 500MVA ICT-II AT NEW PURNEA. | 2019-04-05 | 9:30 | 2019-04-05 | 18:00 | ODB | POWERGRID ER-I | For upgradation of transformer Isolator | BSEB
211 | 400/220KV 500MVA ICT-I AT NEW PURNEA. | 2019-04-08 | 9:30 | 2019-04-08 | 18:00 | ODB | POWERGRID ER-I | For upgradation of transformer Isolator | BSEB
212 | 220kV BUS-II AT NEW PURNEA. | 2019-04-18 | 9:30 | 2019-04-18 | 18:00 | ODB | POWERGRID ER-I | AMP WORK | BSEB
213 | 220kV BUS-I AT NEW PURNEA. | 2019-04-23 | 9:30 | 2019-04-23 | 18:00 | ODB | POWERGRID ER-I | AMP WORK | BSEB
214 | 132 KV MAIN BAY OF PURNEA(PG)- PURNEA (BSPTCL)-I AT PURNEA(PG) | 2019-04-02 | 9:30 | 2019-04-02 | 18:00 | ODB | POWERGRID ER-I | FOR NTAMC WORK | BSEB
215 | 133 KV MAIN BAY OF PURNEA(PG)- PURNEA (BSPTCL)-II AT PURNEA(PG) | 2019-04-03 | 9:30 | 2019-04-03 | 18:00 | ODB | POWERGRID ER-I | FOR NTAMC WORK | BSEB
216 | 134 KV MAIN BAY OF PURNEA(PG)- PURNEA (BSPTCL)-III AT PURNEA(PG) | 2019-04-04 | 9:30 | 2019-04-04 | 18:00 | ODB | POWERGRID ER-I | FOR NTAMC WORK | BSEB
217 | 132 KV MAIN BAY OF PURNEA(PG)- KISHANGANJ (BSPTCL)-I AT PURNEA(PG) | 2019-04-06 | 9:30 | 2019-04-06 | 18:00 | ODB | POWERGRID ER-I | FOR NTAMC WORK | BSEB
218 | 200MVA,400/132KV ICT-1 at Banka | 2019-04-25 | 10:00 | 2019-04-25 | 13:00 | ODB | POWERGRID ER-I | To install insulation tape on dome & connector of tertiary bushing of ICT-1. | BSEB
219 | 200MVA,400/132KV ICT-2 at Banka | 2019-04-26 | 10:00 | 2019-04-26 | 13:00 | ODB | POWERGRID ER-I | To install insulation tape on dome & connector of tertiary bushing of ICT-2. | BSEB
220 | 400KV MAIN BAY OF 80 MVAR B/R AT RANCHI | 2019-04-03 | 10:00 | 2019-03-03 | 17:00 | ODB | POWERGRID ER-I | AMP
221 | 400KV TIE BAY OF NEW RANCHI-IV AND FUTURE AT RANCHI | 2019-04-04 | 10:00 | 2019-04-04 | 17:00 | ODB | POWERGRID ER-I | AMP
222 | 400KV MAIN BAY OF 400KV NEW RANCHI-IV AT RANCHI | 2019-04-05 | 10:00 | 2019-04-05 | 17:00 | ODB | POWERGRID ER-I | AMP
223 | 400 KV MAIN BUS-1 AT RANCHI | 2019-04-09 | 10:00 | 2019-04-09 | 17:00 | ODB | POWERGRID ER-I | Errection & Commisssioning of Jack bus for Tie Bay of Ranchi-New Ranchi-I & II) & fixing of CVT Stool | JSEB
224 | 400 KV MAIN BUS-2 AT RANCHI | 2019-04-11 | 10:00 | 2019-04-11 | 17:00 | ODB | POWERGRID ER-I | Fixing of stool on Bus CVT Yph .400 KV RNC-NRNC-I & CKT-II WILL BE OUT OF SERVICE DUE TO NON AVAILABILITY OF TIE BAY | JSEB
225 | 400 KV RANCHI-SIPAT-1 LINE AND 80 MVAR LINE REACTOR AT RANCHI | 2019-04-22 | 10:00 | 2019-04-22 | 17:00 | ODB | POWERGRID ER-I | AMP & Replacement of defective CAPTHOR in FSC AND To attend oil leakage in Line Reactor | NLDC
226 | 400KV RANCHI-ROURKELA-I | 2019-04-16 | 9:30 | 2019-04-16 | 17:00 | ODB | POWERGRID ER-I | for insulator replacement work damaged by miscreants
227 | 400KV RANCHI-ROURKELA-II | 2019-04-17 | 9:30 | 2019-04-17 | 17:00 | ODB | POWERGRID ER-I | for insulator replacement work damaged by miscreants
228 | 220KV SIDE BAY OF 400/220KV ICT-I AT CHAIBASA. | 2019-04-02 | 9:30 | 2019-04-02 | 17:30 | ODB | POWERGRID ER-I | AMP WORK .
229 | 400 KV Chaibasa- KHARAGRPUR-I | 2019-04-04 | 9:30 | 2019-03-05 | 17:30 | ODB | POWERGRID ER-I | Auto reclose checking/testing at Chaibasa end | WB
230 | 400 KV Chaibasa- KHARAGRPUR-II | 2019-04-05 | 9:30 | 2019-03-06 | 17:30 | ODB | POWERGRID ER-I | Auto reclose checking/testing at Chaibasa end | WB
231 | 400KV Tie Bay of 400KV KAHALGAON-2 & 80 MVAR B/R AT LAKHISARAI | 2019-04-01 | 10:00 | 2019-04-01 | 14:00 | ODB | POWERGRID ER-I | AMP WORK
232 | 400/132KV 200 MVA ICT-1 AT LAKHISARAI | 2019-04-04 | 9:00 | 2019-04-05 | 17:00 | OCB | POWERGRID ER-I | Checking of Air Cell & AMP works. 33 kV Tretiary bay will also remain out of service. | BSEB | AFTER 29/04/19(ELECTION DATE)
233 | 400/132KV 200 MVA ICT-2 AT LAKHISARAI | 2019-04-06 | 9:00 | 2019-04-07 | 17:00 | OCB | POWERGRID ER-I | Checking of Air Cell & AMP works. | BSEB | AFTER 29/04/19(ELECTION DATE)
234 | 400KV Main Bay of 80 MVAR Bus Reactor AT LAKHISARAI | 2019-04-08 | 10:00 | 2019-04-08 | 14:00 | ODB | POWERGRID ER-I | AMP WORK
235 | 400KV Main Bay of 400 Kv kahalgaon-1 AT LAKHISARAI | 2019-04-11 | 10:00 | 2019-04-11 | 14:00 | ODB | POWERGRID ER-I | AMP WORK
236 | 400KV Tie Bay of 400 kV KAHALGAON-1 & Future Bay AT LAKHISARAI | 2019-04-13 | 10:00 | 2019-04-13 | 14:00 | ODB | POWERGRID ER-I | AMP WORK
237 | 50 MVAR L/R (NON SWITCHABLE) OF KAHALGAON-I AT LAKHISARAI | 2019-04-18 | 9:00 | 2019-04-18 | 17:00 | ODB | POWERGRID ER-I | AMP WORK
238 | 400KV KAHALAGOAN-LAKHISARAI-I | 2019-04-18 | 9:00 | 2019-04-18 | 9:10 | ODB | POWERGRID ER-I | for taking 50 MVAR Line Reactor-II out of service for AMP works.
239 | 400KV KAHALAGOAN-LAKHISARAI-I | 2019-04-18 | 16:50 | 2019-04-18 | 17:00 | ODB | POWERGRID ER-I | for taking 50 MVAR Line Reactor-II in service after AMP works.
240 | 132 kV LAKHISARAI-LAKHISARAI-I | 2019-04-25 | 10:00 | 2019-04-25 | 14:00 | ODB | POWERGRID ER-I | AMP works of Bay Equipments. | BSEB
241 | 132 kV LAKHISARAI-LAKHISARAI-II | 2019-04-27 | 10:00 | 2019-04-27 | 14:00 | ODB | POWERGRID ER-I | AMP works of Bay Equipments. | BSEB
243 | 220KV SIDE MAIN BAY OF 400/220KV 315MVA ICT-1 AT MUZAFFARPUR | 2019-04-12 | 9:30 | 2019-04-12 | 17:30 | ODB | POWERGRID ER-I | AMP WORK | BSEB
244 | 220KV SIDE MAIN BAY OF 400/220KV 315MVA ICT-2 AT MUZAFFARPUR | 2019-04-13 | 9:30 | 2019-04-13 | 17:30 | ODB | POWERGRID ER-I | AMP WORK | BSEB
245 | 220KV SIDE MAIN BAY OF 400/220KV 500MVA ICT-3 AT MUZAFFARPUR | 2019-04-15 | 9:30 | 2019-04-15 | 17:30 | ODB | POWERGRID ER-I | AMP WORK | BSEB
246 | 400KV Biharsarif - Koderma CKT -I | 2019-04-23 | 9:00 | 2019-04-24 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | DVC
247 | 400KV Biharsarif - Koderma CKT -II | 2019-04-25 | 9:00 | 2019-04-26 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | DVC
248 | 400kV Koderma - Bokaro CKT -I | 2019-04-03 | 9:00 | 2019-04-03 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | DVC
249 | 400kV Koderma - Bokaro CKT -II | 2019-04-04 | 9:00 | 2019-04-04 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | DVC
250 | 400 /220 kV 500MVA ICT-III AT GAYA | 2019-04-18 | 9:00 | 2019-04-19 | 18:00 | ODB | POWERGRID ER-I | for commisssioning of CSD work | BSEB | AFTER 13/04/19(ELECTION DATE)
251 | 400 /220 kV 315MVA ICT-II AT GAYA | 2019-04-08 | 9:00 | 2019-04-10 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project. | BSEB | AFTER 13/04/19(ELECTION DATE)
252 | 400 KV 125 MVAR BR-I AT GAYA | 2019-04-01 | 9:00 | 2019-04-03 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project.
253 | 400 KV 125 MVAR BR-II AT GAYA | 2019-04-04 | 9:00 | 2019-04-06 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project.
254 | 400 KV BUS-I AT GAYA | 2019-04-01 | 9:00 | 2019-04-06 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project. | BSEB
255 | 400 KV BUS-I AT GAYA | 2019-04-08 | 9:00 | 2019-04-10 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project. | BSEB
256 | 400 KV BUS-II AT GAYA | 2019-04-11 | 9:00 | 2019-04-12 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project. | BSEB
257 | 400 KV GAYA-NABINAGAR -1 | 2019-04-14 | 9:00 | 2019-04-14 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project.
258 | 400 KV GAYA-NABINAGAR -2 | 2019-04-15 | 9:00 | 2019-04-15 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project.
259 | 400 kV Chandwa-Gaya-2 | 2019-04-09 | 9:00 | 2019-04-10 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant.
260 | 400 kV Maithon-Gaya-1 | 2019-04-02 | 9:00 | 2019-04-28 | 18:00 | OCB | POWERGRID ER-I | Destringing, erection & re-stringing of multi ckt. Tower Loc. 80 | NLDC
261 | 400 kV Maithon-Gaya-2 | 2019-04-02 | 9:00 | 2019-04-28 | 18:00 | OCB | POWERGRID ER-I | Destringing, erection & re-stringing of multi ckt. Tower Loc. 80 | NLDC
262 | 400 kV Koderma-Gaya-1 | 2019-04-02 | 9:00 | 2019-04-28 | 18:00 | OCB | POWERGRID ER-I | Destringing, erection & re-stringing of multi ckt. Tower Loc. 80 | NLDC
263 | 400 kV Koderma-Gaya-2 | 2019-04-02 | 9:00 | 2019-04-28 | 18:00 | OCB | POWERGRID ER-I | Destringing, erection & re-stringing of multi ckt. Tower Loc. 80 | NLDC
264 | 400 KV Biharsharif Banka Ckt - 1 | 2019-04-16 | 10:00 | 2019-04-16 | 18:00 | ODB | POWERGRID ER-I | LINE bay AMP Work
265 | 400KV Biharsharif Banka Ckt - 2 | 2019-04-17 | 10:00 | 2019-04-17 | 18:00 | ODB | POWERGRID ER-I | LINE bay AMP Work
266 | 400/220KV 315 MVA ICT - 3 AT BIHARSHARIFF | 2019-04-26 | 10:00 | 2019-04-26 | 18:00 | ODB | POWERGRID ER-I | AMP work | BSEB
267 | 400KV BIHARSHARIFF - SASARAM- I | 2019-04-01 | 8:00 | 2019-04-25 | 18:00 | OCB | POWERGRID ER-I | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | NLDC
268 | 400KV BIHARSHARIFF - SASARAM- II | 2019-04-01 | 8:00 | 2019-04-25 | 18:00 | OCB | POWERGRID ER-I | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | NLDC
269 | 400KV Barh- Motihari CKT-1 | 2019-04-01 | 8:00 | 2019-04-29 | 18:00 | OCB | Realingmnet works of 400KV Barh- Motihari Line due to Construction of Barh Bypass by NHAI | POWERGRID ER-I | NLDC | Shutdown requset shall be submitted along with work schedule & Skectch of line diversion work & after return of 400KV BSF-SASARAM D/C
270 | 400KV Barh- Motihari CKT-II | 2019-04-01 | 8:00 | 2019-04-29 | 18:00 | OCB | Realingmnet works of 400KV Barh- Motihari Line due to Construction of Barh Bypass by NHAI | POWERGRID ER-I | NLDC
271 | 400KV BARH- PATNA CKT - 3 & 4 | 2019-04-04 | 8:00 | 2019-04-06 | 18:00 | ODB | POWERGRID ER-I | Realingmnet works of 400KV Barh- Motihari Line due to Construction of Barh Bypass by NHAI | NLDC
272 | 400KV BARH - PATNA CKT 3 & 4 | 2019-04-27 | 8:00 | 2019-04-29 | 18:00 | ODB | POWERGRID ER-I | Realingmnet works of 400KV Barh- Motihari Line due to Construction of Barh Bypass by NHAI | NLDC
273 | 400KV Bus -I AT PATNA | 2019-04-01 | 9:30 | 2019-04-03 | 17:30 | ODB | POWERGRID ER-I | Stringing of Sky bus under SS03 package of Patna Nabinagar Ckt 1 | BSEB
274 | 400KV Bus 2 AT PATNA | 2019-04-04 | 9:30 | 2019-04-06 | 17:30 | ODB | POWERGRID ER-I | Stringing of Sky bus under SS03 package of Patna Nabinagar Ckt 1 | BSEB
275 | 416 bay Ballia -2 Main bay AT PATNA | 2019-04-07 | 9:30 | 2019-04-09 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
276 | 420 Tie bay of Barh 3 and ballia 3 AT PATNA | 2019-04-07 | 9:30 | 2019-04-07 | 17:30 | ODB | POWERGRID ER-I | AMP
277 | 422 Main bay OF Ballia 4 AT PATNA | 2019-04-08 | 9:30 | 2019-04-08 | 17:30 | ODB | POWERGRID ER-I | AMP
278 | 423 bay Tie bay of Barh 4 and Ballia 4 AT PATNA | 2019-04-09 | 9:30 | 2019-04-09 | 17:30 | ODB | POWERGRID ER-I | AMP
279 | 424 Main bay OF Barh 4 AT PATNA | 2019-04-10 | 9:30 | 2019-04-10 | 17:30 | ODB | POWERGRID ER-I | AMP
280 | 205 bay Bus coupler AT PATNA | 2019-04-12 | 9:30 | 2019-04-14 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling | BSEB
281 | 207 bay 220KV SIDE MAIN BAY of 500 MVA ICT 3 AT PATNA | 2019-04-01 | 9:30 | 2019-04-01 | 17:30 | ODB | POWERGRID ER-I | AMP
282 | 208 bay main bay OF sipara 1 AT PATNA | 2019-04-02 | 9:30 | 2019-04-03 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
283 | 210 bay main bay OF sipara 2 AT PATNA | 2019-04-04 | 9:30 | 2019-04-06 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
284 | 220 KV Ara khagaul line 1 | 2019-04-07 | 9:30 | 2019-04-07 | 17:30 | ODB | POWERGRID ER-I | AMP WORK | BSEB
285 | 220 KV Ara Khagaul line 2 | 2019-04-08 | 9:30 | 2019-04-08 | 17:30 | ODB | POWERGRID ER-I | AMP WORK | BSEB
286 | 125 MVAR Bus reactor 1 AT PATNA | 2019-04-12 | 9:30 | 2019-04-12 | 17:30 | ODB | POWERGRID ER-I | AMP
287 | 500 MVA ICT 3 AT PATNA | 2019-04-18 | 9:30 | 2019-04-18 | 17:30 | ODB | POWERGRID ER-I | AMP | BSEB
288 | 220 Kv Patna Sipara 3 | 2019-04-19 | 9:30 | 2019-04-19 | 17:30 | ODB | POWERGRID ER-I | AMP AT PATNA END | BSEB
292 | 204 bay Main BAY OF Sipra 3 AT PATNA | 2019-04-20 | 9:30 | 2019-04-20 | 17:30 | ODB | POWERGRID ER-I | AMP
293 | 213 main bay 220KV Fatuha line AT PATNA | 2019-04-21 | 9:30 | 2019-04-23 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
294 | 400KV Bus -I AT PATNA | 2019-04-22 | 9:30 | 2019-04-23 | 17:30 | ODB | POWERGRID ER-I | Jumper connection of Bus isolaor and Bus stability | BSEB
295 | 400KV Bus 2 AT PATNA | 2019-04-24 | 9:30 | 2019-04-25 | 17:30 | ODB | POWERGRID ER-I | Jumper connection of Bus isolaor and Bus stability | BSEB
296 | 214 Main bay ICT 1 AT PATNA | 2019-04-26 | 9:30 | 2019-04-27 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
297 | 400 KV Patna Barh line 1 | 2019-04-01 | 9:30 | 2019-04-15 | 17:30 | OCB | POWERGRID ER-I | Under SS03 package for commissioning of 80 MVAR Bus reactor as switchable line reactor
298 | 409 Main bay ICT 2 AT PATNA | 2019-05-24 | 9:30 | 2019-04-25 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
299 | 417 Tie bay Ballia 2 & Barh 2 AT PATNA | 2019-04-16 | 9:30 | 2019-04-18 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
300 | 418 Main bay Barh 1 AT PATNA | 2019-04-30 | 9:30 | 31/04/19 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
301 | 412 Main bay Of ICT 1 AT PATNA | 2019-04-16 | 9:30 | 2019-04-28 | 17:30 | OCB | POWERGRID ER-I | Equipment uprating under SS03 package for Patna Nabinagar Bay
302 | 220Kv Bus 1 AT PATNA | 2019-04-14 | 9:30 | 2019-04-15 | 17:30 | ODB | POWERGRID ER-I | AMP | BSEB
303 | 220KV Bus 2 AT PATNA | 2019-04-16 | 9:30 | 2019-04-17 | 17:30 | ODB | POWERGRID ER-I | AMP | BSEB
304 | 413 Main Bay Ballia 1 AT PATNA | 2019-04-22 | 9:30 | 2019-04-25 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
305 | 414 bay Tie of Ballia 1 & Barh 2 AT PATNA | 2019-04-26 | 9:30 | 2019-04-27 | 17:30 | OCB | POWERGRID ER-I | AMP & CB Overhauling
306 | 400KV PATNA-BALIA-I | 2019-04-10 | 8:00 | 2019-04-10 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer | NLDC
307 | 400KV PATNA-BALIA-II | 2019-04-11 | 8:00 | 2019-04-11 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer | NLDC
310 | 400KV PATNA-BARH-I | 2019-04-15 | 8:00 | 2019-04-15 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer
311 | 400KV PATNA-BARH-II | 2019-04-16 | 8:00 | 2019-04-16 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer
312 | 400 kV BARH-KAHALGAON-I | 2019-04-17 | 8:00 | 2019-04-17 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer
313 | 400 kV BARH-KAHALGAON-II | 2019-04-18 | 8:00 | 2019-04-18 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer
316 | 400 KV D/C Nabinagar-Sasaram-I & II | 2019-04-20 | 8:00 | 2019-04-30 | 18:00 | OCB | POWERGRID ER-I | for replacement of bend leg at loc no.170(DD+0).
317 | 220kV Main Bus-I at Pusauli | 2019-04-11 | 9:00 | 2019-04-11 | 18:00 | ODB | POWERGRID ER-I | To attend Isolator Misalignment Problem & Reley retrofitting Job | BSEB
318 | 220kV Pusauli-Sahapuri | 2019-04-12 | 9:00 | 2019-04-12 | 13:00 | ODB | POWERGRID ER-I | To attend Isolator Misalignment Problem & Reley retrofitting Job | NLDC
319 | 220kV Pusauli-Ara | 2019-04-05 | 8:00 | 2019-04-05 | 18:00 | ODB | POWERGRID ER-I | To attend Isolator Misalignment Problem & Reley retrofitting Job | BSEB
320 | 220kV Main Bus-II at Pusauli | 2019-04-13 | 8:00 | 2019-04-13 | 20:00 | ODB | POWERGRID ER-I | To attend Isolator Misalignment Problem & Reley retrofitting Job | BSEB
322 | 220kV Pusauli-Dehri | 2019-04-15 | 13:00 | 2019-04-15 | 18:00 | ODB | POWERGRID ER-I | To attend Isolator Misalignment Problem & Reley retrofitting Job | BSEB
323 | 400kV East Side Bus-I at Pusauli | 2019-04-18 | 8:00 | 2019-04-18 | 18:00 | ODB | POWERGRID ER-I | To attend Isolator Misalignment Problem & Reley retrofitting Job | NLDC
324 | 400kV East Side Bus-II at Pusauli | 2019-04-19 | 8:00 | 2019-04-19 | 18:00 | ODB | POWERGRID ER-I | To attend Isolator Misalignment Problem & Reley retrofitting Job | NLDC
325 | 400kV North Side Bus-I at Pusauli | 2019-04-21 | 8:00 | 2019-04-21 | 18:00 | ODB | POWERGRID ER-I | To attend Isolator Misalignment Problem & Reley retrofitting Job | NLDC
326 | 220kV Bus Coupler at Pusauli | 2019-04-22 | 8:00 | 2019-04-22 | 18:00 | ODB | POWERGRID ER-I | AMP work | NLDC
327 | 400kV North Side Bus-II at Pusauli | 2019-04-25 | 8:00 | 2019-04-25 | 18:00 | ODB | POWERGRID ER-I | To attend Isolator Misalignment Problem & Reley retrofitting Job | NLDC
328 | 132kV Pusauli-Dehri | 2019-04-16 | 9:00 | 2019-04-16 | 18:00 | ODB | POWERGRID ER-I | To attend Isolator Problem and Relay retrofitting Job | BSEB
329 | 132kV Pusauli-Karmanasha | 2019-04-17 | 9:00 | 2019-04-17 | 18:00 | ODB | POWERGRID ER-I | To attend Isolator Problem and Relay retrofitting Job | NLDC
330 | 400kV Varanasi Main Bay (East Side) at Pusauli | 2019-04-26 | 9:00 | 2019-04-26 | 18:00 | ODB | POWERGRID ER-I | AMP work
331 | 765KV,125MVAR Bus Reactor Main Bay at Pusauli | 2019-04-27 | 9:00 | 2019-04-27 | 18:00 | ODB | POWERGRID ER-I | AMP work | NLDC
334 | 400KV D/C Farakka - Gokarna Ckt-I & II | 2019-04-04 | 8:00 | 2019-04-05 | 18:00 | OCB | POWERGRID ER-I | for termination with Farakka & Gokarna line of 400KV D/C Rajarhat-Purnea Line (Bihar Section) | WB
335 | 400KV Kahalgaon - Maithan - I | 2019-04-08 | 9:00 | 2019-04-14 | 17:00 | ODB | POWERGRID ER-I | for Replacement of PID detected defect insulator with Polymer Insulator
336 | 400KV Kahalgaon - Maithan - II | 2019-04-15 | 9:00 | 2019-04-21 | 17:00 | ODB | POWERGRID ER-I | for Replacement of PID detected defect insulator with Polymer Insulator
337 | 400 KV BIHARSARIF - BANKA - II | 2019-03-01 | 8:00 | 2019-03-31 | 18:00 | ODB | POWERGRID ER-I | A/R FOR OPGW INSTALLATION WORK
338 | 400 KV BIHARSARIF - KODERMA - II | 2019-03-01 | 8:00 | 2019-03-31 | 18:00 | ODB | POWERGRID ER-I | A/R FOR OPGW INSTALLATION WORK | DVC
341 | 220 kV Sasaram - Sahupuri | 2019-04-02 | 9:00 | 2019-04-05 | 18:00 | OCB | POWERGRID ER-I | TO FACILITATE THE SHUT DOWN OF ICT - I AT PUSAULI SS | NLDC
342 | Maintenance work for BUS Reactor | 2019-04-08 | 9:30 | 2019-04-19 | 18:00 | OCB | BARH | Annual Maintenance & Testing of BUS Reactor
343 | Maintenance work for BUS Reactor Bay | 2019-04-08 | 9:30 | 2019-04-19 | 18:00 | OCB | BARH | Annual Maintenance & Testing of Bays Equipments
344 | Barh Kahalgaon LINE # 1 | 2019-04-23 | 9:30 | 2019-04-24 | 18:00 | OCB | BARH | For Leveling of Land & Annual Maintenance & Testing of Bays Equipments
345 | New 400KV Bus#2 & 400 KV Bus#4 | 2019-04-03 | 8:00 | 2019-04-03 | 18:30 | ODB | KAHALGAON | For 400 KV Bus Sectionalizer Bay#2 commissioning
346 | 400KV Kh-Barh#1 | 2019-04-10 | 9:30 | 2019-04-10 | 17:30 | ODB | KAHALGAON | PM works and Relay Testing
347 | 400KV Kh-Barh#2 | 2019-04-17 | 9:30 | 2019-04-17 | 17:30 | ODB | KAHALGAON | PM works and Relay Testing
348 | 400KV Bus Reactor-1 | 2019-04-18 | 9:00 | 2019-04-19 | 17:00 | ODB | FARAKKA | Reactor & CB test
349 | 400KV FKK-Kahalgaon Line#4 | 2019-04-22 | 9:00 | 2019-04-23 | 17:00 | ODB | FARAKKA | CB and Relay test
350 | 400KV FKK-Kahalgaon Line#3 | 2019-04-25 | 9:00 | 2019-04-26 | 17:00 | ODB | FARAKKA | CB and Relay test
351 | 400KV FKK-Kahalgaon Line#1 | 2019-04-29 | 9:00 | 2019-04-30 | 17:00 | ODB | FARAKKA | CB,CT and Relay test
354 | 400kV D/C lB OPGC Jharsuguda - 1 | 2019-04-23 | 9:00 | 2019-04-23 | 18:00 | ODB | OGPTL | AMP Work
355 | 4OOkV D/C lB OPGC-Jharsuguda- 2 | 2019-04-24 | 9:00 | 2019-04-24 | 18:00 | ODB | OGPTL | AMP Work
356 | 400KV Bus Reactor-1 | 2019-04-18 | 9:00 | 2019-04-19 | 17:00 | ODB | FARAKKA | Reactor Test & CB Test
357 | 400KV FKK-Kahalgaon Line-4 | 2019-04-22 | 9:00 | 2019-04-23 | 17:00 | ODB | FARAKKA | CB & Relay Test
358 | 400KV FKK-Kahalgaon Line-3 | 2019-04-25 | 9:00 | 2019-04-26 | 17:00 | ODB | FARAKKA | CB & Relay Test
359 | 400KV FKK-Kahalgaon Line-1 | 2019-04-29 | 9:00 | 2019-04-30 | 17:00 | ODB | FARAKKA | CB & CT & Relay Test
360 | Maithon-Mejia #1 Line | 2019-04-22 | 9:00 | 2019-04-23 | 17:00 | ODB | DVC | Replacement of broken insulators damaged by miscreants
361 | Maithon-Mejia #2 Line | 2019-04-24 | 9:00 | 2019-04-25 | 17:00 | ODB | DVC | Replacement of Main Bay and Line Bay CT
362 | 400KV KTPS-GAYA Line#1 | 2019-04-08 | 9:00 | 2019-04-08 | 17:00 | ODB | DVC | for preventive maintenance job
363 | 400KV KTPS-GAYA Line#2 | 2019-04-10 | 9:00 | 2019-04-10 | 17:00 | ODB | DVC | for preventive maintenance job
364 | ICT-I (3x 105 MVA) at Jeypore | 2019-04-04 | 8:00 | 2019-04-04 | 20:00 | ODB | ER-II/Odisha /Jeypore | For changing ICT-I combination form Unit-I,III, IV to Unit-I , II & IV for charging Unit-II & To carry Insulation sleeves work Teritiry side of ICT 1 , For Isolator Retrofitting works (220KV ICT I TBC Isolator) ,Testing of Back Up Impedance relay and testing of 33KV auxilliary Bay & Transformer by contractor as per contractual agreement for starting of 5 years warranty period.. | GRIDCO
365 | ICT-I (3x 105 MVA) at Jeypore | 2019-04-05 | 10:00 | 2019-04-05 | 13:00 | ODB | ER-II/Odisha /Jeypore | For Change over of ICT-I, from TBC CB to ICT-I Bay(201 CB) after Isolator Retrofitting works of 30 Years old 201 89C ( ICT-I Isolator) | GRIDCO
366 | (+/- )450MVAr STATCOM at Jeypore | 2019-04-06 | 8:00 | 2019-04-08 | 18:00 | OCB | ER-II/Odisha /Jeypore | To carry out AMP of +/- 450MVAr STATCOM by contractor as per contractual agreement for starting of 5 years warranty period.
367 | 400 kV Jeypore-Indravati S/C Line | 2019-04-10 | 8:00 | 2019-04-11 | 18:00 | ODB | ER-II/Odisha /Jeypore | For testing New A/R relayof Jeypore - Indravati Line & For PID defect insulator replacement work | NLDC
368 | 412 Main Bay (JEYPORE-GAZ I MAIN BAY) | 2019-04-22 | 9:00 | 2019-04-27 | 18:00 | OCB | ER-II/Odisha /Jeypore | Overhauling of R, Y, B of 41252 (CB)(JEYPORE-GAZ I MAIN BAY) | GRIDCO
369 | 315MVA ICT # II at Jeypore | 2019-04-30 | 9:00 | 2019-04-30 | 18:00 | ODB | ER-II/Odisha /Jeypore | AMP of ICT # II, 208 Bay CT and testing of Back up Impedance relay | GRIDCO
370 | 413 MAIN BAY (JEYPORE-GAZ II MAIN BAY) at Jeypore | 2019-05-01 | 9:00 | 2019-05-03 | 17:00 | OCB | ER-II/Odisha /Jeypore | Overhauling of 41352 (CB)(JEYPORE-GAZ II MAIN BAY) | GRIDCO
371 | 765/400kV, 3*500MVA ICT-1 at Angul | 2019-04-02 | 9:00 | 2019-04-02 | 18:00 | ODB | ER-II/Odisha/Angul SS | For retrofitting of Back up impedance relays of ICT. | GRIDCO
372 | 765/400kV, 3*500MVA ICT-2 at Angul | 2019-04-03 | 9:00 | 2019-04-03 | 18:00 | ODB | ER-II/Odisha/Angul SS | For retrofitting of Back up impedance relays of ICT.
373 | 765/400kV, 3*500MVA ICT-3 at Angul | 2019-04-04 | 9:00 | 2019-04-04 | 18:00 | ODB | ER-II/Odisha/Angul SS | For retrofitting of Back up impedance relays of ICT. | GRIDCO
374 | 765/400kV, 3*500MVA ICT-4 at Angul | 2019-04-05 | 9:00 | 2019-04-05 | 18:00 | ODB | ER-II/Odisha/Angul SS | For retrofitting of Back up impedance relays of ICT. | GRIDCO
375 | Main Bay (403) of 400kV Bolangir Line at Angul | 2019-04-08 | 9:00 | 2019-04-08 | 18:00 | ODB | ER-II/Odisha/Angul SS | AMP Work. | GRIDCO
376 | Main Bay (427) of 400kV GMR Line-1 at Angul | 2019-04-09 | 9:00 | 2019-04-09 | 18:00 | ODB | ER-II/Odisha/Angul SS | AMP Work.
377 | Main Bay (430) of 400kV GMR Line-2 at Angul | 2019-04-10 | 9:00 | 2019-04-10 | 18:00 | ODB | ER-II/Odisha/Angul SS | AMP Work. | NLDC
378 | Main Bay (712) of 765kV Bus reactor-1 at Angul | 2019-04-11 | 9:00 | 2019-04-11 | 18:00 | ODB | ER-II/Odisha/Angul SS | AMP Work. | NLDC
379 | 400kV Angul-Meramundali ckt-I | 2019-04-14 | 8:00 | 2019-04-14 | 17:00 | ODB | ER-II/Odisha/Angul SS | Taking into service the LILO bypass arrangement at Angul | NLDC
380 | 400kV Angul-Meramundali ckt-II | 2019-04-15 | 8:00 | 2019-04-15 | 17:00 | ODB | ER-II/Odisha/Angul SS | Taking into service the LILO bypass arrangement at Angul | NLDC
381 | 400kV Angul-Talcher | 2019-04-15 | 8:00 | 2019-04-15 | 17:00 | ODB | ER-II/Odisha/Angul SS | Taking into service the LILO bypass arrangement at Angul
382 | Main Bay (726) of 765kV Srikakulam Line-2 at Angul | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | ER-II/Odisha/Angul SS | AMP Work.
383 | 765KV, 3*80 MVAR SRIKAKULAM LINE REACTOR-2 AT ANGUL | 2019-04-13 | 10:00 | 2019-04-13 | 18:00 | ODB | ER-II/Odisha/Angul SS | AMP Work.
384 | 765KV,3*110 MVAR BUS REACTOR-2 AT ANGUL | 2019-04-16 | 10:00 | 2019-04-16 | 18:00 | ODB | ER-II/Odisha/Angul SS | AMP Work.
385 | 765KV SUNDARGARH LINE-1 REACTOR BAY (709R) | 2019-04-09 | 10:00 | 2019-04-09 | 18:00 | ODB | ER-II/Odisha/Angul SS | AMP Work. | GRIDCO
386 | 765KV SUNDARGARH LINE-2 REACTOR BAY (706R) | 2019-04-11 | 10:00 | 2019-04-11 | 18:00 | ODB | ER-II/Odisha/Angul SS | AMP Work. | GRIDCO
387 | ICT-II at Indravati | 2019-04-09 | 8:00 | 2019-04-09 | 17:00 | ODB | ER-II/Odisha /Indravati | For retrofitting of Backup Impedance relay in ICT-II at OHPC S/Y.
388 | 125 MVAR BR at Indravati | 2019-04-11 | 8:00 | 2019-04-11 | 12:00 | ODB | ER-II/Odisha /Indravati | To Replace Terminal Box of PRD.
389 | 400 KV Indravati-Jeypore Main Bay (401) | 2019-04-16 | 8:00 | 2019-04-16 | 17:00 | ODB | ER-II/Odisha /Indravati | AMP work of 400 KV Indravati-Jeypore Main Bay (401) | NLDC
390 | 400kV Bus bar-1 at indravati | 2019-04-26 | 8:00 | 2019-04-26 | 17:00 | ODB | ER-II/Odisha /Indravati | AMP works -Bus-1 | NLDC
391 | 400kV Bus bar-2 at Indravati | 2019-04-27 | 8:00 | 2019-04-27 | 17:00 | ODB | ER-II/Odisha /Indravati | AMP works -Bus-2 | NLDC
392 | 400 KV Indravati-Rengali line | 2019-04-05 | 9:00 | 2019-04-05 | 17:00 | ODB | ER-II/Odisha/Indravati | Oil leakage from the reactor.For removal of 50MVAR LR of Rengali-Indravati Line from service, Opening of Jumpers for replacement of Gaskets of bushings.Line conductor is just above the reactor.Due to crane movement during maintenance of the reactor line shutdown is required . | NLDC | All shutdwons pertains to SR TTC curtailment may be reshceduled after 15th Apr 19.(SR DEMAND REDUCTION)
393 | 400 KV Indravati-Rengali line | 2019-04-06 | 9:00 | 2019-04-06 | 17:00 | ODB | ER-II/Odisha/Indravati | Removal of bushings and Replacement of Gaskets. And placing of bushings after replacement of gaskets. Line conductor is just above the reactor.Due to crane movement during maintenance of the reactor line shutdown is required . | GRIDCO
394 | 50MVAR L/R of 400KV Indravati-Rengali Line at indravati | 2019-04-05 | 9:00 | 2019-04-09 | 14:00 | OCB | ER-II/Odisha/Indravati | Replacement of Gaskets in Bushings, PRD, Inspection point, Radiator Banks, Valves, Oil Circulation work. During this period, 50MVAR LR will be out of service but the 400KV Indravati-Rengali line will remain in charged condition and there will be no power interruption.
395 | 400 KV Indravati-Rengali line | 2019-04-09 | 9:00 | 2019-04-09 | 14:00 | ODB | ER-II/Odisha/Indravati | Connection of Jumpers in Rengali Line before charging and taking the LR into service.
396 | 400 KV, FSC Bay (Bay No-412FSC) at Rengali | 2019-04-03 | 9:00 | 2019-04-03 | 17:00 | ODB | ER-II/Odisha/Rengali | AMP Work | GRIDCO
397 | 400 KV, 315 MVA ICT # 2 at Rengali | 2019-04-05 | 9:00 | 2019-04-09 | 17:00 | ODB | ER-II/Odisha/Rengali | For bushing replacement of 200 KV Side R-Ph. | GRIDCO
398 | 400 KV Rourkela-Talcher Line # 1 Auto reclose in Non-Auto Mode | 2019-04-01 | 8:00 | 2019-04-10 | 17:00 | ODB | ER-II/Odisha/Rengali | For PID Work | NLDC
399 | 400 KV Rourkela-Talcher Line # 2 in Non-Auto Mode | 2019-04-11 | 8:00 | 2019-04-30 | 17:00 | ODB | ER-II/Odisha/Rengali | For PID Work | NLDC
400 | 400 KV Rengali-Talcher Line # 2 | 2019-04-11 | 10:00 | 2019-04-11 | 18:00 | ODB | ER-II/Odisha/Rengali | For Rectification of shutdown nature Defects
401 | 400 KV Rourkela-Talcher Line # 1 | 2019-04-12 | 9:00 | 2019-04-13 | 17:00 | ODB | ER-II/Odisha/Rengali | Insulator Replacement Work | NLDC
402 | 400 KV Rourkela-Talcher Line # 2 | 2019-04-14 | 9:00 | 2019-04-15 | 17:00 | ODB | ER-II/Odisha/Rengali | Insulator Replacement Work
403 | 400 KV Indravati - Bus Reactor # 1 Tie Bay (Bay No-411) | 2019-04-23 | 9:00 | 2019-04-23 | 17:00 | ODB | ER-II/Odisha/Rengali | For Retrofitting of AR Relay
404 | Tie Bay of 400 KV Rengali-Keonjhar & Rengali-Talcher Line (Bay No-402) | 2019-04-26 | 9:00 | 2019-04-26 | 17:00 | ODB | ER-II/Odisha/Rengali | For Retrofitting of AR Relay | GRIDCO
405 | 220 KV TBC Bay at Rengali | 2019-04-28 | 9:00 | 2019-04-28 | 17:00 | ODB | ER-II/Odisha/Rengali | MOM Box Retrofitting | GRIDCO
406 | 220 KV BC Bay at Rengali | 2019-04-30 | 9:00 | 2019-04-30 | 17:00 | ODB | ER-II/Odisha/Rengali | MOM Box Retrofitting
407 | 400kV Sundargarh-Raigarh Ckt#1 | 2019-04-02 | 8:00 | 2019-04-14 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | For PID Testing of Porcelain Insulator. Only Auto reclose relay will be off. Line will be in service
408 | 400kV Sundargarh-Raigarh Ckt#3 | 2019-04-15 | 8:00 | 2019-04-30 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | For PID Testing of Porcelain Insulator. Only Auto reclose relay will be off. Line will be in service
409 | 400kV Sundargarh-Rourkela Ckt #3 & 4 | 2019-04-04 | 8:00 | 2019-04-04 | 18:00 | OCB | ER-II /ODISHA/SUNDERGARH | TL Maintenance works (Shut down of Sundargarh -Rourkela Ckt-III & IV is required together for maint. of Multi circuit/ LILO portion)
410 | 400kV Sundargarh-Raigarh Ckt #3 & 4 | 2019-04-06 | 8:00 | 2019-04-06 | 18:00 | OCB | ER-II /ODISHA/SUNDERGARH | TL Maintenance works (Shut down of Sundargarh -Raigarh Ckt-III & IV is required together for maint. of Multi circuit/ LILO portion)
411 | 765 KV DC Sundargarh - Dharamjaygarh Ckt-I | 2019-04-09 | 8:00 | 2019-04-09 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | TL Maintenance works
412 | 765 KV DC Sundargarh - Dharamjaygarh Ckt-II | 2019-04-10 | 8:00 | 2019-04-10 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | TL Maintenance works
413 | 765 KV DC Sundargarh - Dharamjaygarh Ckt-III | 2019-04-12 | 8:00 | 2019-04-12 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | TL Maintenance works
414 | 765 KV DC Sundargarh - Dharamjaygarh Ckt-IV | 2019-04-13 | 8:00 | 2019-04-13 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | TL Maintenance works
415 | 400kV Sundargarh-Rourkela Ckt #1 | 2019-04-19 | 8:00 | 2019-04-19 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | TL Maintenance works
416 | 400kV Sundargarh-Rourkela Ckt #2 | 2019-04-20 | 8:00 | 2019-04-20 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | TL Maintenance works | NLDC
417 | 765KV 240 MVAR Bus Reactor-1 at Sundergarh | 2019-04-02 | 10:00 | 2019-04-02 | 12:00 | ODB | ER-II/Odisha/Sundergarh | Taking R-Ph Reactor in to service in place of Spare Reactor after attending oil leakage of R-Ph reactor | NLDC
418 | 765KV Sundargarh-Angul Ckt #4 with LR | 2019-04-03 | 10:00 | 2019-04-03 | 12:00 | ODB | ER-II/Odisha/Sundergarh | To take spare Reactor in to service in place of B-Ph Reactor for attending oil leakage in B-Ph reactor | NLDC
419 | 765/400KV 1500MVA ICT-2 at Sundergarh | 2019-04-04 | 9:00 | 2019-04-04 | 12:00 | ODB | ER-II/Odisha/Sundergarh | Taking spare ICT in service in place of B-Ph ICT for attending oil leakage of B-Ph ICT | NLDC
420 | 765KV Bus-I at Sundargarh | 2019-04-15 | 9:00 | 2019-04-23 | 18:00 | OCB | ER-II/Odisha/Sundergarh | Erection of SF6 to Air bushing of 765KV GIS bus sectionalizer, jumpering , HV & impulse testing for commissioning of 765KV GIS and Stringing of jack bus of 765KV Raipur Ckt-1&2 i.e. Bay 709 & 712 for commissioning of the lines under construction head. | NLDC
421 | Main Bay-707 of 765KV Angul Ckt-4 | 2019-04-06 | 8:00 | 2019-04-06 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
422 | 765KV Bus-II at Sundargarh | 2019-04-05 | 9:00 | 2019-04-13 | 18:00 | OCB | ER-II/Odisha/Sundergarh | Erection of SF6 to Air bushing of 765KV GIS bus sectionalizer, jumpering , HV & impulse testing for commissioning of 765KV GIS under construction head. | NLDC
423 | Tie Bay-708 of 765KV Angul Ckt-4 & Future | 2019-04-09 | 8:00 | 2019-04-09 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
424 | Main Bay-710 of 765KV Angul Ckt-3 | 2019-04-10 | 8:00 | 2019-04-10 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
425 | Tie Bay-711 of 765KV Angul ckt-3 & future | 2019-04-11 | 8:00 | 2019-04-11 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
426 | Main Bay-713 of 765KV Angul Ckt-2 | 2019-04-12 | 8:00 | 2019-04-12 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
427 | Tie Bay-714 of 765KV Angul ckt-2 & Dharamjaygarh Ckt-3 | 2019-04-13 | 8:00 | 2019-04-13 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work
428 | Main Bay-715 of 765KV Dharamjaygarh Ckt-3 | 2019-04-15 | 8:00 | 2019-04-15 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work
429 | Main Bay-716 of 765KV Angul Ckt-1 | 2019-04-16 | 8:00 | 2019-04-16 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work
430 | Tie Bay-717 of 765KV Dharamjaygarh Ckt-4 & Angul-1 at Sundargarh | 2019-04-17 | 8:00 | 2019-04-17 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
431 | Main Bay-718 of 765KV Dharamjaygarh Ckt-4 at Sundargarh | 2019-04-18 | 8:00 | 2019-04-18 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
432 | Main Bay-719 of 765KV Darlipali Ckt-2 | 2019-04-19 | 8:00 | 2019-04-19 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
433 | Tie Bay-720 of 765KV Darlipali-2 7 Dharamjaygarh-1 | 2019-04-20 | 8:00 | 2019-04-20 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
434 | Main Bay-721 of 765KV Dharamjaygarh Ckt-1 at Sundargarh | 2019-04-22 | 8:00 | 2019-04-22 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
435 | Main Bay-722 of 765KV Darlipali Ckt-1 | 2019-04-23 | 8:00 | 2019-04-23 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
436 | Tie Bay-723 of 765KV Darlipali Ckt-1 & Dharamjaygarh Ckt-2 at Sundargarh | 2019-04-24 | 8:00 | 2019-04-24 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
437 | Main Bay-724 of 765KV Dharamjaygarh Ckt-2 | 2019-04-25 | 8:00 | 2019-04-25 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
438 | 765KV Bus-II(GISBus Split Section & Darlipali#1&2 dia) at Sundargarh | 2019-04-27 | 9:00 | 2019-04-28 | 18:00 | OCB | ER-II/Odisha/Sundergarh | for 765KV GIS and ICT-3&4 commissioning work under construction head. -Only Main bay of NTPC Darlilipali#1&2 will be off after 765 Bus Sectionalisor#1 is commissioned. | NLDC
439 | 765KV Bus-I (GIS Bus Split Section & Dharamjaygarh #1&2 dia)at Sundargarh | 2019-04-29 | 9:00 | 2019-04-30 | 18:00 | OCB | ER-II/Odisha/Sundergarh | for 765KV GIS and ICT-3&4 commissioning work under construction head. -Only Main bay of Dharmajaygarh #1&2 will be off after 765 Bus Sectionalisor#2 is commissioned. . | NLDC
440 | 765KV 240 MVAR Bus Reactor-2 at Sundergarh | 2019-04-03 | 8:00 | 2019-04-03 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
441 | 765/400KV 1500MVA ICT-1 Sundergarh | 2019-04-04 | 8:00 | 2019-04-04 | 18:00 | ODB | ER-II/Odisha/Sundergarh | AMP Work | NLDC
442 | 400 KV GIS BUS-I | 2019-04-26 | 9:00 | 2019-04-26 | 15:00 | ODB | ER-II/Odisha/Sundergarh | For modification of secondary box of Bus PTs of 400 KV GIS of Sundergarh substation | NLDC
443 | 401 KV GIS BUS-II | 2019-04-27 | 9:00 | 2019-04-27 | 15:00 | ODB | ER-II/Odisha/Sundergarh | For modification of secondary box of Bus PTs of 400 KV GIS of Sundergarh substation | NLDC
444 | 400KV BARIPADA - DUBURI LINE | 2019-04-05 | 8:00 | 2019-04-06 | 18:00 | ODB | ER-II/Odisha/Bhadrak TL | AMP Work | NLDC
445 | 315 MVA ICT#1 & 125 MAR B/R#1 TIE BAY (BAY NO.-423) | 2019-04-01 | 9:00 | 2019-04-13 | 18:00 | OCB | ER-II/ODISHA/ROURKELA | RETROFITTING OF OLD HYDRAULIC OPERATED BHEL MAKE CB BY NEW SPRING-SPRING OPERATED CGPISL MAKE CB | NLDC
446 | 400 KV ROURKELA-RANCHI#2 | 2019-04-04 | 10:00 | 2019-04-04 | 14:00 | ODB | ER-II/ODISHA/ROURKELA | CHECKING & TESTING OF A/R CIRCUIT OF BOTH MAIN & TIE CB | NLDC
447 | 400 KV ROURKELA-RANCHI#1 | 2019-04-05 | 10:00 | 2019-04-05 | 14:00 | ODB | ER-II/ODISHA/ROURKELA | CHECKING & TESTING OF A/R CIRCUIT OF BOTH MAIN & TIE CB | NLDC
448 | 315 MVA ICT#1 at Rourkela | 2019-04-09 | 9:00 | 2019-04-09 | 18:00 | ODB | ER-II/ODISHA/ROURKELA | RETROFITTING OF EXISTING OLD ICT PROTECTION RELAYS WITH NEW NUMERICAL RELAYS | NLDC
449 | 315 MVA ICT#2 at Rourkela | 2019-04-10 | 9:00 | 2019-04-10 | 18:00 | ODB | ER-II/ODISHA/ROURKELA | RETROFITTING OF EXISTING OLD ICT PROTECTION RELAYS WITH NEW NUMERICAL RELAYS | NLDC
450 | 400 KV ROURKELA-CHAIBASA#2 | 2019-04-11 | 9:00 | 2019-04-11 | 18:00 | ODB | ER-II/ODISHA/ROURKELA | RETROFITTING OF EXISTING OLD CONVENTIONAL B/U RELAY BY NUMERICAL RELAY IN ITS LINE REACTOR | NLDC
451 | 50 MVAR CHAIBASA#1 LINE REACTOR | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | ER-II/ODISHA/ROURKELA | RETROFITTING OF EXISTING OLD CONVENTIONAL B/U RELAY BY NUMERICAL RELAY | NLDC
452 | 315 MVA ICT#2 TIE BAY (BAY NO.-414) | 2019-04-15 | 9:00 | 2019-04-23 | 18:00 | OCB | ER-II/ODISHA/ROURKELA | RETROFITTING OF OLD HYDRAULIC OPERATED BHEL MAKE CB BY NEW SPRING-SPRING OPERATED CGPISL MAKE CB | NLDC
453 | 125 MVAR BUS REACTOR-I | 2019-04-22 | 9:00 | 2019-04-22 | 18:00 | ODB | ER-II/ODISHA/ROURKELA | COMMISSIONING OF CSD IN ITS TIE BAY CB (42352 CB) | NLDC
454 | 400 KV TALCHER#2 & 400 KV CHAIBASA#2 TIE BAY (BAY NO.-408) | 2019-04-23 | 9:00 | 31/04/19 | 18:00 | OCB | ER-II/ODISHA/ROURKELA | RETROFITTING OF OLD HYDRAULIC OPERATED BHEL MAKE CB BY NEW SPRING-SPRING OPERATED CGPISL MAKE CB | NLDC
455 | 125 MVAR BUS REACTOR at Balangir | 2019-03-28 | 09:00 Hrs | 2019-03-29 | 18:00 Hrs | OCB | ER-II/Odisha/Balangir | Replacement of defective Air Cell of conervator. | GRIDCO
456 | 400KV Balangir-Jeypore Line TIE BAY(40304BAY) | 2019-04-05 | 09:00 Hrs | 2019-04-05 | 18:00 Hrs | ODB | ER-II/Odisha/Balangir | AMP for 40304 52 CB and 40304 CT
457 | 400KV Balangir-Angul Line | 2019-04-14 | 08:00 Hrs | 2019-04-16 | 18:00 Hrs | ODB | ER-II/Odisha/Balangir | Replacement of defective insulator by Polymer long Rod Insulator
458 | 400KV Balangir-Jeypore Line | 2019-04-12 | 08:00 Hrs | 2019-04-13 | 18:00 Hrs | ODB | ER-II/Odisha/Balangir | Replacement of defective insulator by Polymer long Rod Insulator
459 | 400KV Balangir-Jeypore Line Main BAY(403BAY) | 2019-04-15 | 09:00 Hrs | 2019-04-17 | 18:00 Hrs | OCB | ER-II/Odisha/Balangir | For arresting SF6 Gas leakage in R-PH CB of 403 Bay CB. | GRIDCO
460 | 400KV Balangir-Angul Line TIE BAY(40102BAY) | 2019-04-18 | 09:00 Hrs | 2019-04-18 | 18:00 Hrs | ODB | ER-II/Odisha/Balangir | AMP for 40102 52 CB and 40102 CT | GRIDCO
461 | 220KV,Future Line-IV BAY (209 BAY) at Balangir | 2019-04-20 | 09:00 Hrs | 2019-04-20 | 18:00 Hrs | ODB | ER-II/Odisha/Balangir | AMP for 209 52 CB and 209 CT
462 | Future ICT main bay 400 kv (410) at Pandiabili | 2019-04-15 | 10:00 | 2019-04-15 | 17:00 | ODB | ER-II/Odisha/ Pandiabili GIS | Timing & CRM of Breaker
463 | 220 KVBus Coupler (206) at Pandiabili | 2019-04-19 | 10:00 | 2019-04-19 | 17:00 | ODB | ER-II/Odisha/ Pandiabili GIS | Timing & CRM of Breaker
464 | 63 MVAR Duburi Line Reactor bay(404R) | 2019-04-01 | 8:30 | 2019-04-01 | 17:00 | ODB | ER-II/Odisha/ Pandiabili GIS | AMP of Duburi L/R
465 | 63 MVAR Duburi Line Reactor bay(403R) | 2019-04-02 | 8:30 | 2019-04-02 | 17:00 | ODB | ER-II/Odisha/ Pandiabili GIS | AMP of Baripada L/R
466 | 400 KV 406 Main Bay of 315 MVA ICT-II at Baripada | 2019-04-03 | 9:00 | 2019-04-03 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | AMP works
467 | 220KV 203 Bus Coupler Bay at Baripada | 2019-04-04 | 9:00 | 2019-04-04 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | AMP works
468 | 400 kV 411 Tie Bay of Baripada-Pandiabili & Baripada-TISCO line | 2019-04-07 | 9:00 | 2019-03-08 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | AMP & Gasket replacement | NLDC
469 | 125 MVAR Bus Reactor-1 at Baripada | 2019-04-10 | 9:00 | 2019-04-10 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | AMP works | NLDC
470 | 41052- Main Bay of Pandiabilli line | 2019-04-11 | 9:00 | 2019-04-11 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | AMP works
471 | 40552- Tie Bay of Kharagpur line & 315MVA ICT II | 2019-04-12 | 9:00 | 2019-04-12 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | AMP works
472 | 20852- 315MVA ICT I Bay at Baripada | 2019-04-13 | 9:00 | 2019-04-13 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | Amp Works
473 | 20452- 315MVA ICT II Bay at Baripada | 2019-04-14 | 9:00 | 2019-04-14 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | Amp Works
474 | 400 kV 408 Tie Bay of Baripada-Duburi & Baripada-Jamshedpur line | 2019-04-15 | 9:00 | 2019-04-16 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | Gasket replacement
475 | 400/220 Kv 315MVA ICT II at Baripada | 2019-04-28 | 9:00 | 2019-04-28 | 17:30 | ODB | ER-II/Odisha/BARIPADA S/S | Oil Leakage Arresting
476 | 125 MVAR Bus Reactor at Keonjhar | 2019-04-08 | 9:00 | 2019-04-11 | 18:00 | OCB | ER-II/Odisha/KEONJHAR S/S | For replacement of defective rediator of Bus Reactor
477 | 205 ICT-II Bay at Keonjhar | 2019-04-16 | 9:00 | 2019-04-16 | 18:00 | ODB | ER-II/Odisha/KEONJHAR S/S | For CB timing & DCRM rectification job | GRIDCO
478 | 207 bus coupler at Keonjhar | 2019-04-17 | 9:00 | 2019-04-17 | 18:00 | ODB | ER-II/Odisha/KEONJHAR S/S | For CB timing & DCRM rectification job | GRIDCO
479 | 206 Bay at Keonjhar | 2019-04-18 | 9:00 | 2019-04-18 | 18:00 | ODB | ER-II/Odisha/KEONJHAR S/S | For CB timing & DCRM rectification job | GRIDCO
480 | 204 bay at Keonjhar | 2019-04-19 | 9:00 | 2019-04-19 | 18:00 | ODB | ER-II/Odisha/KEONJHAR S/S | For CB timing & DCRM rectification job | gRIDCO
481 | 315MVA ICT-I at Keonjhar | 2019-04-24 | 9:00 | 2019-04-24 | 18:00 | ODB | ER-II/Odisha/Keonjhar | Retro fitting of Back up Impedance relay
482 | 315MVA ICT-II at Keonjhar | 2019-04-26 | 9:00 | 2019-04-26 | 18:00 | ODB | ER-II/Odisha/Keonjhar | Retro fitting of Back up Impedance relay | GRIDCO
483 | 765KV Angul-Srikakulam ckt-I | 2019-03-26 | 7:00 | 2019-03-27 | 18:00 | ODB | ER-II/Odisha/Nyg&Bmp TLAM | AMP Work | GRIDCO | All shutdwons pertains to SR TTC may be reshceduled after 15th Apr 19.
484 | 765KV Angul-Srikakulam ckt-II | 2019-03-28 | 7:00 | 2019-03-29 | 18:00 | ODB | ER-II/Odisha/Nyg&Bmp TLAM | AMP Work
485 | 765KV Angul-Srikakulam ckt-I | 2019-04-01 | 7:00 | 2019-04-02 | 18:00 | ODB | ER-II/Odisha/Nyg&Bmp TLAM | AMP Work-Shutdown is required if not granted in March 2019 | GRIDCO
486 | 765KV Angul-Srikakulam ckt-II | 2019-04-03 | 7:00 | 2019-04-04 | 18:00 | ODB | ER-II/Odisha/Nyg&Bmp TLAM | AMP Work-Shutdown is required if not granted in March 2019 | GRIDCO
516 | 400KV Bus 1 in TSTPS | 2019-04-03 | 7:00 | 2019-04-03 | 18:00 | ODB | TALCHER | For attending bus isolator problem and replacement of twin moose conductor of bus side of 400KV TSTPS Meramunduli line Main bay
517 | (i)220KV BUS-2 in TSTPS alongwith (ii)220 KV TSTPS Meramunduli 2( Bay 3) line shut down | 2019-04-05 | 7:00 | 2019-04-06 | 18:00 | OCB | TALCHER | 220KV Bus CVT replacement due to aging. 220 KV TSTPS Meramunduli 2 ( Bay 3) line shut down is required due to high proximity of bay to Bus II which will restrict hydra movement during CVT replacement. | GRIDCO
518 | 400KV GMR-ANGUL | 2019-04-09 | 9:00 | 2019-04-11 | 11:00 | ODB | GMR | necessary maintenance
525 | At Arambag:ABG-BKTPP 400kv line | 2019-04-08 | 6:00 | 2019-04-08 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
526 | At Arambag:315 MVA ICT 1 in TBC bay,s/d of 400KV Main bus-1,Bus coupler | 2019-04-09 | 6:00 | 2019-04-09 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
527 | At Arambag:315 MVA ICT 1 in TBC bay,s/d of 400KV Main bus-2,Bus coupler | 2019-04-10 | 6:00 | 2019-04-10 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
528 | At Arambag:315 MVA ICT 2 in TBC bay,s/d of 400KV Main bus-1,Bus coupler | 2019-04-12 | 6:00 | 2019-04-12 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
529 | At Arambag:315 MVA ICT 2 in TBC bay,s/d of 400KV Main bus-2,Bus coupler | 2019-04-13 | 6:00 | 2019-04-13 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
530 | 400 KV ARAMBAG-KTPP line on TBC Bay.s/d of 400KV Main Bus 1 & Bus coupler | 2019-04-16 | 6:00 | 2019-04-16 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
531 | 400 KV ARAMBAG-KTPP line on TBC Bay.s/d of Main Bus 2 & Bus coupler | 2019-04-17 | 6:00 | 2019-04-17 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
532 | 400 kv Arambag-Durgapur line on TBC Bay s/d 400KV Main Bus 1 & Bus coupler | 2019-04-19 | 6:00 | 2019-04-19 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
533 | 400 kv Arambag-Durgapur line on TBC Bay s/d 400KV Main Bus 1 & Bus coupler | 2019-04-20 | 6:00 | 2019-04-20 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
534 | At Arambag:315 MVA ICT 3 in TBC bay,s/d of 400KV Main bus-1,Bus coupler | 2019-04-22 | 6:00 | 2019-04-22 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
535 | At Arambag:315 MVA ICT 3 in TBC bay,s/d of 400KV Main bus-2,Bus coupler | 2019-04-23 | 6:00 | 2019-04-23 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
536 | At Arambag:400KV Bus coupler Bay with 400kv Main Bus-1 | 2019-04-25 | 6:00 | 2019-04-25 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
537 | At Arambag:400KV Bus coupler Bay with 400kv Main Bus-2 | 2019-04-26 | 6:00 | 2019-04-26 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
538 | 400kv Arambag-KTPP Feeder | 2019-04-27 | 6:00 | 2019-04-27 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
539 | 400kv Arambag-KTPP Feeder | 2019-04-28 | 6:00 | 2019-04-28 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
540 | At BANKURA: 400kv NEW PPSP-Arambag #1 | 2019-04-08 | 6:00 | 2019-04-08 | 16:00 | ODB | WBSETCL | MAINTENANCE WORK
541 | At BANKURA:400kv NEW PPSP-Arambag #1 | 2019-04-09 | 6:00 | 2019-04-09 | 16:00 | ODB | WBSETCL | MAINTENANCE WORK
542 | At BANKURA: 400kv NEW PPSP-Arambag #2 | 2019-04-10 | 6:00 | 2019-04-10 | 16:00 | ODB | WBSETCL | MAINTENANCE WORK
543 | At BANKURA: 400kv NEW PPSP-Arambag #2 | 2019-04-11 | 6:00 | 2019-04-11 | 16:00 | ODB | WBSETCL | MAINTENANCE WORK
544 | At BKTPP: 400kv Bus Reactor Bay | 2019-04-02 | 6:00 | 2019-04-03 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
545 | At BKTPP:400/220/33kv 315MVA IBT #1 | 2019-04-05 | 6:00 | 2019-04-06 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
546 | At BKTPP: 400/220/33kv 315MVA IBT #2 | 2019-04-08 | 6:00 | 2019-04-09 | 15:00 | ODB | WBSETCL | MAINTENANCE WORK
547 | 400KV D/C BINAGURI-BONGAIGAON I & II | 2019-04-02 | 8:00 | 2019-04-03 | 18:00 | ODB | ATL | STRINGING ACTIVITY OF 400KV D/C QUAD ALIPURDUAR-SILLIGURI TRANSMISSION LINE
548 | 400KV D/C TALA-BINAGURI T/L-I (CKT3&4) | 2019-04-07 | 8:00 | 2019-04-08 | 18:00 | ODB | ATL | STRINGING ACTIVITY OF 400KV D/C QUAD ALIPURDUAR-SILLIGURI TRANSMISSION LINE
549 | 132 KV Purnea(PG)-Kishanganj S/C Transmission line | 2019-03-26 |  | 2019-04-03 |  | OCB | BSEB | For piling work of (including pile foundation,dismantling of existing conductors and towers,erection of new towers and re-stringing of conductor) at tower location nos-80,81 and 83 across Parman river near Baisi
550 | 132 KV Purnea(PG)-Kishanganj S/C Transmission line | 2019-04-20 |  | 2019-04-30 |  | OCB | BSEB | For piling work of (including pile foundation,dismantling of existing conductors and towers,erection of new towers and re-stringing of conductor) at tower location nos-80,81 and 83 across Parman river near Baisi
551 | 132kv Motihari(400/132 KV)(ISTS )-Bettiah D/C trans line | 2019-03-26 | 9:00 | 2019-03-27 | 17:00 | ODB | BSEB | For pre summer Maintenance work.
552 | a) 220 kV Muzaffarpur(PG)- Hajipur Ckt no.-01 | 2019-03-28 | 10:00 | 2019-03-30 | 17:00 | ODB | BSEB | For tree pruning.
553 | b) 220 kV Muzaffarpur(PG)- Hajipur Ckt no.-02 | 2019-03-28 | 10:00 | 2019-03-30 | 17:00 | ODB | BSEB | For tree pruning.
554 | 132kv Half main bus at GSS Ramnagar | 2019-04-02 | 11:00 | 2019-04-02 | 12:00 | ODB | BSEB | For jumper work of existing main bus for main bus extension work(railway bay)Railway bay is newly constructed for power supply to TSS Harinagar from GSS Ramnagar
555 | 132 KV Rajgir-Barhi S/C T/L | 2019-03-26 | 8:00 | 2019-04-27 | 15:00 | ODB | BSEB | For reconductoring work of 132KV D/C Bihar Sharif –Barhi T/L(between loc no 185 to 187)
556 | 220 KV Gaya(PG)-Sonenagar ckt-2 | 2019-03-26 | 11:00 | 2019-03-26 | 15:00 | ODB | BSEB | For pre summer Maintenance work.
557 | 220 KV Biharsharif-TTPS T/L | 2019-03-26 | 8:00 | 2019-03-31 | 18:00 | OCB | BSEB | For gantry erection and stringing at loc no. 501, for stringing of 132 kv ckt-2 of 132 KV Biharsharif-Nawada D/C T/L.
558 | (a 220 KV D/C Patna (PG)-Gaurichak tr line.(b) 220 KV Gaurichak-Fathua ckt-I(c) 220 KV Gaurichak-Khagaul ckt-II | 2019-03-27 | 9:30 | 2019-03-31 | 15:30 | ODB | BSEB | For one no of tower erection work in 220 KV D/C Patna (PG) –Khagaul transmission line (AP-40/0,MD+12) in Gaurichak GSS premises. (BGCL work)
559 | a) 220 kV Gaya(PG)- Dehri Ckt no.-01 b) 220 kV Gaya(PG)- Dehri Ckt no.-02 | 2019-04-02 | 12:00/13:30 | 2019-04-02 | 13:00/14:30 | ODB | BSEB | For jumper tightening work at different loctions.
560 | a)220 kv Bihar Sharif(PG)-Bihar Sharif ICT 1 bay b)220kv Bihar-Sharif(PG) Bihar Sharif ICT 2 bay | 03/04/19 / 04/04/19 | 10:00 | 03/04/01/ /04/04/19 | 13:00 | ODB | BSEB | For pre summer maintenance work
561 | a)220 KV Bihar Sharif(PG)-Bihar Sharif ICT 3 | 2019-03-26 | 9:00 | 2019-03-26 | 17:00 | ODB | BSEB | For jumper tightening & conductor replacement of Bihar Sharif-TTPS line at loc no504(As both T/L share same Tower & Ganterv)
562 | 400kV, 125MVAR Bus Reactor-1 | 2019-03-27 | 10:00 | 2019-03-27 | 18:00 | ODB | Powergrid, ER-II | For HV testing of Farakka Line Reactor (under construction stage). Due to Air Bushing clearance issue (during testing ) with 125MVAR Bus Reactor -1
563 | Maithon-Mejia 1 | 2019-04-02 | 10:00 | 2019-04-03 | 17:00 | ODB | Powergrid, ER-II | Porcelain Insulators needs to be replaced | Circuit 1 : Loc. No. 12 ,69,84 , 101 , 157
564 | Maithon-Mejia 2 | 2019-04-04 | 10:00 | 2019-04-05 | 17:00 | ODB | Powergrid, ER-II | Porcelain Insulators needs to be replaced | Circuit 2 : Loc.No. 12 ,87 , 124,125 , 142 , 170
565 | 400KV BONGAINGOAN - ALIPURDUAR -1 & 2 | 2019-03-31 | 8:00 | 2019-04-02 | 16:00 | ODB | Powergrid, ER-II | for construction 400kV D/C (Quad) Jigmeling-Alipurduar T/L , crossing the 400kV D/C (Quad) Bongaigaon-Siliguri T/L of ENICL at loc. no. 112/0 - 113/0 at village Bhomrabill near Srirampur for carry out the stringing works at the crossing under police protection due to ROW issues.
566 | 220 KV Alipurduar - Salakati D/C(One Ckt at a time On Alternate Day Basis) | 2019-04-08 | 8:00 | 2019-04-28 | 18:00 | ODB | Powergrid, ER-II | for installation of Transmission Line Lightning Arrestor
567 | 400 KV S/C Durgapur - Jamshedpur TL- ( TL-329-330) | 2019-03-29 | 8:00 | 2019-03-30 | 17:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 102/0 (DD+25+1.5 RC)-103/0( DD+9). Span Length-208 mtr
568 | 400 KV D/C Maithan - Jamshedpur(TATA) (TL -(316-317) | 2019-04-02 | 8:00 | 2019-04-03 | 17:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 85/0 (DD+25)-86/0( DD+25+1.5 RC). Span Length-262 mtr
569 | 132 KV D/C Purulia - Jamshedpur (TL-104-105) | 2019-04-05 | 8:00 | 2019-04-06 | 17:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 95/0 (DD+9)-96/0( DD+18). Span Length-258 mtr
562
563
564
565
566
567
568
569
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
* | Detail paln of insulator replacement must be submitted
Outages approved in other RPCs requiring ERPC approval
Sl No | Name of Elements | From |  | To |  | Basis | outages proposed in | Reason | Remarks
|  | Date | Time | Date | Time
1
2
3
4
5
6
7
8
9
10

## Sheet2
SL. No | NAME OF THE ELEMENTS | DATE | TIME | DATE | TIME | REMARKS | S.D availed BY | Reason | SUBJECT TO CONSENT FROM AGENCY | COMMENT
334 | 400KV D/C Farakka - Gokarna Ckt-I & II | 2019-04-04 | 8:00 | 2019-04-05 | 18:00 | OCB | POWERGRID ER-I | for termination with Farakka & Gokarna line of 400KV D/C Rajarhat-Purnea Line (Bihar Section) | WB
60 | 220 KV Bus 1&2 with siliguri 1&2, Birpara1&2, Bus sectionalizer 1&2 | 2019-04-13 | 9:00 | 2019-04-13 | 15:00 | ODB | Powergrid, ER-II | for stringing of Jackbus of 315 MVA ICT#3(Construction package-Techno) under ERSS-XVII | WB | MAY BE AVOIDED ON ELECTION DAYS
5 | 400KV BERHAMPORE-SAGARDIGHI-1 | 2019-04-12 | 9:00 | 2019-04-13 | 17:00 | ODB | Powergrid, ER-II | Line Maintenance | WB
8 | 400KV BERHAMPORE-SAGARDIGHI-1 | 2019-04-18 | 9:00 | 2019-04-18 | 17:00 | ODB | Powergrid, ER-II | Line Maintenance | WB
9 | 400KV BERHAMPORE-SAGARDIGHI-2 | 2019-04-20 | 9:00 | 2019-04-20 | 17:00 | ODB | Powergrid, ER-II | Line Maintenance | WB
12 | 400KV SAGARDIGHI-JEERAT LINE | 2019-04-24 | 9:00 | 2019-04-25 | 17:00 | ODB | Powergrid, ER-II | Live line defects attending and defective isulator replacement in line.. | WB
13 | 400KV SAGARDIGHI-SUBHASGRAM LINE | 2019-04-29 | 9:00 | 2019-04-30 | 17:00 | ODB | Powergrid, ER-II | Live line defects attending and defective isulator replacement in line. | WB
16 | 400KV RAJARHAT-JEERAT | 2019-03-25 | 10:00 | 2019-03-25 | 18:00 | ODB | Powergrid, ER-II | For erection of Bus Pipe of Gokarna Bay coming below Jeerat Line , shutdown require due to Clearance issue with Jeerat Line. Live line defects attending and defective isulator replacement in line. | WB
17 | 400KV RAJARHAT SUBHASGRAM | 2019-03-28 | 10:00 | 2019-03-29 | 18:00 | ODB | Powergrid, ER-II | For Termination of Farakka Line at Gantry Tower , Clearance issue with Subhashgram Line R-Ph LA Rlacement AT Subhasgram end and live line defects attending and defective isulator replacement in line. | WB
18 | 500MVA ICT-I AT RAJARHAT | 2019-04-06 | 10:00 | 2019-04-06 | 18:00 | ODB | Powergrid, ER-II | For attending LA Counter Jumper Connection i.e to attend BALANCE CONSTRUCTON WORK | WB
28 | 315 MVA ICT#1 at Subhasgram S/s | 2019-04-06 | 9:00 | 2019-04-06 | 17:00 | ODB | Powergrid, ER-II | Retrofitting of Numerical REF Relay | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
29 | 315 MVA ICT#2 at Subhasgram S/s | 2019-04-08 | 9:00 | 2019-04-08 | 17:00 | ODB | Powergrid, ER-II | Retrofitting of Numerical REF Relay | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
30 | 315 MVA ICT#3 at Powergrid,Subhasgram | 2019-04-09 | 9:00 | 2019-04-09 | 17:00 | ODB | Powergrid, ER-II | AMP of 315 MVA ICT#3. | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
31 | 315 MVA ICT#4 at Powergrid,Subhasgram | 2019-04-10 | 9:00 | 2019-04-10 | 17:00 | ODB | Powergrid, ER-II | AMP of 315 MVA ICT#4. | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
32 | 500 MVA ICT#5 at Powergrid,Subhasgram | 2019-04-11 | 9:00 | 2019-04-11 | 17:00 | ODB | Powergrid, ER-II | CSD Commissioing in 414 Bay | WB | CONSENT OF CESC NEEDS TO BE TAKEN BY WBSEB
83 | 220 KV TBC at Malda | 2019-04-01 | 8:00 | 2019-04-30 | 17:00 | OCB | Powergrid, ER-II | ERSS-XVII-B Constructional work | WB | DALKHOLA BUS COUPLER SHALL BE OPENED
84 | 400KV TBC at Malda | 2019-04-01 | 8:00 | 2019-04-30 | 17:00 | OCB | Powergrid, ER-II | ERSS-XVII-B Constructional work | WB | DALKHOLA BUS COUPLER SHALL BE OPENED
88 | 400KV BUS-I at Malda | 2019-04-23 | 8:00 | 2019-04-24 | 17:00 | OCB | Powergrid, ER-II | Isolator closing(ERSS-XVII-B Constructional work) | WB
89 | 400 KV BUS-II at Malda | 2019-04-25 | 8:00 | 2019-04-26 | 17:00 | OCB | Powergrid, ER-II | Isolator closing(ERSS-XVII-B Constructional work) | WB
94 | A/R OF 400 KV Farakka- Sagradighi-II | 2019-04-01 | 9:00 | 31/04/19 | 18:00 | ODB | Powergrid, ER-II | Auto reclose to be kept on Non auto mode from both end for PID testing of insulator. | WB
101 | 400 KV Farakka-Gokarna-I | 2019-04-12 | 9:00 | 2019-04-13 | 18:00 | ODB | Powergrid, ER-II | For Event Logger commissioning (Integration with NTPC system) under ERSS-V. | WB
120 | 220 KV S/C STPS - Chandil TL-(TL-229-230)-WBSETCL | 2019-04-09 | 192:00 | 2019-04-10 | 408:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 83/0 (DD+9)-84/0( DD+9). Span Length-160 mtr | WB/JSEB
229 | 400 KV Chaibasa- KHARAGRPUR-I | 2019-04-04 | 9:30 | 2019-03-05 | 17:30 | ODB | POWERGRID ER-I | Auto reclose checking/testing at Chaibasa end | WB
230 | 400 KV Chaibasa- KHARAGRPUR-II | 2019-04-05 | 9:30 | 2019-03-06 | 17:30 | ODB | POWERGRID ER-I | Auto reclose checking/testing at Chaibasa end | WB
232 | 400/132KV 200 MVA ICT-1 AT LAKHISARAI | 2019-04-04 | 9:00 | 2019-04-05 | 17:00 | OCB | POWERGRID ER-I | Checking of Air Cell & AMP works. 33 kV Tretiary bay will also remain out of service. | BSEB | AFTER 29/04/19(ELECTION DATE)
233 | 400/132KV 200 MVA ICT-2 AT LAKHISARAI | 2019-04-06 | 9:00 | 2019-04-07 | 17:00 | OCB | POWERGRID ER-I | Checking of Air Cell & AMP works. | BSEB | AFTER 29/04/19(ELECTION DATE)
250 | 400 /220 kV 500MVA ICT-III AT GAYA | 2019-04-18 | 9:00 | 2019-04-19 | 18:00 | ODB | POWERGRID ER-I | for commisssioning of CSD work | BSEB | AFTER 13/04/19(ELECTION DATE)
251 | 400 /220 kV 315MVA ICT-II AT GAYA | 2019-04-08 | 9:00 | 2019-04-10 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project. | BSEB | AFTER 13/04/19(ELECTION DATE)
254 | 400 KV BUS-I AT GAYA | 2019-04-01 | 9:00 | 2019-04-06 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project. | BSEB
255 | 400 KV BUS-I AT GAYA | 2019-04-08 | 9:00 | 2019-04-10 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project. | BSEB
256 | 400 KV BUS-II AT GAYA | 2019-04-11 | 9:00 | 2019-04-12 | 18:00 | ODB | POWERGRID ER-I | For uprating of bay equipment under Nabinagar -2 Project. | BSEB
273 | 400KV Bus -I AT PATNA | 2019-04-01 | 9:30 | 2019-04-03 | 17:30 | ODB | POWERGRID ER-I | Stringing of Sky bus under SS03 package of Patna Nabinagar Ckt 1 | BSEB
274 | 400KV Bus 2 AT PATNA | 2019-04-04 | 9:30 | 2019-04-06 | 17:30 | ODB | POWERGRID ER-I | Stringing of Sky bus under SS03 package of Patna Nabinagar Ckt 1 | BSEB
290 | 400KV Bus -I AT PATNA | 2019-04-14 | 9:30 | 2019-04-15 | 17:30 | ODB | POWERGRID ER-I | Dismantling and erection of Bus isolator of Dia of Patna Nabinagar D/C | BSEB
291 | 400KV Bus 2 AT PATNA | 2019-04-16 | 9:30 | 2019-04-17 | 17:30 | ODB | POWERGRID ER-I | Dismantling and erection of Bus isolator of Dia of Patna Nabinagar D/C | BSEB
80 | 132kV BUS-1 at Rangpo | 2019-04-02 | 9:00 | 2019-04-12 | 17:00 | OCB | Powergrid, ER-II | For Bus extension to new Chuzachen bays (Construction works) | SIKKIM
81 | 132kV BUS-2 at Rangpo | 2019-04-14 | 9:00 | 2019-04-24 | 17:00 | OCB | Powergrid, ER-II | For Bus extension to new Chuzachen bays (Construction works) | SIKKIM
82 | 132kV Rangpo Chuzachen and 132kV Rangpo Melli | 2019-04-28 | 8:00 | 2019-04-28 | 18:00 | ODB | Powergrid, ER-II | For new Chuzachen bays LILO (Construction works) | SIKKIM
122 | 132 KV D/C Purulia - Jamshedpur (TL 104- MBE-DA+0—TL 105-MBE-DA+0) ) | 2019-04-17 | 192:00 | 2019-04-18 | 408:00 | ODB | Powergrid, ER-II | For Powerline crossing of 765 KV RMTL-AP 95/0 (DD+9)-96/0( DD+18). Span Length-258 mtr | DVC | AFTER 15/04/19 CHANDIL ASSISTENCE
130 | 500MVA ICT-1 at Maithon SS. | 2019-04-05 | 7:00 | 2019-04-06 | 18:00 | ODB | Powergrid, ER-II | Rectification of MOG, CT replacement Main and X-mer bay, and AMP | DVC/JSEB
55 | 400 KV Malda-New Purnea -I | 2019-04-10 | 8:00 | 2019-04-11 | 17:00 | ODB | S/D required for rectification of OPGW Peak Bend,CT replacement at Malda end | Powergrid, ER-II | NLDC
59 | 400KV Binaguri Rangpo Ckt-1&2 | 2019-04-01 | 9:00 | 2019-04-30 | 17:00 | OCC | Line reconductoring job | Powergrid, ER-II | NLDC | Due to High hydro , SD may not be Feasible. If SD required consent from Teesta & Dickchu other shall be obtained.
63 | 400KV Bus#1 at Binaguri | 2019-04-17 | 9:00 | 2019-04-17 | 17:00 | ODB | GIS bushing erection under 400KV Bus#1under ERSS-XVII | Powergrid, ER-II | NLDC
64 | 400KV Bus#2 at Binaguri | 2019-04-18 | 9:00 | 2019-04-18 | 17:00 | ODB | GIS bushing erection under 400KV Bus#2 under ERSS-XVII | Powergrid, ER-II | NLDC
85 | 400 KV Malda-Purnea-II at Malda | 2019-04-17 | 8:00 | 2019-04-17 | 17:00 | ODB | CT Replacement at Malda end | Powergrid, ER-II | NLDC
10 | 400KV BERHAMPORE-BHERAMARA-1 | 2019-04-22 | 9:00 | 2019-04-23 | 17:00 | ODB | Modified SPS scheme implementation | Powergrid, ER-II | NLDC | Power order of Bheramara poles shall be restricted to 800MW.
11 | 400KV BERHAMPORE-BHERAMARA-2 | 2019-04-24 | 9:00 | 2019-04-25 | 17:00 | ODB | Modified SPS scheme implementation | Powergrid, ER-II | NLDC
146 | 400KV PATNA-BALIA-III | 2019-04-12 | 8:00 | 2019-04-13 | 17:00 | ODB | Power line crossing work of 400 kV Patna - Nabinagar line | POWERGRID ER-I | NLDC | Subject to availability all other lines in ER-NR corridor.
147 | 400KV PATNA-BALIA-IV | 2019-04-12 | 8:00 | 2019-04-13 | 17:00 | ODB | Power line crossing work of 400 kV Patna - Nabinagar line | POWERGRID ER-I | NLDC
153 | 765KV GAYA-BALIA-S/C | 2019-03-26 | 8:00 | 2019-04-10 | 18:00 | ODB | FOR TOWER STRENGTHENING WORK. | POWERGRID ER-I | NLDC | Subject to availability all other lines in ER-NR corridor.
158 | 765 KV S/C Sasaram-Fatehpur | 2019-04-15 | 7:00 | 2019-04-30 | 19:00 | ODB | FOR TOWER STRENTHENING WORK | POWERGRID ER-I | NLDC | Subject to availability all other lines in ER-NR corridor.
209 | 765KV GAYA-BALIA-S/C | 2019-03-26 | 8:00 | 2019-04-10 | 18:00 | ODB | FOR TOWER STRENGTHENING WORK. | POWERGRID ER-I | NLDC | Duplicate entry.
314 | 765 KV S/C Sasaram-Fatehpur | 2019-04-15 | 7:00 | 2019-04-30 | 19:00 | ODB | FOR TOWER STRENTHENING WORK | POWERGRID ER-I | NLDC | Duplicate entry.
339 | 765 kV Sasaram - Fatehpur | 2019-04-01 | 8:00 | 2019-04-08 | 18:00 | ODB | Strengthing of balance suspension towers delta configuration (419 Nos) | POWERGRID NR3 | NLDC | Duplicate entry.
340 | 765 KVGaya - balia | 2019-03-25 | 8:00 | 2019-03-28 | 18:00 | ODB | Strengthening of suspension towers Delta Configuration (82 Nos) | POWERGRID NR3 | NLDC | Duplicate entry.
154 | 400KV BIHARSHARIFF - VARANASI - I | 2019-04-01 | 8:00 | 2019-04-29 | 18:00 | OCB | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | POWERGRID ER-I | NLDC | After return of 400kv Biharsariff-Sasaram D/C
155 | 400KV BIHARSHARIFF - VARANASI - II | 2019-04-01 | 8:00 | 2019-04-29 | 18:00 | OCB | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | POWERGRID ER-I | NLDC
156 | 400KV BIHARSHARIFF - SASARAM- I | 2019-04-01 | 8:00 | 2019-04-25 | 18:00 | OCB | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | POWERGRID ER-I | NLDC
157 | 400KV BIHARSHARIFF - SASARAM- II | 2019-04-01 | 8:00 | 2019-04-25 | 18:00 | OCB | Realingmnet works of 400KV Biharsharif - Varanasi & 400KV Biharsharif - Sasaram Line due to Construction of New Railway Line by ECR from Natesar to Islampur. HVDC SASARAM WILL BE OUT OF SERVICE | POWERGRID ER-I | NLDC
159 | 765 KV S/C Gaya-Varanasi-II | 2019-04-11 | 7:00 | 2019-04-12 | 18:00 | ODB | for rectification of defects identified | POWERGRID ER-I | NLDC | Subject to availability all other lines in ER-NR corridor.
160 | 400 KV RANCHI-SIPAT-1 LINE AND ITS 80 MVAR LINE REACTOR AT RANCHI | 2019-04-22 | 10:00 | 2019-04-22 | 17:00 | ODB | AMP & Replacement of defective CAPTHOR in FSC AND To attend oil leakage in Line Reactor | POWERGRID ER-I | NLDC
162 | 220 kV Pusauli - Sahupuri | 2019-04-02 | 9:00 | 2019-04-05 | 18:00 | OCB | TO FACILITATE THE SHUT DOWN OF ICT - I AT PUSAULI SS | POWERGRID ER-I | NLDC
191 | 400 kV Chandwa-Gaya CKT-I | 2019-04-18 | 9:00 | 2019-04-18 | 18:00 | ODB | For shifting of 33 kV under crossing line of JUSNL (400 kV Chandwa-Gaya T/L Line tripped due to less clearence). | POWERGRID ER-I | NLDC
192 | 400 kV Chandwa-Gaya CKT-II | 2019-04-18 | 9:00 | 2019-04-18 | 18:00 | ODB | For shifting of 33 kV under crossing line of JUSNL (400 kV Chandwa-Gaya T/L Line tripped due to less clearence). | POWERGRID ER-I | NLDC
260 | 400 kV Maithon-Gaya-1 | 2019-04-02 | 9:00 | 2019-04-28 | 18:00 | OCB | Destringing, erection & re-stringing of multi ckt. Tower Loc. 80 | POWERGRID ER-I | NLDC
261 | 400 kV Maithon-Gaya-2 | 2019-04-02 | 9:00 | 2019-04-28 | 18:00 | OCB | Destringing, erection & re-stringing of multi ckt. Tower Loc. 80 | POWERGRID ER-I | NLDC
262 | 400 kV Koderma-Gaya-1 | 2019-04-02 | 9:00 | 2019-04-28 | 18:00 | OCB | Destringing, erection & re-stringing of multi ckt. Tower Loc. 80 | POWERGRID ER-I | NLDC
263 | 400 kV Koderma-Gaya-2 | 2019-04-02 | 9:00 | 2019-04-28 | 18:00 | OCB | Destringing, erection & re-stringing of multi ckt. Tower Loc. 80 | POWERGRID ER-I | NLDC
269 | 400KV Barh- Motihari CKT-1 | 2019-04-01 | 8:00 | 2019-04-29 | 18:00 | OCB | Realingmnet works of 400KV Barh- Motihari Line due to Construction of Barh Bypass by NHAI | POWERGRID ER-I | NLDC | Shutdown requset shall be submitted along with work schedule & Skectch of line diversion work & after return of 400KV BSF-SASARAM D/C | AFTER BSF SASARAM
270 | 400KV Barh- Motihari CKT-II | 2019-04-01 | 8:00 | 2019-04-29 | 18:00 | OCB | Realingmnet works of 400KV Barh- Motihari Line due to Construction of Barh Bypass by NHAI | POWERGRID ER-I | NLDC
271 | 400KV BARH- PATNA CKT - 3 & 4 | 2019-04-04 | 8:00 | 2019-04-06 | 18:00 | ODB | Realingmnet works of 400KV Barh- Motihari Line due to Construction of Barh Bypass by NHAI | POWERGRID ER-I | NLDC
272 | 400KV BARH - PATNA CKT 3 & 4 | 2019-04-27 | 8:00 | 2019-04-29 | 18:00 | ODB | Realingmnet works of 400KV Barh- Motihari Line due to Construction of Barh Bypass by NHAI | POWERGRID ER-I | NLDC
308 | 400KV PATNA-BALIA-III | 2019-04-12 | 8:00 | 2019-04-12 | 17:00 | ODB | Power line crossing work of 400 kV Patna - Nabinagar line | POWERGRID ER-I | NLDC | Duplicate entry.
309 | 400KV PATNA-BALIA-IV | 2019-04-13 | 8:00 | 2019-04-13 | 17:00 | ODB | Power line crossing work of 400 kV Patna - Nabinagar line | POWERGRID ER-I | NLDC | Duplicate entry.
315 | 765 KV S/C Gaya-Varanasi-II | 2019-04-11 | 7:00 | 2019-04-12 | 18:00 | ODB | for rectification of defects identified by corporate AM department. | POWERGRID ER-I | NLDC | Duplicate entry.
341 | 220 kV Sasaram - Sahupuri | 2019-04-02 | 9:00 | 2019-04-05 | 18:00 | OCB | TO FACILITATE THE SHUT DOWN OF ICT - I AT PUSAULI SS | POWERGRID ER-I | NLDC
187 | 400 kV Jeypore-Indravati S/C Line | 2019-04-10 | 8:00 | 2019-04-11 | 18:00 | ODB | For testing New A/R relayof Jeypore - Indravati Line & For PID defect insulator replacement work | ER-II/Odisha /Jeypore | NLDC
188 | 400 KV Indravati-Rengali line | 2019-04-05 | 9:00 | 2019-04-05 | 17:00 | ODB | Oil leakage from the reactor.For removal of 50MVAR LR of Rengali-Indravati Line from service, Opening of Jumpers for replacement of Gaskets of bushings.Line conductor is just above the reactor.Due to crane movement during maintenance of the reactor line shutdown is required . | ER-II/Odisha/Indravati | NLDC | All shutdwons pertains to SR TTC curtailment may be reshceduled after 15th Apr 19.(SR DEMAND REDUCTION)
189 | 400 KV Indravati-Rengali line | 2019-04-06 | 9:00 | 2019-04-06 | 17:00 | ODB | Removal of bushings and Replacement of Gaskets. And placing of bushings after replacement of gaskets. Line conductor is just above the reactor.Due to crane movement during maintenance of the reactor line shutdown is required . | ER-II/Odisha/Indravati | NLDC
190 | 400KV Balangir-Angul Line | 2019-04-14 | 8:00 | 2019-04-16 | 18:00 | ODB | Replacement of defective insulator by Polymer long Rod Insulator | ER-II/Odisha/Balangir | NLDC
52 | 400KV Balangir-Jeypore Line | 2019-04-12 | 8:00 | 2019-04-13 | 18:00 | ODB | Replacement of defective insulator by Polymer long Rod Insulator | ER-II/Odisha/Balangir | NLDC |  | AFTER SEPT HYDRO
53 | 765KV Angul-Srikakulam ckt-I | 2019-03-26 | 7:00 | 2019-03-27 | 18:00 | ODB | AMP Work | ER-II/Odisha/Nyg&Bmp TLAM | NLDC | All shutdwons pertains to SR TTC may be reshceduled after 15th Apr 19.
121 | 765KV Angul-Srikakulam ckt-II | 2019-03-28 | 7:00 | 2019-03-29 | 18:00 | ODB | AMP Work | ER-II/Odisha/Nyg&Bmp TLAM | NLDC |  | ?
345 | 765KV Angul-Srikakulam ckt-I | 2019-04-01 | 7:00 | 2019-04-02 | 18:00 | ODB | AMP Work-Shutdown is required if not granted in March 2019 | ER-II/Odisha/Nyg&Bmp TLAM | NLDC
| 765KV Angul-Srikakulam ckt-II | 2019-04-03 | 7:00 | 2019-04-04 | 18:00 | ODB | AMP Work-Shutdown is required if not granted in March 2019 | ER-II/Odisha/Nyg&Bmp TLAM | NLDC
| 400KV New Ranchi- Ranchi Ckt-3 | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | For Insulation sleeve installation work at Loc 054-055 OF 400 kV Ranchi-New Ranchi CKT-3 & 4. | POWERGRID ER-I
| 400KV New Ranchi- Ranchi Ckt-4 | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | For Insulation sleeve installation work at Loc 054-055 OF 400 kV Ranchi-New Ranchi CKT-3 & 4. | POWERGRID ER-I
| 400kv Ranchi-Maithan(PG) -s/c | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | For Insulation sleeve installation work at Loc 054-055 OF 400 kV Ranchi-New Ranchi CKT-3 & 4. | POWERGRID ER-I
| 400 kv Ranchi-Raghunathpur -I | 2019-04-12 | 9:00 | 2019-04-12 | 18:00 | ODB | For Insulation sleeve installation work at Loc 054-055 OF 400 kV Ranchi-New Ranchi CKT-3 & 4. | POWERGRID ER-I | DVC
| 220KV SILIGURI-KISHENGUNJ # I & II | 2019-04-03 | 8:00 | 2019-04-04 | 17:00 | OCB | For shorting at Anch-I tower (M/C)to by-pass the LILO portion of 220KV SLG-KNE-DLK -I&II line terminating Kishanganj S/S . This arrangement required for tower erection on new Pile foundation near Kishanganj S/S. After shoring line will be established as 220KV SLG-DLK line . Antipacted outage duration of LILO M/C portion feeding Kishanganj S/S 40 days. | Powergrid, ER-II
| 220KV DALKHOLA-KISHENGUNJ # I & II | 2019-04-03 | 8:00 | 2019-04-04 | 17:00 | OCB | For shorting at Anch-I tower (M/C)to by-pass the LILO portion of 220KV SLG-KNE-DLK -I&II line terminating Kishanganj S/S . This arrangement required for tower erection on new Pile foundation near Kishanganj S/S. After shoring line will be established as 220KV SLG-DLK line . Antipacted outage duration of LILO M/C portion feeding Kishanganj S/S 40 days. | Powergrid, ER-II
| 400 KV D/C Maithan - Jamshedpur(TATA) (TL -(316-317) | 2019-04-11 | 192:00 | 2019-04-12 | 408:00 | ODB | For Powerline crossing of 765 KV RMTL-AP 85/0 (DD+25)-86/0( DD+25+1.5 RC). Span Length-262 mtr | Powergrid, ER-II
| New 400KV Bus#2 & 400 KV Bus#4 | 2019-04-03 | 8:00 | 2019-04-03 | 18:30 | ODB | For 400 KV Bus Sectionalizer Bay#2 commissioning | KAHALGAON

## Sheet3
SL. No | NAME OF THE ELEMENTS | DATE | TIME | DATE | TIME | REMARKS | S.D availed BY | Reason | SUBJECT TO CONSENT FROM AGENCY | COMMENT
246 | 400KV Biharsarif - Koderma CKT -I | 2019-04-23 | 9:00 | 2019-04-24 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | DVC
247 | 400KV Biharsarif - Koderma CKT -II | 2019-04-25 | 9:00 | 2019-04-26 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | DVC
248 | 400kV Koderma - Bokaro CKT -I | 2019-04-03 | 9:00 | 2019-04-03 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | DVC
249 | 400kV Koderma - Bokaro CKT -II | 2019-04-04 | 9:00 | 2019-04-04 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | DVC
144 | 400KV PATNA-BALIA-I | 2019-04-10 | 8:00 | 2019-04-10 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer | NLDC
145 | 400KV PATNA-BALIA-II | 2019-04-11 | 8:00 | 2019-04-11 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer | NLDC
148 | 765 kV New Ranchi - Dharamjaygarh CKT-II | 2019-04-23 | 9:00 | 2019-04-27 | 18:00 | ODB | POWERGRID ER-I | for replacement of broken Glass insulators damaged by miscreants about 140 nos. locations | NLDC
149 | 400KV BIHARSHARIFF-BALIA-I | 2019-04-23 | 8:00 | 2019-04-24 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
150 | 400KV BIHARSHARIFF-BALIA-II | 2019-04-25 | 8:00 | 2019-04-26 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
151 | 400KV PATNA-BALIA-I | 2019-04-27 | 8:00 | 2019-04-27 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
152 | 400KV PATNA-BALIA-II | 2019-04-28 | 8:00 | 2019-04-28 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
161 | 765 kV Gaya-Varanasi-2 | 2019-04-23 | 9:00 | 2019-04-24 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant. | NLDC
205 | 400KV BIHARSHARIFF-BALIA-I | 2019-04-23 | 8:00 | 2019-04-24 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
206 | 400KV BIHARSHARIFF-BALIA-II | 2019-04-25 | 8:00 | 2019-04-26 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
207 | 400KV PATNA-BALIA-I | 2019-04-27 | 8:00 | 2019-04-27 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
208 | 400KV PATNA-BALIA-II | 2019-04-28 | 8:00 | 2019-04-28 | 18:00 | ODB | POWERGRID ER-I | for replacement of porcelain insulator by polymer insulator | NLDC
142 | 400KV Mejia-Jamshedpur line | 2019-04-10 | 9:00 | 2019-04-11 | 18:.00 | ODB | Powergrid, ER-II | Insulator replacement work. | DVC
306 | 400KV PATNA-BALIA-I | 2019-04-10 | 8:00 | 2019-04-10 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer | NLDC
307 | 400KV PATNA-BALIA-II | 2019-04-11 | 8:00 | 2019-04-11 | 17:00 | ODB | POWERGRID ER-I | Replacement of Porcelain Insulator with polymer | NLDC
416 | A/R OF 400kV Sundargarh-Raigarh Ckt#1 | 2019-04-02 | 8:00 | 2019-04-14 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | For PID Testing of Porcelain Insulator. Only Auto reclose relay will be off. Line will be in service | NLDC
417 | A/R OF 400kV Sundargarh-Raigarh Ckt#3 | 2019-04-15 | 8:00 | 2019-04-30 | 18:00 | ODB | ER-II/ODISHA/SUNDERGARH | For PID Testing of Porcelain Insulator. Only Auto reclose relay will be off. Line will be in service | NLDC
50 | 400 KV Binaguri-Tala Ckt-III | 2019-04-17 | 8:00 | 2019-04-17 | 17:30 | ODB | Powergrid, ER-II | Broken Insulator Replacement,Line defect rectification & Line AMP works. | NLDC
51 | 400 KV Binaguri-Tala Ckt-IV | 2019-04-18 | 8:00 | 2019-04-18 | 17:30 | ODB | Powergrid, ER-II | Broken Insulator Replacement,Line defect rectification & Line AMP works. | NLDC
335 | 400KV Kahalgaon - Maithan - I | 2019-04-08 | 9:00 | 2019-04-14 | 17:00 | ODB | POWERGRID ER-I | for Replacement of PID detected defect insulator with Polymer Insulator
336 | 400KV Kahalgaon - Maithan - II | 2019-04-15 | 9:00 | 2019-04-21 | 17:00 | ODB | POWERGRID ER-I | for Replacement of PID detected defect insulator with Polymer Insulator
406 | 400 KV Rourkela-Talcher Line # 1 Auto reclose in Non-Auto Mode | 2019-04-01 | 8:00 | 2019-04-10 | 17:00 | ODB | ER-II/Odisha/Rengali | For PID Work
407 | 400 KV Rourkela-Talcher Line # 2 in Non-Auto Mode | 2019-04-11 | 8:00 | 2019-04-30 | 17:00 | ODB | ER-II/Odisha/Rengali | For PID Work
259 | 400 kV Chandwa-Gaya-2 | 2019-04-09 | 9:00 | 2019-04-10 | 18:00 | ODB | POWERGRID ER-I | For Replacement of Insulators Damaged by Miscreant.
141 | 400KV Maithon-Jamshedpur line. | 2019-04-08 | 9:00 | 2019-04-09 | 18:.00 | ODB | Powergrid, ER-II | Insulator replacement work.
171 | 400kV JSR - Baripada S/C | 2019-04-19 | 9:30 | 2019-04-19 | 17:30 | ODB | POWERGRID ER-I | Defective Insulator replacement work Loc no 241